## Instructions
|  | Capital Planning Business Case Lite | 2011-07-27
Description
1 | This template is used to create Biz-Lite business cases for all capital projects above $100K CAPEX. For projects below 100K this is not needed, please file CER directly
2 | For projects between $100K and $500K CAPEX please consult with Capital Planning if you need any help with the template
3 | For projects beyond $500K in CAPEX please work closely with Capital Planning to develop Biz-Lite
Overall Instructions
1 | Review Definitions and Assumptions Section
2 | Review instructions for Project Scope and Objectives
3 | Review instructions for Financial Assumptions
4 | Review instructions for Project Metrics
5 | Enter data in the green highlighted cells.
Instructions - Project Scope and Objectives Section
1 | Enter the project title
2 | Select Business Sponsor from the drop down menu (review definitions)
3 | Enter the name of the project sponsor
4 | Enter "All" if all divisions will be impacted, "None" if no divisions are impacted, or division name if a specific division is impacted as a result of underataking the project
5 | Select the initiative type
6 | Enter the date Biz-Lite is being prepared
7 | Select the primary project support function from the drop down menu (review definitions)
8 | Enter the name of the primary support lead
9 | Select the primary company strategy to which the project is aligned to
10 | Select the secondary company strategy to which the project is aligned to
11 | Enter a brief description of the project objectives
12 | Enter a brief description of the project scope
Instructions - Financial Assumptions
1 | Enter one time benefits due to project implementation e.g. Sale of old equipment
2 | Enter recurring benefits due to project implementation e.g. Increased profits, reduced expenses
3 | Enter assumptions used to determine benefits e.g. growth rate per year
4 | Enter one time operating expenses without depreciation. E.g One time restructuring fees
5 | Enter recurring operating expenses without depreciation E.g. Employee payroll
6 | Enter one time capital expenes e.g. IT licensing costs, warehouse modification cost
7 | Enter recurring capital expenes e.g. Maintenance fees for IT servers/software
8 | Enter decrease in working capital. Enter a negative number is there is an increase in working capital
9 | Enter assumptions used to determine expenses e.g. RFQs used from vendors
Instructions - Metrics Section
1 | Enter expected start date
2 | Enter expected end date
3 | Select project priority (refer definitions)
4 | Enter all qualitative benefits
5 | Enter all risks
6 | Enter alternatives
7 | Enter comments if any
8 | Enter secondary metrics for RE/IT/SCM only if needed
Contacts
1 | Rishi Potdar - Capital Planning
2 | Harlan Kowitt - Supply Chain
3 | Ann Vechionne - Sales
4 | John Svelnis - IT Strategy
5 | Colin Quinn - Procurement Finance
6 | Stephen Down - Broadline Finance
7 | TBD
8 | TBD

## Definitions and Assumptions
2012 Capital Planning Business Case Lite
Definitions and Assumptions
| Project Scope and Objectives | Description
1 | Project Title | Title of the project
2 | Business Sponsor | The business function sponsoring the project, the owner of the project, accountable for the eventual return
3 | Project Sponsor | Name of the person sponsoring the project
4 | Divisions impacted | Either all divisions or list any specific divisions
5 | Initiative type - New | A completely new initiative e.g. a new warehouse
6 | Initiative type - Maintenance | Maintenance projects such as rolling stock
7 | Initiative type - Retrofit | Retrofit projects such as adding skirts to trailers to improve efficiency
8 | Initiative type - Upgrades | Applicable to IT only, primarily for server/software upgrades
9 | Primary Project Support | The primary function responsible for implementing the project. E.g. IT implementing a new software, jointly responsible for the return
10 | Primary Support Lead | Name of the person providing primary support
11 | Company Strategy - Growth | Select this option if the project is driven by sales/market growth related opportunities e.g. CRM implmentation
12 | Company Strategy - Cost Reduction | Select this option if the project is driven by cost reduction opportunities e.g. Slot Automation
13 | Company Strategy - Competitive Response | Select this option if the project is driven as a result of competition e.g. POD
14 | Company Strategy - Mandatory Projects | Select this option if the project is a mandatory project e.g. Health/Safety
15 | Company Strategy - Strategy Pyramid | Select this option if the project is driven by the strategy pyramid
16 | Company Strategy - Process Automation | Select this option if the project is driven by process automation
| Project Metrics | Description
1 | Terminal Value | Present value of future EBITDA at a steady growth rate, Final Year EBITDA times 8
2 | Discount rate | WACC, 10%
3 | IRR | Pre-tax IRR - calculated as IRR of all cash flows including terminal value
4 | NPV | NPV is the present value of all cash flows not adjusted for inflation including terminal value
5 | Payback period | Payback period is the year in which the cumulative cash flow turns positive
6 | ROIC | Return on invested capital - Year 5 EBITDA divided by total Capex not adjusted for inflation
7 | Balanced Scorecard | A weighted scorecard used to calculate the score of the project for ranking purposes
Balanced scorecard used with 75% weightage on quantitative benefits and 25% on qualitative benefits and risks
Maximum score of quantitative benefits is 15.0 and qualitative benefits is 12.5 with a total maximum of 27.50
IRR: >50%,5; >40%,4; >30%,3, >20%,2, >10%, 1 else 0
NPV: >20,000,5; >15,000,4; >10,000,3;> 5,000,2; >1,000,1; else 0
Payback period: less than 1 year,5; less than 2 years,4; less than 3 years ,3; less than 4 years is 2; less than 5 years is 1, else 0
ROIC: Greater than 50%,5; greater than 40%,4; greater than 30%,3, greater than 20%,2, greater than 10% is 1, else 0
8 | Priority | This is not used to rank the project, only used for project sequencing of approved projects
9 | Qualitative Benefits - Customer Satisfaction | Project impacts customer satisfaction e.g. POD select 3 (high)or 2(medium) or 1(low)
10 | Qualitative Benefits - Supplier Satisfaction | Project impacts supplier satisfaction e.g. New Payables Process select 3 (high) or 2(medium) or 1(low)
11 | Qualitative Benefits - Competitive Perception | Project changes competitive perception e.g. Pricing Intelligence select 3 (high) or 2(medium) or 1(low)
12 | Qualitative Benefits - Regulatory Perception | Project changes regulatory perception e.g. New Amonia System select 3 (high) or 2(medium) or 1(low)
13 | Qualitative Benefits - Strategy Alignment | Project aligned to corporate strategy e.g. Oil 2.0 select 3 (high) or 2 (medium) or 1 (low)
14 | Qualitative Benefits - Organizational Effectiveness | Project impacts organizational effectiveness e.g. Office foundations select 3 (high) or 2(medium) or 1(low)
15 | Qualitative Benefits - Level of confidence | Degree of confidence of the financials provided select 3 (high) or 1(low) or 2(medium)
16 | Risks - Scope Change/Complexity | A complex project with a possibility of scope changes. E.g. ERP implementation
17 | Risks - Expected Resource Constraints | Specialized skills/resource requirements which may be hard to obtain
18 | Risks - Change Management | Project needs change management
19 | Risks - Leadership Engagement | Leadership involvement and support in the project
20 | Alternatives - Status Quo | Is the status quo acceptable
21 | Alternative 2, 3 | What alternatives are available if the project is not approved other than status quo
22 | Function Specific Metrics | Projects may have additional metrics such as cases/hour, cases/mile - identify them, not used in scoring

## Business Case Financial
Capital Planning Business Case
Benefits (not adjusted for inflation) | [8 empty] | Expected Start
Expected End
Benefits | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |  | Elapsed Time | 0
One-time Benefits
As-Is Process Flow | 0 | [7 empty] | Balanced Score | #NUM!
To-Be Process Flow | 0
To-Be IT Architecture Vision | 0
Ongoing Benefits | [8 empty] | Priority | Medium
As-Is Process Flow | 0 | 0 | 0 | 0 | 0 | 0
To-Be Process Flow | 0 | 0 | 0 | 0 | 0 | 0 |  |  | (Not used for Scoring)
To-Be IT Architecture Vision | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Quantitative Benefits |  | Score
Total Benefits | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Pre-tax IRR | #NUM! | #NUM!
[9 empty] | NPV (10%) | 0 | 0
Operating Expenses - Excluding depreciation (not adjusted for inflation) | [8 empty] | Payback Period | Beyond 5 | 0
[9 empty] | Post-tax IRR | #NUM! | #NUM!
Expenses | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |  | Return on Investment | #DIV/0!
One-time Benefits
As-Is Process Flow | 0 | [7 empty] | Qualitative Benefits | (1 is low, 5 is high)
To-Be Process Flow | 0 | [7 empty] | Customer Satisfaction
To-Be IT Architecture Vision | 0 | [7 empty] | Supplier Satisfaction
Ongoing Benefits | [8 empty] | Competitive Response
As-Is Process Flow | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Regulatory/Compliance
To-Be Process Flow | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Strategy Alignment
To-Be IT Architecture Vision | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Organizational Effectiveness
Total Opex ex Depr | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Risks | (1 is high, 5 is low)
EBITDA | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Scope Change/Complexity
Expected Resource Constraints
Capital Expenses - (not adjusted for inflation) | [8 empty] | Leadership Engagement
Time to complete
Expenses | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Benefits | [8 empty] | Alternatives
As-Is Process Flow | 0 | [7 empty] | Status Quo | Yes
To-Be Process Flow | 0 | [7 empty] | Alternative 2 | None
To-Be IT Architecture Vision | 0 | [7 empty] | Alternative 3 | None
Ongoing Benefits
As-Is Process Flow | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Comments
To-Be Process Flow | 0 | 0 | 0 | 0 | 0 | 0 |  |  | [Enter Comments on Benefits and Risks]
To-Be IT Architecture Vision | 0 | 0 | 0 | 0 | 0 | 0
Total Capex | 0 | 0 | 0 | 0 | 0 | 0
|  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
EBITDA |  | 0 | 0 | 0 | 0 | 0 | 0
Depreciation (adjust Depreciable life) |  | 0 | 0 | 0
EBIT |  | 0 | 0 | 0 | 0 | 0 | 0
Taxes (40%) |  | 0 | 0 | 0 | 0 | 0 | 0
Earning After Taxes |  | 0 | 0 | 0 | 0 | 0 | 0
Capital |  | 0 | 0 | 0 | 0 | 0 | 0
Decrease(Increase) in Working Capital | [8 empty] | Function Specific Metrics (Only if needed)
Pre-Tax Cash Flow (includes terminal Value) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Please enter any specific metrics only if needed
Post-Tax Cash Flow (includes terminal Value) |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Please enter any specific metrics only if needed
Please enter any specific metrics only if needed
| Pre Tax IRR | #NUM! | [6 empty] | Please enter any specific metrics only if needed
| Post tax IRR | #NUM! | [6 empty] | Please enter any specific metrics only if needed
Cumulative Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0
Year |  | 1 | 2 | 3 | 4 | 5 | 6
Payback Period Calculation |  | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!

## As-Is Process Flow
Business Case Financial Planning for As-Is Process Flow
Benefits ($s thousands, not adjusted for inflation)
| Benefits | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Benefits
| Enter information | Enter information | 0
| Enter information | Enter information | 0
| Enter information | Enter information | 0
| Enter information | Enter information | 0
Ongoing Benefits
| Enter information | Enter information | 0 | 0 | 0 | 0 | 0 | 0
| Enter information | Enter information | 0
| Enter information | Enter information | 0
| Enter information | Enter information | 0
| Total Benefits | Total Benefits | 0 | 0 | 0 | 0 | 0 | 0
Benefit Assumptions
Operating Expenses - Excluding depreciation ($s thousands, not adjusted for inflation)
| Expenses | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Opex - Ex Depr
| Enter information | Enter information | 0
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Opex - Ex Depr
| Enter information | Enter information |  | 0 | 0 | 0 | 0 | 0
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Opex ex Depr | Total Opex | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenses Assumptions
Capital Expenses - ($s thousands, not adjusted for inflation)
| Expenses | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Capex
| Enter information | Enter information | 0
| Enter information | Enter information | 0
| Enter information | Enter information | 0
| Enter information | Enter information | 0
Ongoing Capex
| Enter information | Enter information | 0 | 0 | 0 | 0 | 0 | 0
| Enter information | Enter information | 0 | 0 | 0 | 0 | 0 | 0
| Enter information | Enter information | 0 | 0 | 0 | 0 | 0 | 0
| Enter information | Enter information | 0 | 0 | 0 | 0 | 0 | 0
| Total Capex | Total Capex | 0 | 0 | 0 | 0 | 0 | 0
Capital Expenses Assumptions

## To-Be Process Flow
Business Case Financial Planning for To-Be Process Flow
Benefits ($s thousands, not adjusted for inflation)
| Benefits | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Benefits
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Benefits
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Benefits | Total Benefits | 0 | 0 | 0 | 0 | 0 | 0
Benefit Assumptions
Operating Expenses - Excluding depreciation ($s thousands, not adjusted for inflation)
| Expenses | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Opex - Ex Depr
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Opex - Ex Depr
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Opex ex Depr | Total Opex | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenses Assumptions
Capital Expenses - ($s thousands, not adjusted for inflation)
| Expenses | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Capex
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Capex
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Capex | Total Capex | 0 | 0 | 0 | 0 | 0 | 0
Capital Expenses Assumptions

## To-Be IT Architecture Vision
Business Case Financial Planning for To-Be IT Architecture Vision
Benefits ($s thousands, not adjusted for inflation)
| Benefits | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Benefits
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Benefits
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Benefits | Total Benefits | 0 | 0 | 0 | 0 | 0 | 0
Benefit Assumptions
Operating Expenses - Excluding depreciation ($s thousands, not adjusted for inflation)
| Expenses | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Opex - Ex Depr
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Opex - Ex Depr
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Opex ex Depr | Total Opex | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenses Assumptions
Capital Expenses - ($s thousands, not adjusted for inflation)
| Expenses | Details | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
One-time Capex
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
Ongoing Capex
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Enter information | Enter information
| Total Capex | Total Capex | 0 | 0 | 0 | 0 | 0 | 0
Capital Expenses Assumptions