## Sheet2
Estimated Duration (in weeks) | 39
Estimated Start Date | 2022-07-05
Blinded Rate | 100
Project Type | COTS/SaaS

## Sheet1
Phases | APPDev | COTS | Risk
Initiating | 3% | 3% | 1%
Plan | 7% | 7% | 5%
Selection | 0% | 5% | 3%
Define | 25% | 9% | 10%
Design |  | 12%
Construct |  | 15%
Build | 45% | 30% | 20%
Test | 15% | 15% | 30%
Deploy | 8% | 6% | 10%
Close |  | 1%

## Document
Planning Cost |  | Planning Schedule | Start Date | End Date
|  |  | 0 | 1900-01-24
#REF! | #REF! | #REF! | #REF! | #REF!
Coordinate and Collaborate with Relevant Stakeholders (User Story) | 1310.4 | Coordinate and Collaborate with Relevant Stakeholders (User Story) | 0 | 1900-01-02
Align Measurement and Analysis Activities (User Story) | 1419.6 | Align Measurement and Analysis Activities (User Story) | 0 | 1900-01-02
Establish Estimates (User Story) | 1419.6 | Establish Estimates (User Story) | 0 | 1900-01-02
Develop a Project Plan (User Story) | 1419.6 | Develop a Project Plan (User Story) | 0 | 1900-01-02
Obtain Commitment to the Plan (User Story) | 1092 | Obtain Commitment to the Plan (User Story) | 0 | 1900-01-01
Prepare for Quantitative Management (User Story) | 1092 | Prepare for Quantitative Management (User Story) | 0 | 1900-01-01
Prepare for Risk Management (User Story) | 1092 | Prepare for Risk Management (User Story) | 0 | 1900-01-01
Planning Risk | #VALUE! | Planning Risk | 0 | #VALUE!
| #REF! | Planning Completed | #VALUE!

## COTS (2)
Line Number | Task Name | [6 empty] | Resource Names |  | Percent |  |  |  |  | Estimated Hours |  |  |  | Estimated Cost |  |  |  | Projected Cost |  |  |  | Cost Gap | Estimated Days | Estimated Duration | Depend | Start date | End date | Risk Date
1 | Solution Backlog | [5 empty] | Solution Backlog |  |  | 0.12 | [8 empty] | 18720 | [11 empty] | 2022-07-05 | 2023-04-04
2 | 1.1 | Entrance Criteria | [28 empty] | 2022-07-05 | 2022-07-05
3 |  | 1.1.1 | Approved Project Business Case
4 |  | 1.1.2 | Development Process Design Document
5 |  | 1.1.2 | Scheduled on Portfolio Roadmap | [27 empty] | 2022-07-05 | 2022-07-05
6 | 1.2 | COTS Initiating Process |  |  |  |  | COTS Initiating Process |  |  | 3% | 104.5% |  |  |  | 46.8 |  |  |  | $4680 - $4890.6 | [8 empty] | 7.8 | 7.8 |  | 0
7 |  | 1.1.1 | Coordinate and Collaborate with Relevant Stakeholders (User Story)
8 |  | 1.1.2 | Develop Preliminary Project Plan (User Story) |  |  |  | Develop Preliminary Project Plan (User Story) |  | ü |  | 26% |  |  |  |  | 12.168 |  |  |  | 1216.8 | [9 empty] | 3 | 0 | 0
9 |  | 1.1.3 | Perform Preliminary Project Plan Peer Review (User Story) |  |  |  | Perform Preliminary Project Plan Peer Review (User Story) |  |  |  | 10% | #REF! |  |  |  | 4.68 |  |  |  | 468 | [9 empty] | 4 | 0 | 1900-01-09
10 |  | 1.1.4 | Review and Approve Preliminary Project Plan (User Story) |  |  |  | Review and Approve Preliminary Project Plan (User Story) |  |  |  | 5% | #REF! |  |  |  | 2.34 |  |  |  | 234 | [9 empty] | 6 | 0 | 0
11 |  | 1.1.5 | Develop Project Charter (User Story) |  |  |  | Develop Project Charter (User Story) |  | ü |  | 36% |  |  |  |  | 16.848 |  |  |  | 1684.8 | [10 empty] | 0 | 0
12 |  | 1.1.6 | Perform Project Charter Peer Review (User Story) |  |  |  | Perform Project Charter Peer Review (User Story) |  | ü |  | 10% | #REF! |  |  |  | 4.68 |  |  |  | 468 | [9 empty] | 4 | 0 | 1900-01-09
13 |  | 1.1.7 | Review and Approve Project Charter (User Story) |  |  |  | Review and Approve Project Charter (User Story) |  |  |  | 5% | #REF! |  |  |  | 2.34 |  |  |  | 234 | [9 empty] | 6 | 0 | 0
14 |  | 1.1.8 | Develop Project Planning Schedule (User Story) | [7 empty] | 8% |  |  |  |  | 3.744 |  |  |  | 374.4
15 |  | 1.1.9 | Initiating Risk | [7 empty] | 4.5% |  |  |  |  | 2.106 |  |  |  | 210.6 |  |  | #REF! | [5 empty] | #REF! |  | 0 | #REF!
16 |  | 1.1.10 | COTS Initiating Process Completed | [27 empty] | 0 | 0
17 | 1.3 | COTS Planning Process | [7 empty] | 7% | 91% |  |  |  | 109.2 |  |  |  | 10920 |  |  |  | 18.2 |  |  |  |  | 18.2 | 18.2 | 5 | 0 | 1900-01-24
18 |  | 1.3.2 | Coordinate and Collaborate with Relevant Stakeholders (User Story) | [7 empty] | 12% |  |  |  |  | 13.104 |  |  |  | 1310.4 | [7 empty] | 2.184 | 2.2 | 64 | 0 | 1900-01-02
19 |  | 1.3.3 | Align Measurement and Analysis Activities (User Story) | [7 empty] | 13% |  |  |  |  | 14.196 |  |  |  | 1419.6 | [7 empty] | 2.366 | 2.4 | 71 | 0 | 1900-01-02
20 |  | 1.3.4 | Establish Estimates (User Story) | [7 empty] | 13% |  |  |  |  | 14.196 |  |  |  | 1419.6 | [7 empty] | 2.366 | 2.4 | 76 | 0 | 1900-01-02
21 |  | 1.3.5 | Develop a Project Plan (User Story) | [7 empty] | 13% |  |  |  |  | 14.196 |  |  |  | 1419.6 | [7 empty] | 2.366 | 2.4 | 81 | 0 | 1900-01-02
22 |  | 1.3.6 | Perform Project Plan Peer Review (User Story) | [7 empty] | 10% |  |  |  |  | 10.92 | [11 empty] | 1.82 | 1.9
23 |  | 1.3.7 | Obtain Commitment to the Plan (User Story) | [7 empty] | 10% |  |  |  |  | 10.92 |  |  |  | 1092 | [7 empty] | 1.82 | 1.9 | 87 | 0 | 1900-01-01
24 |  |  |  | Review Plans that Affect the Project | [23 empty] | #VALUE! | #VALUE!
25 |  |  |  | Reconcile Work and Resource Levels | [23 empty] | #VALUE! | #VALUE!
26 |  |  |  | Obtain Plan Commitment | [23 empty] | #VALUE! | #VALUE!
27 |  |  | 1.3.6.1 | Project Plan Peer Review | [7 empty] | 0.0769 | 5 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 | 0 | 69 | 0 | 0
28 |  |  |  | 1.3.2.1 | Prepare for Project Plan Peer Review |  |  | Project Manager |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0 | #REF!
29 |  |  |  |  | 1.3.2.1.1 | Identify Project Plan Peer Review Reviewers |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE! |  | 0 | #VALUE!
30 |  |  |  |  | 1.3.2.1.2 | Check Project Plan |  | Project Manager | [5 empty] | 0.8 | [8 empty] | #REF! |  |  |  |  | #VALUE! | #VALUE! | 69 | 0 | #REF!
31 |  |  |  |  | 1.3.2.1.3 | Schedule Project Plan Peer Review Meeting |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #REF! |  |  |  |  | #VALUE! | #VALUE! | 74 | 0 | #REF!
32 |  |  |  | 1.3.2.2 | Conduct Project Plan Peer Review | [7 empty] | 0.2 | 1 | [8 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE!
33 |  |  |  |  | 1.3.2.2.1 | Conduct Project Plan Peer Review Meeting | [7 empty] | 0.8 | [8 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE!
34 |  |  |  |  | 1.3.2.2.2 | Review and Log Project Plan Feedback | [7 empty] | 0.2 | [8 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE!
35 |  |  |  | 1.3.2.3 | Analyze Project Plan Peer Review | [7 empty] | 0.45 | #REF! | [8 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE!
36 |  |  |  |  | 1.3.2.3.1 | Resolve Project Plan Feedback | [7 empty] | 0.35 | [8 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE!
37 |  |  |  |  | 1.3.2.3.2 | Project Plan Peer Review Follow Up | [7 empty] | 0.2 |  |  | #REF! |  |  |  | #REF! |  | #REF! |  |  |  |  | #REF! | #REF! | 4 | 0 | #REF!
38 |  |  |  |  | 1.3.2.3.3 | Resolve Modifications from Project Plan Peer Review |  |  | 1 |  |  |  |  | 0.35 |  |  |  | #REF! |  |  |  | #REF! | #REF! |  |  |  |  | #REF! | #REF! |  | 0 | #REF!
39 |  |  |  |  | 1.3.2.3.4 | Document and Communicate Project Plan Review Results | [7 empty] | 0.1 |  |  | #REF! |  |  |  | #REF! |  | #REF! |  |  |  |  | #REF! | #REF! | 9 | 0 | #REF!
40 |  |  | 1.3.3 | Review and Approve Project Plan | [18 empty] | #VALUE! |  |  |  |  | #VALUE! | #VALUE!
41 |  |  |  | 1.3.3.1 | Perform Project Plan Verification | [6 empty] | 0.4 | 1 |  |  |  | #REF! | [5 empty] | #REF! |  |  |  |  | #REF! | #REF!
42 |  |  |  |  | 1.3.3.1.1 | Identify Project Plan Reviewers |  |  | 1 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
43 |  |  |  |  | 1.3.3.1.2 | Schedule Review and Approve Project Plan Review |  |  | 1 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
44 |  |  |  |  | 1.3.3.1.3 | Conduct Review and Approve Project Plan Meeting |  |  | 1 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
45 |  |  |  |  | 1.3.3.1.4 | Review and Log Project Plan Feedback |  |  | 1 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
46 |  |  |  | 1.3.3.2 | Analyze Project Plan Verification Results | [6 empty] | 0.6 | 1 |  |  |  | #REF! | [5 empty] | #REF! |  |  |  |  | #REF! | #REF!
47 |  |  |  |  | 1.3.3.2.1 | Resolve Project Plan Feedback |  |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
48 |  |  |  |  | 1.3.3.2.2 | Verify Closure of Customer Requirements Feedback |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.3 |  |  |  |  | #REF! |  | 0 |  |  | #REF! |  |  |  |  | #REF! | #REF! | 71 | 0 | #REF!
49 |  |  |  |  | 1.3.3.2.3 | Document and Communicate Customer Requirements Review Results |  |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  | 0 |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0 | #REF!
50 |  |  |  |  | 1.3.3.2.4 | Obtain Approval and Baseline Customer Requirements |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! |  |  |  |  | #REF! | #REF! |  | 0 | #REF!
51 |  | 1.3.7 | Prepare for Quantitative Management (User Story) | [7 empty] | 10% |  |  |  |  | 10.92 |  |  |  | 1092 | [7 empty] | 1.82 | 1.9 | 96 | 0 | 1900-01-01
52 |  | 1.3.8 | Prepare for Risk Management (User Story) | [7 empty] | 10% |  |  |  |  | 10.92 |  |  |  | 1092 | [7 empty] | 1.82 | 1.9 | 100 | 0 | 1900-01-01
53 |  | 1.3.9 | Planning Risk | [12 empty] | P |  |  |  | #VALUE! | [7 empty] | #VALUE! | #VALUE! | 105 | 0 | #VALUE!
54 | 1.4 | Planning Completed | [25 empty] | 1.9 |  |  | 1900-01-24
55 | [27 empty] | 1.9
56
57 | 1.5 | Supplier Acquisition (Feature) | [7 empty] | 5% | 11% |  |  |  | 78 |  |  |  | 7800 |  |  |  | 13 | [5 empty] | 13 | 51 | 0 | 18
58 |  | 1.5.1 | Prepare for Solicitation and Supplier Agreement Development (User Story) | [12 empty] | 0
59 |  | 1.5.2 | Select Suppliers (User Story)
60 |  | 1.5.3 | Establish Supplier Agreements (User Story)
61 |  | 1.5.4 | Develop Contractual Requirements (User Story)
62 |  | 1.5.2 | Perform Contractual Requirments Peer Review (User Story)
63 |  | 1.5.3 | Review & Approve Contractual Requirments (User Story)
64 |  | 1.5.4 | Satisfy Supplier Agreements (User Story)
65 |  | 1.5.3 | Evaluate Technical Solutions (User Story)
66 |  | 1.5.4 | Perform Interface Management (User Story)
67
68
69 |  | 1.4.3 | Contractual Requirements Peer Review
70 |  | 1.4.1 | Engague Vendor Management Office / Purchasing
71 |  | 1.4.2 | Develop and Release RFI
72 |  | 1.4.3 | Develop and Release RFP
73 |  |  | 1.4.2.1 | Develop Initial Version of Supplier Management Plan |  |  |  |  | 1 |  |  | 6% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
74 |  |  | 1.4.2.2 | Develop RFP and Evaluation Criteria |  |  |  | Project Manager | 1 |  |  | 33% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
75 |  |  | 1.4.2.3 | Distribute RFP to Suppliers |  |  |  | WWP/Contract Manager | 1 |  |  | 6% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
76 |  |  | 1.4.2.4 | Evaluate Proposals |  |  |  | Project Manager | 1 |  |  | 25% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
77 |  |  | 1.4.2.5 | Approve Supplier(s) Down-Select |  |  |  | Senior Manager,Project Manager | 2 |  |  | 6% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
78 |  |  | 1.4.2.6 | Negotiate Agreement and Select Final Supplier |  |  |  |  | 1 |  |  | 6% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
79 |  |  | 1.4.2.7 | Get Single Sourcing Justification Letter and Obtain Approval |  |  |  | CM Lead[30%],Senior Manager[30%],Project Manager[30%] | 3 |  |  | 6% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | [5 empty] | #REF! | 42 | 0 | #REF!
80 |  | 1.4.3 | Establish Supplier Agreement |  |  |  |  | WWP/Contract Manager,Project Manager |  |  | 20% | 100% |  |  |  | #REF! | [6 empty] | #REF! | [5 empty] | #REF! | 6 | 0 | #REF!
81 |  |  | 1.4.3.1 | Determine Acquisition Type | [7 empty] | 8% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0
82 |  |  | 1.4.3.2 | Select Suppiers | [7 empty] | 60% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0
83 |  |  | 1.4.3.3 | Establish Supplier Agreements | [7 empty] | 32% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0
84 |  | 1.4.4 | Communicate Final Supplier Management Plan | [7 empty] | 1% |  |  |  |  | #REF! | [6 empty] | #REF! | [5 empty] | #REF! | 51 | 0 | #REF!
85 |  | 1.4.5 | Conduct Selection Review |  |  |  |  | Project Manager[30%],Requirements Analyst |  |  | 5% |  |  |  |  | #REF! | [6 empty] | #REF! | [5 empty] | #REF! | 67 | 0 | #REF!
86 |  | 1.4.6 | Conduct Bid Evaluations | [7 empty] | 5% | 45% |  |  |  | #REF! | [6 empty] | #REF! | [5 empty] | #REF! | 51 | 0 | #REF!
87 |  |  | 1.4.6.1 | Plan for Product Acquisition |  |  |  | Project Manager,Requirements Analyst |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
88 |  |  | 1.4.6.2 | Plan for Supplier Sourcing (Construct through Deploy) |  |  |  | Project Manager,Senior Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
89 |  |  | 1.4.6.3 | Develop Initial Version of Supplier Management Plan | [7 empty] | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
90 |  |  | 1.4.6.4 | Develop RFP and Evaluation Criteria |  |  |  | Project Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
91 |  |  | 1.4.6.5 | Distribute RFP to Suppliers |  |  |  | WWP/Contract Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
92 |  |  | 1.4.6.6 | Evaluate Proposals |  |  |  | Project Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
93 |  |  | 1.4.6.7 | Approve Supplier(s) Down-Select |  |  |  | Senior Manager,Project Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
94 |  |  | 1.4.6.8 | Negotiate Agreement and Select Final Supplier | [7 empty] | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
95 |  |  | 1.4.6.9 | Get Single Sourcing Justification Letter and Obtain Approval |  |  |  | CM Lead[30%],Senior Manager[30%],Project Manager[30%] |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
96 |  | 1.4.7 | Conduct Selection Tollgate
97 |  |  | 1.4.6.10 | Update Plan(s) for Construct, Test and Deploy Phases |  |  |  | Project Manager,CM Lead,QA Analyst |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 10 | 0 | #REF!
98 |  |  | 1.4.6.11 | Request Tollgate Review |  |  |  | Project Manager[30%] |  |  |  | 1% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 10 | 0 | #REF!
99 |  |  | 1.4.6.12 | Update and Approve (when applicable) Business Case |  |  |  | Project Manager[30%] |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 10 | 0 | #REF!
100 |  |  | 1.4.6.13 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 10 | 0 | #REF!
101 |  |  | 1.4.6.14 | Conduct Define Phase Tollgate |  |  |  | PMO Prg. Mgr.[50%] |  |  |  | 14% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 10 | 0 | #REF!
102 |  |  | 1.4.6.15 | Review Work Product Baseline |  |  |  | QA Analyst |  |  |  | 45% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 56 | 0 | #REF!
103 |  |  | 1.4.6.16 | Conduct CM Audits |  |  |  | QA Analyst |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 57 | 0 | #REF!
104 |  |  | 1.4.6.17 | Prepare Define Tollgate Review Report |  |  |  | Project Manager[20%] |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 58 | 0 | #REF!
105 |  |  | 1.4.6.18 | Update and Communicate Define Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 59 | 0 | #REF!
106 |  |  | 1.4.6.19 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 60 | 0 | #REF!
107 |  |  | 1.4.6.20 | Close Selection Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager |  |  |  | 5% |  |  |  |  | #REF! | [5 empty] | #REF! | [5 empty] | #REF! | 61 | 0 | #REF!
108 |  | 1.4.7 | Select Risk | [12 empty] | #REF! | [6 empty] | #REF! | [5 empty] | #REF! |  | 0 | #REF!
109 |  | 1.4.8 | Select Tollgate Conducted | [27 empty] | 0 | 0
110
111
112 | 1.5 | Incremental
113 |  | 1.5.1 | Increment 1
114 |  |  | 1.5.1.1 | Define
115 |  |  | 1.5.1.2 | Design
116 |  |  | 1.5.1.3 | Construct
117 |  |  | 1.5.1.4 | Build
118 |  |  | 1.5.1.5 | QA Test
119 |  | 1.5.2 | Increment 2
120 |  |  | 1.5.2.1 | Define
121 |  |  | 1.5.2.2 | Design
122 |  |  | 1.5.2.3 | Construct
123 |  |  | 1.5.2.4 | Build
124 |  |  | 1.5.2.5 | QA Test
125 |  | 1.5.2 | Increment N
126 |  |  | 1.5.2.1 | Define
127 |  |  | 1.5.2.2 | Design
128 |  |  | 1.5.2.3 | Construct
129 |  |  | 1.5.2.4 | Build
130 |  |  | 1.5.2.5 | QA Test
119
120
121 | 1.6 | Define
122 |  | 1.6.1 | Process Description Capturing
123
124
125
126 |  | 1.6.2 | Develop Customer Requirements
127 |  |  | 1.5.1.1 | Derive Customer Requirements
128 |  |  | 1.5.3.2 | Complete Customer Requirements Document
129 |  |  | 1.5.3.3 | Check for Consistency with Process Design Summary
130 |  | 1.6.3 | Customer Requirements Peer Review
131 |  |  |  | Prepare for Customer Requirements Peer Review
132 |  |  |  | Conduct Customer Requirements Peer Review
133 |  |  |  | Analyze Customer Requirement Peer Review
134 |  | 1.6.4 | Review and Approve Customer Requirements
135 |  | 1.6.5 | Customer Requirements Developed
136 |  | 1.6.6 | Develop Product Requirements (Features)
137
138 |  | 1.6.7 | Analyze and Validate Requirements
139
140
141 | 1.7 | Design | [7 empty] | #REF!
142 |  | 1.7.1
143 |  | 1.4.7 | Develop Architectural Design |  |  |  |  | Project Architect |  |  | 0.1507 | 1 |  |  |  | 0 | [6 empty] | 0 | 0 | 51 | 0 | 0
144 |  |  | 1.4.7.1 | Design System Architecture |  |  |  | Project Architect |  |  |  | 0.2 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
145 |  |  | 1.4.7.2 | Develop Logical Data Model (LDM) |  |  |  | Project Data Architect |  |  |  | 0.2 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
146 |  |  | 1.4.7.3 | Present to Architectural Review Committee |  |  |  | Project Architect,Project Manager |  |  |  | 0.1 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
147 |  |  | 1.4.7.4 | Update Architectural Design (AD) Document |  |  |  | Project Architect |  |  |  | 0.1 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
148 |  |  | 1.4.7.5 | Create IT Standards Bill of Material (BoM) |  |  |  | Project Architect,Project Manager |  |  |  | 0.0837 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
149 |  |  | 1.4.7.6 | Ensure Review of AD and BoM |  |  |  | Project Manager |  |  |  | 0.05 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
150 |  |  | 1.4.7.7 | Peer Review | [7 empty] | 0.1183 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
151 |  |  | 1.4.7.8 | Obtain Approval and Baseline AD and BoM |  |  |  | Project Manager,PIO Achitect |  |  |  | 0.148 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
152 |  | 1.5.2 | Architectural Design Peer Review | [8 empty] | 0.0769 | 1 |  |  |  | 0 | [5 empty] | 0 | 0 | 69 | 0 | 0
153 |  |  | 1.5.2.1 | Prepare for Architectural Design Peer Review |  |  |  | Project Manager |  |  |  |  | 0.35 | 1 |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0
154 |  |  |  | 1.5.2.1.1 | Identify Customer Requirements Peer Review Reviewers |  |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
155 |  |  |  | 1.5.2.1.2 | Check Customer Requirements |  |  | Project Manager | [5 empty] | 0.8 | [8 empty] | #REF! | #REF! | 69 | 0 | #REF!
156 |  |  |  | 1.5.2.1.3 | Schedule Customer Requirements Peer Review Meeting |  |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #REF! | #REF! | 74 | 0 | #REF!
157 |  |  | 1.5.2.2 | Conduct Architectural Design Peer Review | [8 empty] | 0.2 | 1 | [8 empty] | #VALUE! | #VALUE!
158 |  |  |  | 1.5.2.2.1 | Conduct Customer Requirements Peer Review Meeting | [8 empty] | 0.8 | [8 empty] | #VALUE! | #VALUE!
159 |  |  |  | 1.5.2.2.2 | Review and Log Customer Requirements Feedback | [8 empty] | 0.2 | [8 empty] | #VALUE!
160 |  |  | 1.5.2.3 | Analyze Architectural Design Plan Peer Review | [8 empty] | 0.45 | 1 | [8 empty] | #VALUE! | #VALUE!
161 |  |  |  | 1.5.2.3.1 | Resolve Project Charter Plan Feedback | [8 empty] | 0.35 | [8 empty] | #VALUE! | #VALUE!
162 |  |  |  | 1.5.2.3.2 | Project Charter Plan Peer Review Follow Up | [8 empty] | 0.2 |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 4 | 0 | #REF!
163 |  |  |  | 1.5.2.3.3 | Resolve Modifications from Project Charter Peer Review |  |  |  | 1 |  |  |  |  | 0.35 |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
164 |  |  |  | 1.5.2.3.4 | Document and Communicate Project Charter Review Results | [8 empty] | 0.1 |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 9 | 0 | #REF!
165 |  | 1.5.5 | Create IT Standards Bill of Material
166 |  | 1.5.3 | Review and Approve Architectural Design and Bill of Material | [19 empty] | #VALUE! | #VALUE!
167 |  |  | 1.5.3.1 | Perform Architectural Design and Bill of Material Verification | [7 empty] | 0.4 | 1 |  |  |  | #REF! | [5 empty] | #REF! | #REF!
168 |  |  |  | 1.5.3.1.1 | Identify Customer Requirements Reviewers |  |  |  | 1 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
169 |  |  |  | 1.5.3.1.2 | Schedule Review and Approve Customer Requirements Review |  |  |  | 1 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
170 |  |  |  | 1.5.3.1.3 | Conduct Review and Approve Customer Requirements Meeting |  |  |  | 1 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
171 |  |  |  | 1.5.3.1.4 | Review and Log Customer Requirements Feedback |  |  |  | 1 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
172 |  |  | 1.5.3.2 | Analyze Architectural Design and Bill of Material Verification Results | [7 empty] | 0.6 | 1 |  |  |  | #REF! | [5 empty] | #REF! | #REF!
173 |  |  |  | 1.5.3.2.1 | Resolve Customer Requirements Feedback |  |  |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
174 |  |  |  | 1.5.3.2.2 | Verify Closure of Customer Requirements Feedback |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.3 |  |  |  |  | #REF! |  | 0 |  |  | #REF! | #REF! | 71 | 0 | #REF!
175 |  |  |  | 1.5.3.2.3 | Document and Communicate Customer Requirements Review Results |  |  |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  | 0 |  | #REF! | #REF! |  | 0 | #REF!
176 |  |  |  | 1.5.3.2.4 | Obtain Approval and Baseline Customer Requirements |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
177 |  | 1.5.4 | Architectural Design Developed | [22 empty] | 0 | 0
178 |  | 1.5.5 | Bill of Material Approved
179
180 | [22 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
181 |  | 1.4.7 | Develop Data Design
182
183 |  | 1.4.7 | Develop Security Design
184
185 | 1.8 | Construct | [7 empty] | #REF! | 1.3094 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! |  | 0 | 0
186 |  | 1.8.1
187 |  | 1.8.1 | Conduct Construct Phase Kick-Off |  |  |  |  | Supplier,Project Manager |  |  | 0.005 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  | 0 | #REF!
188 |  | 1.8.2 | Construct Phase Kick-Off Conducted | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
189 |  | 1.8.3 | Develop Test Plans | [7 empty] | 0.25 | 20.94 |  |  |  | 0 | [6 empty] | 0 | 0 |  | 0 | #REF!
190 |  |  | 1.8.3.1 | Identify Pre-Production Environment Requirements | [7 empty] | 0.3 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
191 |  |  | 1.8.3.2 | Identify Pre-Production Environment Requirements | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
192 |  |  | 1.8.3.3 | Identify Test Data Requirements for User Acceptance Testing | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
193 |  |  | 1.8.3.4 | Develop Schedule for User Acceptance Testing |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
194 |  |  | 1.8.3.5 | Document Defect and Problem Reporting Procedures |  |  |  | Project Manager,Supplier[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
195 |  |  | 1.8.3.6 | Document User Acceptance Test Plan | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
196 |  | 1.8.4 | Perform User Acceptance Test Plan Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
197 |  |  | 1.3.4.1 | Prepare for User Acceptance Test Plan Peer Review |  |  | Prepare for User Acceptance Test Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
198 |  |  |  | 1.3.4.1.1 | Identify User Acceptance Test Plan Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
199 |  |  |  | 1.3.4.1.2 | Check Draft User Acceptance Test Plan |  | Check Draft User Acceptance Test Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
200 |  |  |  | 1.3.4.1.3 | Schedule User Acceptance Test Plan Peer Review Meeting |  | Schedule User Acceptance Test Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
201 |  |  | 1.3.4.2 | Conduct User Acceptance Test Plan Peer Review |  |  | Conduct User Acceptance Test Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
202 |  |  |  | 1.3.4.2.1 | Conduct User Acceptance Test Plan Plan Review Meeting |  | Conduct User Acceptance Test Plan Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
203 |  |  |  | 1.3.4.2.2 | Review and Log User Acceptance Test Plan Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
204 |  |  | 1.3.4.3 | Analyze User Acceptance Test Plan Peer Review |  |  | Analyze User Acceptance Test Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 0 | 0
205 |  |  |  | 1.3.4.3.1 | Resolve User Acceptance Test Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
206 |  |  |  | 1.3.4.3.2 | User Acceptance Test Plan Peer Review Follow Up |  | User Acceptance Test Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
207 |  |  |  | 1.3.4.3.3 | Resolve Modifications from User Acceptance Test Plan Peer Review |  | Resolve Modifications from User Acceptance Test Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
208 |  |  |  | 1.3.4.3.4 | Document and Communicate User Acceptance Test Plan Review Results |  | Document and Communicate User Acceptance Test Plan Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
209 |  | 1.8.5 | Review and Approve User Acceptance Test Plan |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
210 |  |  | 1.3.2.1 | Perform User Acceptance Test Plan Verification |  |  | Perform User Acceptance Test Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
211 |  |  |  | 1.3.2.1.1 | Identify User Acceptance Test Plan Reviewers |  | Identify User Acceptance Test Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
212 |  |  |  | 1.3.2.1.2 | Schedule Review and Approve User Acceptance Test Plan Review |  | Schedule Review and Approve User Acceptance Test Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
213 |  |  |  | 1.3.2.1.3 | Conduct Review and Approve User Acceptance Test Plan Plan Meeting |  | Conduct Review and Approve User Acceptance Test Plan Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
214 |  |  |  | 1.3.2.1.4 | Review and Log User Acceptance Test Plan Feedback |  | Review and Log User Acceptance Test Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 0 | #REF!
215 |  |  | 1.3.2.2 | Analyze User Acceptance Test Plan Verification Results |  |  | Analyze User Acceptance Test Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
216 |  |  |  | 1.3.2.2.1 | Resolve User Acceptance Test Plan Feedback |  | Resolve User Acceptance Test Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
217 |  |  |  | 1.3.2.2.2 | Verify Closure of User Acceptance Test Plan Feedback |  | Verify Closure of User Acceptance Test Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
218 |  |  |  | 1.3.2.2.3 | Document and Communicate User Acceptance Test Plan Review Results |  | Document and Communicate User Acceptance Test Plan Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
219 |  |  |  | 1.3.2.2.4 | Obtain Approval and User Acceptance Test Plan |  | Obtain Approval and User Acceptance Test Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 0 | #REF!
220 |  | 1.8.6 | Develop User Acceptance Test Cases | [8 empty] | 0.31 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
221 |  |  | 1.4.4.3.1 | Document User Acceptance Test Cases | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
222 |  |  | 1.4.4.3.2 | Update User Acceptance Test Case References in RTM | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
223 |  | 1.8.7 | Perform User Acceptance Test Cases Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
224 |  |  | 1.8.7.1 | Prepare for User Acceptance Cases Plan Peer Review |  |  | Prepare for User Acceptance Cases Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
225 |  |  |  | 1.8.7.1.1 | Identify User Acceptance Test Cases Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
226 |  |  |  | 1.8.7.1.2 | Check Draft User Acceptance Test Cases |  | Check Draft User Acceptance Test Cases | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
227 |  |  |  | 1.8.7.1.3 | Schedule User Acceptance Test Cases Peer Review Meeting |  | Schedule User Acceptance Test Cases Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
228 |  |  | 1.8.7.2 | Conduct User Acceptance Test Cases Peer Review |  |  | Conduct User Acceptance Test Cases Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
229 |  |  |  | 1.8.7.2.1 | Conduct User Acceptance Test Cases Review Meeting |  | Conduct User Acceptance Test Cases Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
230 |  |  |  | 1.8.7.2.2 | Review and Log User Acceptance Test Cases Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
231 |  |  | 1.8.7.3 | Analyze User Acceptance Test Cases Peer Review |  |  | Analyze User Acceptance Test Cases Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 0 | 0
232 |  |  |  | 1.8.7.3.1 | Resolve User Acceptance Test Cases Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
233 |  |  |  | 1.8.7.3.2 | User Acceptance Test Cases Peer Review Follow Up |  | User Acceptance Test Cases Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
234 |  |  |  | 1.8.7.3.3 | Resolve Modifications from User Acceptance Test Cases Peer Review |  | Resolve Modifications from User Acceptance Test Cases Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
235 |  |  |  | 1.8.7.3.4 | Document and Communicate User Acceptance Test Cases Review Results |  | Document and Communicate User Acceptance Test Cases Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
236 |  | 1.8.8 | Review and Approve User Acceptance Test Cases |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
237 |  |  | 1.8.8.1 | Perform User Acceptance Test Cases Verification |  |  | Perform User Acceptance Test Cases Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
238 |  |  |  | 1.8.8.1.1 | Identify User Acceptance Test Cases Reviewers |  | Identify User Acceptance Test Cases Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
239 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve User Acceptance Test Cases Review |  | Schedule Review and Approve User Acceptance Test Cases Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
240 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve User Acceptance Test Cases Plan Meeting |  | Conduct Review and Approve User Acceptance Test Cases Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
241 |  |  |  | 1.8.8.1.4 | Review and Log User Acceptance Test Cases Feedback |  | Review and Log User Acceptance Test Cases Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 0 | #REF!
242 |  |  | 1.8.8.2 | Analyze User Acceptance Test Cases Verification Results |  |  | Analyze User Acceptance Test Cases Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
243 |  |  |  | 1.8.8.2.1 | Resolve User Acceptance Test Cases Feedback |  | Resolve User Acceptance Test Cases Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
244 |  |  |  | 1.8.8.2.2 | Verify Closure of User Acceptance Test Cases Feedback |  | Verify Closure of User Acceptance Test Cases Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
245 |  |  |  | 1.8.8.2.3 | Document and Communicate User Acceptance Test Cases Review Results |  | Document and Communicate User Acceptance Test Cases Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
246 |  |  |  | 1.8.8.2.4 | Obtain Approval and User Acceptance Test Cases |  | Obtain Approval and User Acceptance Test Cases |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 0 | #REF!
247 |  | 1.8.9 | Document Non-Functional Test Cases | [13 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
248 |  | 1.8.10 | Update Non-Functional Test Case References in Requirements Traceability Matrix | [13 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
249 |  | 1.8.7 | Perform Non-Functional Test Cases Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
250 |  |  | 1.8.7.1 | Prepare for Non-Functional Cases Plan Peer Review |  |  | Prepare for Non-Functional Cases Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
251 |  |  |  | 1.8.7.1.1 | Identify Non-Functional Test Cases Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
252 |  |  |  | 1.8.7.1.2 | Check Draft Non-Functional Test Cases |  | Check Draft Non-Functional Test Cases | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
253 |  |  |  | 1.8.7.1.3 | Schedule Non-Functional Test Cases Peer Review Meeting |  | Schedule Non-Functional Test Cases Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
254 |  |  | 1.8.7.2 | Conduct Non-Functional Test Cases Peer Review |  |  | Conduct Non-Functional Test Cases Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
255 |  |  |  | 1.8.7.2.1 | Conduct Non-Functional Test Cases Review Meeting |  | Conduct Non-Functional Test Cases Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
256 |  |  |  | 1.8.7.2.2 | Review and Log Non-Functional Test Cases Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
257 |  |  | 1.8.7.3 | Analyze Non-Functional Test Cases Peer Review |  |  | Analyze Non-Functional Test Cases Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 0 | 0
258 |  |  |  | 1.8.7.3.1 | Resolve Non-Functional Test Cases Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
259 |  |  |  | 1.8.7.3.2 | Non-Functional Test Cases Peer Review Follow Up |  | Non-Functional Test Cases Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
260 |  |  |  | 1.8.7.3.3 | Resolve Modifications from Non-Functional Test Cases Peer Review |  | Resolve Modifications from Non-Functional Test Cases Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
261 |  |  |  | 1.8.7.3.4 | Document and Communicate Non-Functional Test Cases Review Results |  | Document and Communicate Non-Functional Test Cases Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
262 |  | 1.8.8 | Review and Approve Non-Functional Test Cases |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
263 |  |  | 1.8.8.1 | Perform Non-Functional Test Cases Verification |  |  | Perform Non-Functional Test Cases Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
264 |  |  |  | 1.8.8.1.1 | Identify Non-Functional Test Cases Reviewers |  | Identify Non-Functional Test Cases Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
265 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve Non-Functional Test Cases Review |  | Schedule Review and Approve Non-Functional Test Cases Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
266 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve Non-Functional Test Cases Plan Meeting |  | Conduct Review and Approve Non-Functional Test Cases Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
267 |  |  |  | 1.8.8.1.4 | Review and Log Non-Functional Test Cases Feedback |  | Review and Log Non-Functional Test Cases Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 0 | #REF!
268 |  |  | 1.8.8.2 | Analyze Non-Functional Test Cases Verification Results |  |  | Analyze Non-Functional Test Cases Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
269 |  |  |  | 1.8.8.2.1 | Resolve Non-Functional Test Cases Feedback |  | Resolve Non-Functional Test Cases Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
270 |  |  |  | 1.8.8.2.2 | Verify Closure of Non-Functional Test Cases Feedback |  | Verify Closure of Non-Functional Test Cases Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
271 |  |  |  | 1.8.8.2.3 | Document and Communicate Non-Functional Test Cases Review Results |  | Document and Communicate Non-Functional Test Cases Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
272 |  |  |  | 1.8.8.2.4 | Obtain Approval and Non-Functional Test Cases |  | Obtain Approval and Non-Functional Test Cases |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 0 | #REF!
273 |  | 1.8.9 | Develop System Test Plan | [8 empty] | 0.3 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
274 |  |  | 1.8.9.1 | Identify Test Environment Requirements | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
275 |  |  | 1.8.9.1 | Identify Test Data Requirements for System Testing | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
276 |  |  | 1.8.9.1 | Develop Schedule for System Testing | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
277 |  |  | 1.8.9.1 | Document System Test Plan | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
278 |  | 1.8.10 | Perform System Test Plan Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
279 |  |  | 1.8.7.1 | Prepare for System Test Plan Peer Review |  |  | Prepare for System Test Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
280 |  |  |  | 1.8.7.1.1 | Identify System Test Plan Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
281 |  |  |  | 1.8.7.1.2 | Check Draft System Test Plan |  | Check Draft System Test Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
282 |  |  |  | 1.8.7.1.3 | Schedule System Test Plan Peer Review Meeting |  | Schedule System Test Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
283 |  |  | 1.8.7.2 | Conduct System Test Plan Peer Review |  |  | Conduct System Test Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
284 |  |  |  | 1.8.7.2.1 | Conduct System Test Plan Review Meeting |  | Conduct System Test Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
285 |  |  |  | 1.8.7.2.2 | Review and Log System Test Plan Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
286 |  |  | 1.8.7.3 | Analyze System Test Plan Peer Review |  |  | Analyze System Test Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 0 | 0
287 |  |  |  | 1.8.7.3.1 | Resolve System Test Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
288 |  |  |  | 1.8.7.3.2 | System Test Plan Peer Review Follow Up |  | System Test Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
289 |  |  |  | 1.8.7.3.3 | Resolve Modifications from System Test Plan Peer Review |  | Resolve Modifications from System Test Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
290 |  |  |  | 1.8.7.3.4 | Document and Communicate System Test Plan Review Results |  | Document and Communicate System Test Plan Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
291 |  | 1.8.11 | Review and Approve System Test Plan |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
292 |  |  | 1.8.8.1 | Perform System Test Plan Verification |  |  | Perform System Test Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
293 |  |  |  | 1.8.8.1.1 | Identify System Test Plan Reviewers |  | Identify System Test Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
294 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve System Test Plan Review |  | Schedule Review and Approve System Test Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
295 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve System Test Plan Plan Meeting |  | Conduct Review and Approve System Test Plan Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
296 |  |  |  | 1.8.8.1.4 | Review and Log System Test Plan Feedback |  | Review and Log System Test Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 0 | #REF!
297 |  |  | 1.8.8.2 | Analyze System Test Plan Verification Results |  |  | Analyze System Test Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
298 |  |  |  | 1.8.8.2.1 | Resolve System Test Plan Feedback |  | Resolve System Test Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
299 |  |  |  | 1.8.8.2.2 | Verify Closure of System Test Plan Feedback |  | Verify Closure of System Test Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
300 |  |  |  | 1.8.8.2.3 | Document and Communicate System Test Plan Review Results |  | Document and Communicate System Test Plan Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
301 |  |  |  | 1.8.8.2.4 | Obtain Approval and System Test Plan |  | Obtain Approval and System Test Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 0 | #REF!
302 |  | 1.8.12 | Identify and Document System Test Cases
303 |  | 1.8.10 | Perform System Test Cases Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
304 |  |  | 1.8.7.1 | Prepare for System Test Cases Peer Review |  |  | Prepare for System Test Cases Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
305 |  |  |  | 1.8.7.1.1 | Identify System Test Cases Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
306 |  |  |  | 1.8.7.1.2 | Check Draft System Test Cases |  | Check Draft System Test Cases | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
307 |  |  |  | 1.8.7.1.3 | Schedule System Test Cases Peer Review Meeting |  | Schedule System Test Cases Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
308 |  |  | 1.8.7.2 | Conduct System Test Cases Peer Review |  |  | Conduct System Test Cases Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
309 |  |  |  | 1.8.7.2.1 | Conduct System Test Cases Review Meeting |  | Conduct System Test Cases Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
310 |  |  |  | 1.8.7.2.2 | Review and Log System Test Cases Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
311 |  |  | 1.8.7.3 | Analyze System Test Cases Peer Review |  |  | Analyze System Test Cases Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 0 | 0
312 |  |  |  | 1.8.7.3.1 | Resolve System Test Cases Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
313 |  |  |  | 1.8.7.3.2 | System Test Cases Peer Review Follow Up |  | System Test Cases Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
314 |  |  |  | 1.8.7.3.3 | Resolve Modifications from System Test Cases Peer Review |  | Resolve Modifications from System Test Cases Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
315 |  |  |  | 1.8.7.3.4 | Document and Communicate System Test Cases Review Results |  | Document and Communicate System Test Cases Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
316 |  | 1.8.11 | Review and Approve System Test Cases |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
317 |  |  | 1.8.8.1 | Perform System Test Cases Verification |  |  | Perform System Test Cases Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
318 |  |  |  | 1.8.8.1.1 | Identify System Test Cases Reviewers |  | Identify System Test Cases Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
319 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve System Test Cases Review |  | Schedule Review and Approve System Test Cases Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
320 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve System Test Cases Meeting |  | Conduct Review and Approve System Test Cases Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
321 |  |  |  | 1.8.8.1.4 | Review and Log System Test Cases Feedback |  | Review and Log System Test Cases Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 0 | #REF!
322 |  |  | 1.8.8.2 | Analyze System Test Cases Verification Results |  |  | Analyze System Test Cases Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
323 |  |  |  | 1.8.8.2.1 | Resolve System Test Cases Feedback |  | Resolve System Test Cases Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
324 |  |  |  | 1.8.8.2.2 | Verify Closure of System Test Cases Feedback |  | Verify Closure of System Test Cases Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
325 |  |  |  | 1.8.8.2.3 | Document and Communicate System Test Cases Review Results |  | Document and Communicate System Test Cases Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
326 |  |  |  | 1.8.8.2.4 | Obtain Approval and System Test Cases |  | Obtain Approval and System Test Cases |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 0 | #REF!
327 |  | 1.8.12 | Identify and Document System Test Cases |  |  |  |  | Supplier |  |  |  | 0.03 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
328 |  | 1.8.13 | Complete System Deployment Plan | [7 empty] | 0.08 | 5 |  |  |  | 0 | [6 empty] | 0 | 0 |  | 0 | 0
329 |  |  | 1.8.13.1 | Develop Training Plan for System Deployment | [7 empty] | 0.273 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
330 |  |  | 1.8.13.2 | Develop Pilot Deployment Plan | [7 empty] | 0.273 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | 0
331 |  |  |  | 1.8.13.2.1 | Develop Pilot Security Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
332 |  |  |  | 1.8.13.2.2 | Develop Pilot Data Conversion and Load Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
333 |  |  |  | 1.8.13.2.3 | Develop Pilot Deployment Schedule | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
334 |  |  |  | 1.8.13.2.4 | Develop Pilot Test Plans | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
335 |  |  |  | 1.8.13.2.5 | Develop Pilot Operations, Maintenance and Support Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
336 |  |  |  | 1.8.13.2.6 | Develop Pilot Application Disaster Recovery Plan for the Site | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
337 |  |  |  | 1.8.13.2.7 | Document Pilot Deployment Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
338 |  |  | 1.8.13.3 | Perform Pilot Deployment Plan Peer Review | [6 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
339 |  |  |  | 1.8.13.3.1 | Prepare for Pilot Deployment Plan Peer Review |  | Prepare for Pilot Deployment Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
340 |  |  |  |  | 1.8.13.1.1 | Identify Pilot Deployment Plan Peer Review Reviewers | [6 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
341 |  |  |  |  | 1.8.13.1.2 | Check Draft Pilot Deployment Plan | Check Draft Pilot Deployment Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
342 |  |  |  |  | 1.8.13.1.3 | Schedule Pilot Deployment Plan Peer Review Meeting | Schedule Pilot Deployment Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
343 |  |  |  | 1.8.13.3.2 | Conduct Pilot Deployment Plan Peer Review |  | Conduct Pilot Deployment Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
344 |  |  |  |  | 1.8.13.3.2.1 | Conduct Pilot Deployment Plan Review Meeting | Conduct Pilot Deployment Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
345 |  |  |  |  | 1.8.13.3.2.2 | Review and Log Pilot Deployment Plan Peer Review Feedback | [6 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
346 |  |  | 1.8.14.3 | Analyze Pilot Deployment Plan Peer Review |  |  | Analyze Pilot Deployment Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 0 | 0
347 |  |  |  | 1.8.14.3.1 | Resolve Pilot Deployment Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
348 |  |  |  | 1.8.14.3.2 | Pilot Deployment Plan Peer Review Follow Up |  | Pilot Deployment Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
349 |  |  |  | 1.8.14.3.3 | Resolve Modifications from Pilot Deployment Plan Peer Review |  | Resolve Modifications from Pilot Deployment Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
350 |  |  |  | 1.8.14.3.4 | Document and Communicate Pilot Deployment Plan Peer Review Results |  | Document and Communicate Pilot Deployment Plan Peer Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
351 |  |  | 1.8.13.4 | Review and Approve Pilot Deployment Plan |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
352 |  |  |  | 1.8.13.4.1 | Perform Pilot Deployment Plan Verification |  | Perform Pilot Deployment Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
353 |  |  |  |  | 1.8.13.4.1 | Identify Pilot Deployment Plan Reviewers | Identify Pilot Deployment Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
354 |  |  |  |  | 1.8.13.4.2 | Schedule Review and Approve Pilot Deployment Plan Review | Schedule Review and Approve Pilot Deployment Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
355 |  |  |  |  | 1.8.13.4.3 | Conduct Review and Approve Pilot Deployment Plan Meeting | Conduct Review and Approve Pilot Deployment Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
356 |  |  |  |  | 1.8.13.4.4 | Review and Log Pilot Deployment Plan Feedback | Review and Log Pilot Deployment Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 0 | #REF!
357 |  |  |  | 1.8.13.4.2 | Analyze Pilot Deployment Plan Verification Results |  | Analyze Pilot Deployment Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
358 |  |  |  |  | 1.8.13.4.1 | Resolve Pilot Deployment Plan Feedback | Resolve Pilot Deployment Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
359 |  |  |  |  | 1.8.13.4.2 | Verify Closure of Pilot Deployment Plan Feedback | Verify Closure of Pilot Deployment Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
360 |  |  |  |  | 1.8.13.4.3 | Document and Communicate Pilot Deployment Plans Review Results | Document and Communicate Pilot Deployment Plans Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
361 |  |  |  |  | 1.8.13.4.4 | Obtain Approval and Pilot Deployment Plan | Obtain Approval and Pilot Deployment Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 0 | #REF!
362 |  |  | 1.8.13.5 | Develop Site Deployment Plan | [7 empty] | 0.18 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
363 |  |  |  | 1.8.13.5.1 | DevelopSite Security Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
364 |  |  |  | 1.8.13.5.2 | Develop Site Data Conversion and Load Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
365 |  |  |  | 1.8.13.5.3 | Develop Site Deployment Schedule | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
366 |  |  |  | 1.8.13.5.4 | Develop Site Test Plans | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
367 |  |  |  | 1.8.13.5.5 | Develop Site Operations, Maintenance and Support Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
368 |  |  |  | 1.8.13.5.6 | Develop Site Application Disaster Recovery Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
369 |  |  |  | 1.8.13.5.7 | Document Site Deployment Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
370
371 |  |  |  | 1.4.5.3.8 | Review Site Deployment Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
372 |  |  |  | 1.4.5.3.9 | Obtain Approval and Baseline SDP | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
373
374 |  |  | 1.8.13.6 | Develop System Deployment Schedule | [7 empty] | 0.05 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
375 |  |  | 1.8.13.7 | Document System Deployment Plan | [7 empty] | 0.05 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
376 |  |  | 1.4.5.6 | Willow will will | [7 empty] | 0.02 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
377
378 |  |  | 1.4.5.7 | Ensure Review System Deployment Plan | [7 empty] | 0.02 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
379 |  |  |  | 1.4.5.7.1 | Identify Reviewers | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
380 |  |  |  | 1.4.5.7.2 | Schedule Review | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
381 |  |  |  | 1.4.5.7.3 | Review and Log Feedback | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
382 |  |  |  | 1.4.5.7.4 | Fix Defects Detected from Review | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
383 |  |  |  | 1.4.5.7.5 | Verify Closure of Defects | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
384 |  |  |  | 1.4.5.7.1 | Document and Communicate Review Results | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
385 |  |  | 1.4.4.8 | Obtain Approval and Baseline DP | [7 empty] | 0.134 |  |  |  |  | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
386
387 |  | 1.8.14 | System Deployment Plan Completed | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
388 |  | 1.8.15 | Configure, Integrate and Deliver System |  |  |  |  | Supplier |  |  | 0.025 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  | 0 | #REF!
389 |  |  | 1.8.15.1 | Integrate and Build the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
390 |  |  | 1.8.15.2 | Configure the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
391 |  |  | 1.8.15.3 | Conduct Integration Testing | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
392 |  |  | 1.8.15.4 | Update Requirements Traceability Matrix (RTM) | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
393 |  |  | 1.8.15.5 | Develop System Documentation and Training Material for the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
394 |  |  | 1.8.15.6 | Deliver the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
395 |  | 1.8.16 | Conduct System Testing Readiness Review | [7 empty] | 0.01 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  | 0 | #REF!
396 |  |  | 1.8.16.1 | Set Up Test Environment | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
397 |  |  |  | 1.8.16.1.1 | Install Test Environment
398 |  |  |  | 1.8.16.1.2 | Apply Inftrastructure Changes
399 |  |  |  | 1.8.16.1.3 | Apply Security Changes
400 |  |  |  | 1.8.16.1.4 | Convent and Migrate Data
401 |  |  |  | 1.8.16.1.5 | Verity Test Environment
402 |  |  |  | 1.8.16.1.6 | Verify and Audit Test Environment
403 |  |  |  | 1.8.16.1.7 | Fix Gaps Related to Test Environment
404 |  |  | 1.8.16.2 | Test Build and Installation of the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
405 |  |  |  | 1.8.16.2.1 | Verify Installation and System Documentation
406 |  |  |  | 1.8.16.2.2 | Fix Defects and Issues
407 |  |  |  | 1.8.16.2.3 | Update Installation and System Documentation
408 |  |  |  | 1.8.16.2.1 | Build the System
409 |  |  |  | 1.8.16.2.1 | Install and Configure the System
410 |  |  |  | 1.8.16.2.1 | Obtain Approval and Check-in System Documentation, SC and Installation Guide
411 |  |  | 1.8.16.3 | Conduct system test readiness review meeting | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
412 |  |  | 1.8.16.4 | Conduct Release Audit | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
413 |  | 1.4.10 | Conduct Construct Tollgate | [7 empty] | 0.01 |  |  |  |  | 0 | [6 empty] | 0 | 0 |  | 0 | #REF!
414 |  |  | 1.4.10.1 | Update Plan(s) for Test and Deploy Phases |  |  |  | Project Manager,CM Lead,QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
415 |  |  | 1.4.10.2 | Request Tollgate Review |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
416 |  |  | 1.4.10.3 | Update Business Case |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
417 |  |  | 1.4.10.4 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
418 |  |  | 1.4.10.5 | Review Plan(s) for Test and Deploy Phases |  |  |  | PMO Prg. Mgr.[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
419 |  |  | 1.4.10.6 | Review Work Product Baseline and Conduct CM Audit |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
420 |  |  | 1.4.10.7 | Conduct CM Audits |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
421 |  |  | 1.4.10.8 | Prepare Construct Tollgate Review Report |  |  |  | Project Manager[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
422 |  |  | 1.4.10.9 | Update and Communicate Construct Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
423 |  |  | 1.4.10.10 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
424 |  |  | 1.4.10.11 | Close Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
425 |  | 1.4.11 | Construct Tollgate Conducted
426 | [22 empty] | #VALUE! | #VALUE! |  | 0 | 0
427 | 1.5 | Build | [7 empty] | #REF!
428 |  |  | Develop Source Code and Conduct Unit Testing
429 |  |  | Update Requirements Traceability Matrix (RTM)
430 |  |  | Develop Integration Test Cases
431
432 | 1.6 | Test | [7 empty] | #REF! |  |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! |  | 0 | 0
433 |  | 1.5.1 | Conduct System Testing | [19 empty] | #VALUE! | #VALUE! |  | 0 | 0
434 |  |  | 1.5.1.1 | Develop Test Scripts |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
435 |  |  | 1.5.1.2 | Validate Test Scripts |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
436 |  |  | 1.5.1.3 | Update Requirements Traceability Matrix |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
437 |  |  | 1.5.1.4 | Check-In Test Scripts and Requirements Traceability Matrix |  |  |  | Supplier Lead[60%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
438 |  |  | 1.5.1.5 | Set Up Test Environment | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
439 |  |  |  | 1.5.1.5.1 | Install Test Environment |  |  | Project Manager, Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
440 |  |  |  | 1.5.1.5.2 | Apply Infrastructure Changes |  |  | Project Manager,Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
441 |  |  |  | 1.5.1.5.3 | Apply Security Changes |  |  | Project Manager,Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
442 |  |  |  | 1.5.1.5.4 | Convert and Migrate Data |  |  | Project Manager,Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
443 |  |  |  | 1.5.1.5.5 | Verify Test Environment |  |  | Test Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
444 |  |  |  | 1.5.1.5.6 | Verify and Audit Test Environment |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
445 |  |  |  | 1.5.1.5.7 | Fix Gaps Related to Test Environment |  |  | Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
446 |  |  | 1.5.1.6 | Test Build and Installation of the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
447 |  |  |  | 1.5.1.6.1 | Build the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
448 |  |  |  | 1.5.1.6.2 | Install and Configure the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
449 |  |  |  | 1.5.1.6.3 | Verify Installation and System Documentation |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
450 |  |  |  | 1.5.1.6.4 | Fix Defects and Issues |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
451 |  |  |  | 1.5.1.6.5 | Update Installation and System Documentation |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
452 |  |  |  | 1.5.1.6.6 | Obtain Approval and Check-In SD, SC and Installation Guide |  |  | CM Lead[30%],Supplier,Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
453 |  |  | 1.5.1.7 | Execute System Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
454 |  |  |  | 1.5.1.7.1 | Prepare System Test Summary Report (STSR) for the Cycle | [20 empty] | 0
455 |  |  |  | 1.5.1.7.1 | Review System Test Summary Report (STSR) for the Cycle
456 |  |  |  | 1.5.1.7.1 | Plan Next Test Cycle
457 |  |  |  | 1.5.1.7.1 | Fix Defects and Issues
458 |  |  |  | 1.5.1.7.1 | Verify System Test Results
459 |  |  |  | 1.5.1.7.1 | Log Defects and Issues
460 |  |  |  | 1.5.1.7.1 | Generate Final System Test Summary Report (STSR)
461 |  |  |  | 1.5.1.7.1 | Check-In System Test Cases and System Test Summary Report (STSR)
462 |  | 1.5.2 | Prepare Pre-Production Environment at Site | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
463 |  |  | 1.5.2.1 | Prepare Site for System Changes | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
464 |  |  |  | 1.5.2.1.1 | Prepare Site for Infrastructure Changes |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
465 |  |  |  | 1.5.2.1.2 | Prepare Site for Security Changes |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
466 |  |  |  | 1.5.2.1.3 | Prepare Site for Application Data Migration |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
467 |  |  | 1.5.2.2 | Create System Migration Plan |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
468 |  |  | 1.5.2.3 | Conduct Test and Site Readiness Review |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
469 |  |  | 1.5.2.4 | Prepare Test Cases for the Sites |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
470 |  |  | 1.5.2.5 | Update System Documentation and Test Plans for the Site |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
471 |  |  | 1.5.2.6 | Update Site Deployment Plan |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
472 |  |  | 1.5.2.7 | Apply Infrastructure Changes |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
473 |  |  | 1.5.2.8 | Apply Security Changes |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
474 |  |  | 1.5.2.9 | Convert and Migrate Data |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
475 |  | 1.5.3 | Conduct Acceptance Testing Readiness Review | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
476 |  |  | 1.5.3.1 | Perform Checks to Verify Pre-Production Environment |  |  |  | Operations and Support Manager,System Deployment Manager,Test Manager,Project Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
477 |  |  | 1.5.3.2 | Fix Gaps Related to Pre-Production Environment |  |  |  | Operations and Support Manager,System Deployment Manager,Test Manager,Project Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
478 |  |  | 1.5.3.3 | Verify and Audit Pre-Production Environment |  |  |  | Test Manager,Project Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
479 |  |  | 1.5.3.4 | Review and Approve System Documentation |  |  |  | Operations and Support Manager,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
480 |  |  | 1.5.3.5 | Test Build and Installation for Acceptance Testing | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
481 |  |  |  | 1.5.3.5.1 | Build the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
482 |  |  |  | 1.5.3.5.2 | Install and Configure the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
483 |  |  |  | 1.5.3.5.3 | Verify Installation and System Documentation |  |  | Supplier,Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
484 |  |  |  | 1.5.3.5.4 | Fix Defects and Issues |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
485 |  |  |  | 1.5.3.5.5 | Update Installation and System Documentation |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
486 |  |  |  | 1.5.3.5.6 | Obtain Approval and Check-In SD, SC and Installation Guide |  |  | Supplier,Project Manager,CM Lead[60%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
487 |  |  | 1.5.3.6 | Conduct Release Audit |  |  |  | Supplier,CM Lead[60%],QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
488 |  |  | 1.5.3.7 | Conduct Acceptance Testing Readiness Review Meeting |  |  |  | Test Manager,System Deployment Manager,Operations and Support Manager,QA Analyst,PMO Prg. Mgr,Project Manager,Senior Manager[40%],End-users | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
489 |  | 1.5.4 | Conduct Acceptance Testing | [19 empty] | #VALUE! | #VALUE! |  | 0 | 0
490 |  |  | 1.5.4.1 | Execute User Acceptance Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
491 |  |  | 1.5.4.2 | Verify Acceptance Test Results | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
492 |  |  | 1.5.4.3 | Log Defects and Issues | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
493 |  |  | 1.5.4.4 | Prepare User Acceptance Test Summary Report (UATSR) for the Cycle | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
494 |  |  | 1.5.4.5 | Ensure Review of User Acceptance Test Summary Report | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
495 |  |  | 1.5.4.6 | Plan Next Test Cycle | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
496 |  |  | 1.5.4.7 | Generate Final User Acceptance Test Summary Report | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
497 |  |  | 1.5.4.8 | Sign-off on User Acceptance Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
498 |  |  | 1.5.4.9 | Approve Acceptance Test Results | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
499 |  |  | 1.5.410 | Communicate Final UATSR to Senior Management | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
500 |  |  | 1.5.4.11 | Provide Approval to Baseline Source, Binaries and System Documentation | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
501 |  |  | 1.5.4.12 | Sign-off on Non-Functional Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
502 |  |  | 1.5.4.13 | Execute Non-Functional Acceptance Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
503 |  | 1.5.5 | Acceptance Testing Conducted | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
504 |  | 1.5.6 | Analyze Defects and Change Requests | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
505 |  | 1.5.7 | Verify Production Readiness | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
506 |  | 1.5.8 | Conduct Test Tollgate | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
507 |  |  | 1.5.8.1 | Update Plan(s) for Deploy Phase |  |  |  | Project Manager,CM Lead,QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
508 |  |  | 1.5.8.2 | Request Tollgate Review |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
509 |  |  | 1.5.8.3 | Update Business Case |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
510 |  |  | 1.5.8.4 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
511 |  |  | 1.5.8.5 | Review Plan(s) for Deploy Phase |  |  |  | PMO Prg. Mgr.[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
512 |  |  | 1.5.8.6 | Review Work Product Baseline and Conduct CM Audit |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
513 |  |  | 1.5.8.7 | Conduct CM Audits |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
514 |  |  | 1.5.8.8 | Prepare Test Tollgate Review Report |  |  |  | Project Manager[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
515 |  |  | 1.5.8.9 | Update and Communicate Test Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
516 |  |  | 1.5.8.10 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
517 |  |  | 1.5.8.11 | Close Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
518 |  | 1.5.9 | Accept Product |  |  |  |  | System Deployment Manager[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
519 |  |  | 1.5.8.12.1 | Accept the Acquired Product | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
520 |  |  | 1.5.8.12.2 | Transition product to Operations | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
521 |  |  | 1.5.8.12.3 | Review Supplier Performance | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
522 |  |  | 1.5.8.12.4 | Execute Supplier payment process | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
523 |  | 1.5.9 | Test Tollgate Conducted | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
524
525
526 | 1.6 | Deploy | [7 empty] | #REF! |  |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! |  | 0 | #REF!
527 |  | 1.6.1 | Deploy at Pilot Site | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
528 |  |  | 1.6.1.1 | Migrate to New System at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
529 |  |  |  | 1.6.1.1.1 | Execute Migration |  |  | Pilot Site Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
530 |  |  |  | 1.6.1.1.2 | Perform Checks to Verify Migration |  |  | Pilot Site Lead,Pilot Site Deployment Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
531 |  |  |  | 1.6.1.1.3 | Check Contingency Plan for Alternative(s) |  |  | Pilot Site Lead,Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
532 |  |  |  | 1.6.1.1.4 | Modify System Environment or Components |  |  | Pilot Site Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
533 |  |  |  | 1.6.1.1.5 | Execute Back out Plan |  |  | Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
534 |  |  |  | 1.6.1.1.6 | Communicate To Stakeholders |  |  | Pilot Site Deployment Manager,Senior Manager,Pilot Site Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
535 |  |  |  | 1.6.1.1.7 | Communicate Deployment Status |  |  | System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
536 |  |  | 1.6.1.2 | Migrated to New System at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
537 |  |  | 1.6.1.3 | Update Generic Site Deployment Materials & System Documentation |  |  |  | Pilot Site Deployment Manage,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
538 |  |  | 1.6.1.4 | Transition to Operations at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
539 |  |  |  | 1.6.1.4.1 | Support New System |  |  | Pilot Site Deployment Team Member,Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
540 |  |  |  | 1.6.1.4.2 | Transfer Ownership to System Owner |  |  | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
541 |  |  |  | 1.6.1.4.3 | Archive System Documentation, Training Material & Application/System Components |  |  | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
542 |  |  |  | 1.6.1.4.4 | Train Operations Team |  |  | Pilot Site Operations & Support Team,System Owner,Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
543 |  |  | 1.6.1.5 | De-Install Legacy System at Pilot Site |  |  |  | Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
544 |  |  | 1.6.1.6 | Legacy System De-Installed at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
545 |  | 1.6.2 | Deploy at Site <1> | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
546 |  |  | 1.6.2.1 | Migrate to New System at at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
547 |  |  |  | 1.6.2.1 | Execute Migration |  |  | Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
548 |  |  |  | 1.6.2.2 | Perform Checks to Verify Migration |  |  | Site1 Deployment Manager[30%],Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
549 |  |  |  | 1.6.2.3 | Check Contingency Plan for Alternative(s) |  |  | Site1 Deployment Manager,Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
550 |  |  |  | 1.6.2.4 | Modify System Environment or Components |  |  | Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
551 |  |  |  | 1.6.2.5 | Execute Back out Plan |  |  | Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
552 |  |  |  | 1.6.2.6 | Communicate To Stakeholders |  |  | Site1 Manager,Senior Manager,Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
553 |  |  |  | 1.6.2.7 | Communicate Deployment Status |  |  | System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
554 |  |  | 1.6.2.2 | Migrated to New System at at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
555 |  |  | 1.6.2.3 | Update Generic Site Deployment Materials & System Documentation |  |  |  | Site1 Deployment Manage,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
556 |  |  | 1.6.2.4 | Transition to Operations at at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
557 |  |  |  | 1.6.2.4.1 | Support New System |  |  | Site1 Deployment Manager,Site1 Deployment Team Member | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
558 |  |  |  | 1.6.2.4.2 | Transfer Ownership to System Owner |  |  | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
559 |  |  |  | 1.6.2.4.3 | Archive System Documentation, Training Material & Application/System Components |  |  | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
560 |  |  |  | 1.6.2.4.4 | Train Operations Team |  |  | Site1 Deployment Manager,System Owner,Site1 Operations & Support Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
561 |  |  | 1.6.2.5 | De-Install Legacy System at at Site <1> |  |  |  | Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
562 |  |  | 1.6.2.6 | Legacy System De-Installed at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | 0
563
564 | 1.7 | Close Project | [7 empty] | #REF! | [12 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
565 |  | 1.7.1 | Conduct Post-Project Review | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
566 |  |  | 1.7.1.1 | Develop Post Project Review Breakout Session Topics & Agenda |  |  |  | Project Team,Project Manager,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
567 |  |  | 1.7.1.1 | Conduct Post Project Review Meeting |  |  |  | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
568 |  |  | 1.7.1.1 | Complete Post Project Review Report |  |  |  | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
569 |  |  | 1.7.1.1 | Create Project Role Feedback Forms |  |  |  | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
570 |  | 1.7.2 | Archive Documents |  |  |  |  | Project Manager,Project Team,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
571 |  | 1.7.3 | Close Project formally and Communicate |  |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
572 |  | 1.7.4 | Project <PTS -ID> Closed | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
573
Formulas:
Start date = IF(ISBLANK([Depend]),,WORKDAY(VLOOKUP([Depend],A2:AG150,26),0))
End date = (WORKDAY([Start date],Sheet2!C2*5))
End date = (WORKDAY([Start date],[Estimated Duration]))
Cost Gap = (WORKDAY(AA156,[Projected Cost]))
Cost Gap = WORKDAY(AA165,[Projected Cost])

## COTS
Line Number |  | Task Name | [5 empty] | Resource Names |  | Percent |  |  |  |  | Estimated Hours |  |  |  | Cost |  |  |  | Estimated Days | Estimated Duration | Depend | Start date | End date | Risk Date
1 | Project Schedule for Template | [5 empty] | Project Schedule for Template |  |  | 100% | [8 empty] | 88920 | [6 empty] | 44747 | 45020
2 | 1.1 | Entrance Criteria | [23 empty] | 44747 | 44747
3 |  | 1.1.1 | Approved Project Business Case
4 |  | 1.1.2 | Development Process Design Document
5 |  | 1.1.2 | Scheduled on Portfolio Roadmap | [22 empty] | 44747 | 44747
6 | 1.2 | Initiating | [7 empty] | 3% | 85% |  |  |  | 46.8 | [7 empty] | 7.8 | 7.8 |  | 0
7 |  | 1.1.2 | Develop Preliminary Project Plan |  |  |  | Develop Preliminary Project Plan |  |  |  | 20% | 100% |  |  |  | 9.36 |  |  |  | 936 |  |  | 1.56 | 1.6 | 3 | 0 | 2
8 |  |  | 1.2.1.1 | Create Preliminary Project Plan |  |  | Create Preliminary Project Plan | Project Manager | 1 |  |  | 100% |  |  |  |  | 9.36 |  |  |  | 936 |  | 1.56 | 1.6 | 3 | 0 | 2
9 |  | 1.1.3 | Perform Preliminary Project Plan Peer Review |  |  |  | Perform Preliminary Project Plan Peer Review |  |  |  | 10% | 100% |  |  |  | 4.68 |  |  |  | 468 |  |  | 0.78 | 0.8 | 4 | 0 | 10
10 |  |  | 1.1.3.1 | Prepare for Preliminary Project Plan Peer Review |  |  | Prepare for Preliminary Project Plan Peer Review |  |  |  |  | 35% | 100% |  |  |  | 1.638 |  |  |  | #REF! |  | 0.273 | 0.3 |  | 0 | 0
11 |  |  |  | 1.1.3.1.1 | Identify Preliminary Project Plan Peer Review Reviewers | [7 empty] | 10% |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
12 |  |  |  | 1.1.3.1.2 | Check Draft Preliminary Project Plan |  | Check Draft Preliminary Project Plan | Project Manager | 1 |  |  |  | 80% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
13 |  |  |  | 1.1.3.1.3 | Schedule Preliminary Project Plan Peer Review Meeting |  | Schedule Preliminary Project Plan Peer Review Meeting |  | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
14 |  |  | 1.1.3.2 | Conduct Preliminary Project Plan Peer Review |  |  | Conduct Preliminary Project Plan Peer Review |  |  |  |  | 20% | 100% |  |  |  | 0.936 |  |  |  | 93.6 |  | 0.156 | 0.2 | 4 | 0 | 0
14 |  |  |  | 1.1.3.2.1 | Conduct Preliminary Project Peer Plan Review Meeting |  | Conduct Preliminary Project Peer Plan Review Meeting |  | 1 |  |  |  | 80% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
15 |  |  |  | 1.1.3.2.2 | Review and Log Project Plan Peer Review Feedback |  | Review and Log Project Plan Peer Review Feedback |  | 1 |  |  |  | 20% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
16 |  |  | 1.1.3.3 | Analyze Preliminary Project Plan Peer Review |  |  | Analyze Preliminary Project Plan Peer Review |  |  |  |  | 45% | 100% |  |  |  | 2.106 |  |  |  | 210.6 |  | 0.351 | 0.4 | 9 | 4 | 4
17 |  |  |  | 1.1.3.3.1 | Resolve Preliminary Project Plan Feedback | [7 empty] | 35% |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
18 |  |  |  | 1.1.3.3.2 | Preliminary Project Plan Peer Review Follow Up |  | Preliminary Project Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 20% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
19 |  |  |  | 1.1.3.3.3 | Resolve Modifications from Preliminary Project Plan Peer Review |  | Resolve Modifications from Preliminary Project Plan Peer Review | Project Manager | 1 |  |  |  | 35% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
20 |  |  |  | 1.1.3.3.4 | Document and Communicate Preliminary Project Plan Review Results |  | Document and Communicate Preliminary Project Plan Review Results | Project Manager | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
21 |  | 1.1.4 | Review and Approve Preliminary Project Plan |  |  |  | Review and Approve Preliminary Project Plan |  |  |  | 5% | 100% |  |  |  | 2.34 |  |  |  | 234 |  |  | 0.39 | 0.4 | 6 | 0 | 0
22 |  |  | 1.1.4.1 | Perform Preliminary Project Plan Verification |  |  | Perform Preliminary Project Plan Verification |  |  |  |  | 40% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
23 |  |  |  | 1.1.4.1.1 | Identify Preliminary Project Plan Reviewers |  | Identify Preliminary Project Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 12% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
24 |  |  |  | 1.1.4.1.2 | Schedule Review and Approve Preliminary Project Plan Review |  | Schedule Review and Approve Preliminary Project Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 2% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
25 |  |  |  | 1.1.4.1.3 | Conduct Review and Approve Preliminary Project Plan Meeting |  | Conduct Review and Approve Preliminary Project Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 38% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
26 |  |  |  | 1.1.4.1.4 | Review and Log Preliminary Project Plan Feedback |  | Review and Log Preliminary Project Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 48% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
27 |  |  | 1.1.4.2 | Analyze Preliminary Project Plan Verification Results |  |  | Analyze Preliminary Project Plan Verification Results |  |  |  |  | 60% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
28 |  |  |  | 1.1.4.2.1 | Resolve Preliminary Project Plan Feedback |  | Resolve Preliminary Project Plan Feedback |  | 1 |  |  |  | 50% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
29 |  |  |  | 1.1.4.2.2 | Verify Closure of Preliminary Project Plan Feedback |  | Verify Closure of Preliminary Project Plan Feedback |  | 1 |  |  |  | 30% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
30 |  |  |  | 1.1.4.2.3 | Document and Communicate Preliminary Project Plan Review Results |  | Document and Communicate Preliminary Project Plan Review Results |  | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
31 |  |  |  | 1.1.4.2.4 | Obtain Approval and Baseline Preliminary Project Plan |  | Obtain Approval and Baseline Preliminary Project Plan |  | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
32 |  | 1.1.5 | Develop Project Charter | [7 empty] | 35% | 100% |  |  |  | 16.38 |  |  |  | 1638 |  |  | 2.73 | 2.8 |  | 0 | 3
33 |  |  | 1.1.5.1 | Define Project Scope |  |  |  | Project Manager,QA Analyst | 2 |  |  | 30% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
34 |  |  | 1.1.5.2 | Create Project Charter Document |  |  |  | Project Manager,QA Analyst | 2 |  |  | 70% |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 28 | 0 | #REF!
35 |  | 1.1.6 | Perform Project Charter Peer Review |  |  |  | Perform Project Charter Peer Review |  |  |  | 10% | 100% |  |  |  | 4.68 |  |  |  | 468 |  |  | 0.78 | 0.8 | 4 | 0 | 10
36 |  |  | 1.1.3.1 | Prepare for Project Charter Peer Review |  |  | Prepare for Project Charter Peer Review |  |  |  |  | 10% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
37 |  |  |  | 1.1.3.1.1 | Identify Project Charter Peer Review Reviewers | [7 empty] | 10% |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
38 |  |  |  | 1.1.3.1.2 | Check Draft Project Charter |  | Check Draft Project Charter | Project Manager | 1 |  |  |  | 80% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
39 |  |  |  | 1.1.3.1.3 | Schedule Project Charter Peer Review Meeting |  | Schedule Project Charter Peer Review Meeting |  | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0
40 |  |  | 1.1.3.2 | Conduct Project Charter Peer Review |  |  | Conduct Project Charter Peer Review |  |  |  |  | 45% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 4 | 0 | #REF!
41 |  |  |  | 1.1.3.2.1 | Conduct Project Charter Peer Review Meeting |  | Conduct Project Charter Peer Review Meeting |  | 1 |  |  |  | 100% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
42 |  |  | 1.1.3.3 | Analyze Project Charter Plan Peer Review |  |  | Analyze Project Charter Plan Peer Review |  |  |  |  | 45% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 9 | 4 | #REF!
43 |  |  |  | 1.1.3.3.1 | Resolve Project Charter Plan Feedback |  | Resolve Project Charter Plan Feedback | Project Manager | 1 |  |  |  | 35% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
44 |  |  |  | 1.1.3.3.2 | Project Charter Plan Peer Review Follow Up |  | Project Charter Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 20% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
45 |  |  |  | 1.1.3.3.3 | Resolve Modifications from Project Charter Peer Review |  | Resolve Modifications from Project Charter Peer Review | Project Manager | 1 |  |  |  | 35% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
46 |  |  |  | 1.1.3.3.4 | Document and Communicate Project Charter Review Results |  | Document and Communicate Project Charter Review Results | [5 empty] | 10% |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
47 |  | 1.1.7 | Review and Approve Project Charter |  |  |  | Review and Approve Project Charter |  |  |  | 5% | 100% |  |  |  | 2.34 |  |  |  | 234 |  |  | 0.39 | 0.4 | 6 | 0 | 0
48 |  |  | 1.1.4.1 | Perform Preliminary Project Plan Verification |  |  | Perform Preliminary Project Plan Verification |  |  |  |  | 40% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
49 |  |  |  | 1.1.4.1.1 | Identify Project Charter Reviewers |  | Identify Project Charter Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 12% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
50 |  |  |  | 1.1.4.1.2 | Schedule Review and Approve Project Charter Review |  | Schedule Review and Approve Project Charter Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 2% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
51 |  |  |  | 1.1.4.1.3 | Conduct Review and Approve Project Charter Plan Meeting |  | Conduct Review and Approve Project Charter Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 38% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
52 |  |  |  | 1.1.4.1.4 | Review and Log Project Charter Feedback |  | Review and Log Project Charter Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 48% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
53 |  |  | 1.1.4.2 | Analyze Project Charter Verification Results |  |  | Analyze Project Charter Verification Results |  |  |  |  | 60% | 100% |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
54 |  |  |  | 1.1.4.2.1 | Resolve Project Charter Feedback |  | Resolve Project Charter Feedback |  | 1 |  |  |  | 50% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
55 |  |  |  | 1.1.4.2.2 | Verify Closure of Project Charter Feedback |  | Verify Closure of Project Charter Feedback |  | 1 |  |  |  | 30% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
56 |  |  |  | 1.1.4.2.3 | Document and Communicate Project Charter Review Results |  | Document and Communicate Project Charter Review Results |  | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
57 |  |  |  | 1.1.4.2.4 | Obtain Approval and Baseline Project Charter |  | Obtain Approval and Baseline Project Charter |  | 1 |  |  |  | 10% |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
|  | 1.1.8 | Identify Stakeholders | [19 empty] | #VALUE! | #VALUE!
58 |  | 1.1.8 | Develop Project Schedule for Planning | [19 empty] | #VALUE! | #VALUE!
59 |  |  | 1.1.8.1 | Confirm Planning Activities and Task | [18 empty] | #VALUE! | #VALUE!
60 |  |  | 1.1.8.2 | Estimate Effort for Planning | [18 empty] | #VALUE! | #VALUE!
61 |  | 1.1.9 | Initiating Risk | [19 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
62 |  | 1.1.10 | Initiating Completed | [22 empty] | 0 | 0
63 | 1.3 | Planning | [7 empty] | 7% | 1.2236 |  |  |  | 109.2 |  |  |  | 10920 |  |  |  | 18.2 | #REF! | 2 | 0 | #REF!
64 |  | 1.3.1 | Estimate Effort for Selection & Define | [7 empty] | 0.18 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 6 | 0 | #REF!
65 |  |  | 1.3.1.1 | Identify Estimation Team |  |  |  | Requirements Analyst,Project Manager | 2 |  |  | 0.15 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
66 |  |  | 1.3.1.2 | Identify Estimation Method |  |  |  | Requirements Analyst,Project Manager | 2 |  |  | 0.15 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
67 |  |  | 1.3.1.3 | Estimate Size, Effort, Cost and Forecast Dates |  |  |  | Requirements Analyst,Project Manager | 2 |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
68 |  |  | 1.3.1.4 | Review and Validate Cost Estimates |  |  |  | Requirements Analyst,Project Manager | 2 |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
69 |  |  | 1.3.1.5 | Prepare Estimation Reports |  |  |  | Requirements Analyst,Project Manager | 2 |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
70 |  | 1.3.2 | Review and Approve Selection & Define Cost Estimate |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
71 |  |  | 1.3.2.1 | Perform Selection & Define Verification |  |  | Perform Selection & Define Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
72 |  |  |  | 1.3.2.1.1 | Identify Selection & Define Cost Estimate Reviewers |  | Identify Selection & Define Cost Estimate Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
73 |  |  |  | 1.3.2.1.2 | Schedule Review and Approve Selection & Define Cost Estimate Review |  | Schedule Review and Approve Selection & Define Cost Estimate Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
74 |  |  |  | 1.3.2.1.3 | Conduct Review and Approve Selection & Define Cost Estimate Plan Meeting |  | Conduct Review and Approve Selection & Define Cost Estimate Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
75 |  |  |  | 1.3.2.1.4 | Review and Log Selection & Define Cost Estimate Feedback |  | Review and Log Selection & Define Cost Estimate Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
76 |  |  | 1.3.2.2 | Analyze Selection & Define Cost Estimate Verification Results |  |  | Analyze Selection & Define Cost Estimate Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
77 |  |  |  | 1.3.2.2.1 | Resolve Selection & Define Cost Estimate Feedback |  | Resolve Selection & Define Cost Estimate Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
78 |  |  |  | 1.3.2.2.2 | Verify Closure of Selection & Define Cost Estimate Feedback |  | Verify Closure of Selection & Define Cost Estimate Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
79 |  |  |  | 1.3.2.2.3 | Document and Communicate Selection & Define Cost Estimate Review Results |  | Document and Communicate Selection & Define Cost Estimate Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
80 |  |  |  | 1.3.2.2.4 | Obtain Approval and Baseline Selection & Define Cost Estimate |  | Obtain Approval and Baseline Selection & Define Cost Estimate |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
81 |  | 1.3.3 | Develop Project Plan | [7 empty] | 0.22 | 1.3 |  |  |  | #REF! |  |  |  | #REF! | 0 | 0 | #REF! | #REF! | 6 | 0 | #REF!
82 |  |  | 1.3.3.1 | Develop Project Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
83 |  |  | 1.3.3.2 | Develop Scope Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
84 |  |  | 1.3.3.3 | Develop Schedule Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
85 |  |  | 1.3.3.4 | Develop Cost Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
86 |  |  | 1.3.3.5 | Develop Quality Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
87 |  |  | 1.3.3.6 | Develop Human Resource Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
88 |  |  | 1.3.3.7 | Develop Communications Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
89 |  |  | 1.3.3.8 | Develop Risk Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
90 |  |  | 1.3.3.9 | Develop Procurement Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
91 |  |  | 1.3.3.10 | Develop Stakeholder Management Plan |  |  |  |  | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! |  | 0 | #REF!
92 |  |  | 1.3.3.11 | Identify Customer Deliverables |  |  |  | Project Manager,Project Team | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
93 |  |  | 1.3.3.12 | Identify Reusable Components |  |  |  | Project Manager[50%] | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
94 |  |  | 1.3.3.13 | Tailor Project for Project Characteristics |  |  |  | Project Manager,QA Analyst | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 14 | 0 | #REF!
95 |  |  | 1.3.3.14 | Develop Peer Review Plan |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
96 |  |  | 1.3.3.15 | Identify Resources, Tools and Training Needs |  |  |  | Project Manager,Project Team | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 15 | 0 | #REF!
97 |  |  | 1.3.3.16 | Document CM Plan |  |  |  | Project Manager,CM Lead | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
98 |  |  | 1.3.3.17 | Document Project Data Management Plan |  |  |  | Project Manager,CM Lead | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
99 |  |  | 1.3.3.18 | Document QA Plan |  |  |  | Project Manager,QA Analyst | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
100 |  |  | 1.3.3.19 | Document Stakeholder(s) Involvement Plan |  |  |  | Project Manager,Project Team,Senior Manager | 3 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
101 |  |  | 1.3.3.20 | Document Project Training Plan |  |  |  | Project Manager,Project Team | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
102 |  |  | 1.3.3.21 | Identify Critical Dependencies and Issues |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 15 | 0 | #REF!
103 |  |  | 1.3.3.22 | Asess and Create Procurement Plan for Acquiring Supplier/Products for System Deployment |  |  |  | Project Manager,Project Team | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
104 |  |  | 1.3.3.23 | Refine and Optimize Project Schedule |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
105 |  |  | 1.3.3.24 | Document Prelimnary Project Plan |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 12 | 0 | #REF!
106 |  |  | 1.3.3.25 | Check for Consistency in PQP, QA Plan, Risk Mgmt, CM Plan and Schedule |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 26 | 19 | #REF!
107 |  |  | 1.3.3.26 | Orient QA with Project Background |  |  |  | QA Analyst,Project Manager | 2 |  |  | 0.05 |  |  |  |  | #REF! |  |  | 0 | #REF! | 0 | #REF! | #REF! | 26 | 19 | #REF!
108 |  | 1.3.4 | Perform Project Plan Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
109 |  |  | 1.3.4.1 | Prepare for Project Plan Peer Review |  |  | Prepare for Project Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
110 |  |  |  | 1.3.4.1.1 | Identify Project Plan Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
111 |  |  |  | 1.3.4.1.2 | Check Draft Project Plan |  | Check Draft Project Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
112 |  |  |  | 1.3.4.1.3 | Schedule Project Plan Peer Review Meeting |  | Schedule Project Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
113 |  |  | 1.3.4.2 | Conduct Project Plan Peer Review |  |  | Conduct Project Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
114 |  |  |  | 1.3.4.2.1 | Conduct Project Peer Plan Review Meeting |  | Conduct Project Peer Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
115 |  |  |  | 1.3.4.2.2 | Review and Log Project Plan Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
116 |  |  | 1.3.4.3 | Analyze Project Plan Peer Review |  |  | Analyze Project Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
117 |  |  |  | 1.3.4.3.1 | Resolve Project Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
118 |  |  |  | 1.3.4.3.2 | Project Plan Peer Review Follow Up |  | Project Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
119 |  |  |  | 1.3.4.3.3 | Resolve Modifications from Project Plan Peer Review |  | Resolve Modifications from Project Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
120 |  |  |  | 1.3.4.3.4 | Document and Communicate Project Plan Review Results |  | Document and Communicate Project Plan Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
121 |  | 1.3.2 | Review and Approve Project Plan |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
122 |  |  | 1.3.2.1 | Perform Preliminary Project Plan Verification |  |  | Perform Preliminary Project Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
123 |  |  |  | 1.3.2.1.1 | Identify Define Phase Cost Estimate Reviewers |  | Identify Define Phase Cost Estimate Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
124 |  |  |  | 1.3.2.1.2 | Schedule Review and Approve Define Phase Cost Estimate Review |  | Schedule Review and Approve Define Phase Cost Estimate Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
125 |  |  |  | 1.3.2.1.3 | Conduct Review and Approve Define Phase Cost Estimate Plan Meeting |  | Conduct Review and Approve Define Phase Cost Estimate Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
126 |  |  |  | 1.3.2.1.4 | Review and Log Define Cost Estimate Feedback |  | Review and Log Define Cost Estimate Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
127 |  |  | 1.3.2.2 | Analyze Define Phase Cost Estimate Verification Results |  |  | Analyze Define Phase Cost Estimate Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
128 |  |  |  | 1.3.2.2.1 | Resolve Define Cost Estimate Feedback |  | Resolve Define Cost Estimate Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
129 |  |  |  | 1.3.2.2.2 | Verify Closure of Define Cost Estimate Feedback |  | Verify Closure of Define Cost Estimate Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
130 |  |  |  | 1.3.2.2.3 | Document and Communicate Define Cost Estimate Review Results |  | Document and Communicate Define Cost Estimate Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
131 |  |  |  | 1.3.2.2.4 | Obtain Approval and Baseline Define Cost Estimate |  | Obtain Approval and Baseline Define Cost Estimate |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
132 |  | 1.3.3 | Procure Resources for Selection & Define | [7 empty] | 0.1 | 3.04 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 17 | 0 | #REF!
133 |  |  | 1.3.3.1 | Engage Time and Material Resources |  |  |  | Project Manager,PMO Prg. Mgr.,WWP/Contract Manager | 3 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
134 |  |  | 1.3.3.2 | Allocate Resources for Define |  |  |  | Project Manager | 1 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
135 |  |  | 1.3.3.10 | Orient Project Team on Project Plan |  |  |  |  | 1 |  |  | 0.04 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
136 |  | 1.3.4 | PlanningTollgate Review | [7 empty] | 0.05 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 10 | 0 | #REF!
137 |  |  | 1.3.4.1 | Update Plan(s) for Define, Construct, Test and Deploy s |  |  |  | Project Manager,CM Lead,QA Analyst | 3 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 10 | 0 | #REF!
138 |  |  | 1.3.4.2 | Request Tollgate Review |  |  |  | Project Manager | 1 |  |  | 0.01 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 10 | 0 | #REF!
139 |  |  | 1.3.4.3 | Update and Approve (when applicable) Business Case |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 10 | 0 | #REF!
140 |  |  | 1.3.4.4 | Prepare for PlanningPhase Tollgate Review |  |  |  | Stakeholder | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 10 | 0 | #REF!
141 |  |  | 1.3.4.5 | Conduct PlanningPhase Tollgate |  |  |  | PMO Prg. Mgr. | 1 |  |  | 0.14 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 10 | 0 | #REF!
142 |  |  | 1.3.4.6 | Review Work Product Baseline |  |  |  | QA Analyst | 1 |  |  | 0.45 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 56 | 23 | #REF!
143 |  |  |  | Review Plan(s) for Define, Test and Deplay
144 |  |  | 1.3.4.7 | Conduct CM Audits |  |  |  | QA Analyst | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 57 | 24 | #REF!
145 |  |  | 1.3.4.8 | Prepare PlanningTollgate Review Report |  |  |  | Project Manager | 1 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 58 | 0 | #REF!
146 |  |  | 1.3.4.9 | Update and Communicate Tollgate Review Report |  |  |  | Senior Manager,Project Manager,Supplier,Stakeholder,Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] | 10 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 59 | 0 | #REF!
147 |  |  | 1.3.4.10 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager | 3 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 60 | 0 | #REF!
148 |  |  | 1.3.4.11 | Close Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager | 4 |  |  | 0.05 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 61 | 0 | #REF!
149 |  | 1.3.11 | Planning Risk | [12 empty] | #REF! |  |  |  | 0 |  |  | #REF! | #REF! |  | 0 | #REF!
150 |  | 1.3.12 | Planning Completed | [22 empty] | 0 | 0
151 | 1.4 | Selection | [7 empty] | 5% | 0.11 |  |  |  | 78 |  |  |  | 7800 |  |  |  | 13 | 13 | 51 | 18 | 37
152 |  | 1.4.1 | Develop and Release RFI
153 |  | 1.4.2 | Develop and Release RFP
154 |  |  | 1.4.2.1 | Develop Initial Version of Supplier Management Plan |  |  |  |  | 1 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
155 |  |  | 1.4.2.2 | Develop RFP and Evaluation Criteria |  |  |  | Project Manager | 1 |  |  | 0.33 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
156 |  |  | 1.4.2.3 | Distribute RFP to Suppliers |  |  |  | WWP/Contract Manager | 1 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
157 |  |  | 1.4.2.4 | Evaluate Proposals |  |  |  | Project Manager | 1 |  |  | 0.25 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
158 |  |  | 1.4.2.5 | Approve Supplier(s) Down-Select |  |  |  | Senior Manager,Project Manager | 2 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
159 |  |  | 1.4.2.6 | Negotiate Agreement and Select Final Supplier |  |  |  |  | 1 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
160 |  |  | 1.4.2.7 | Get Single Sourcing Justification Letter and Obtain Approval |  |  |  | CM Lead[30%],Senior Manager[30%],Project Manager[30%] | 3 |  |  | 0.06 |  |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 42 | 9 | #REF!
161 |  | 1.4.3 | Establish Supplier Agreement |  |  |  |  | WWP/Contract Manager,Project Manager |  |  | 0.2 | 1 |  |  |  | #REF! | [6 empty] | #REF! | #REF! | 6 | 0 | #REF!
162 |  |  | 1.4.3.1 | Determine Acquisition Type | [7 empty] | 0.08 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0
163 |  |  | 1.4.3.2 | Select Suppiers | [7 empty] | 0.6 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0
164 |  |  | 1.4.3.3 | Establish Supplier Agreements | [7 empty] | 0.32 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0
165 |  | 1.4.4 | Communicate Final Supplier Management Plan | [7 empty] | 0.01 |  |  |  |  | #REF! | [6 empty] | #REF! | #REF! | 51 | 18 | #REF!
166 |  | 1.4.5 | Conduct Selection Review |  |  |  |  | Project Manager[30%],Requirements Analyst |  |  | 0.05 |  |  |  |  | #REF! | [6 empty] | #REF! | #REF! | 67 | 0 | #REF!
167 |  | 1.4.6 | Conduct Bid Evaluations | [7 empty] | 0.05 | 0.45 |  |  |  | #REF! | [6 empty] | #REF! | #REF! | 51 | 18 | #REF!
168 |  |  | 1.4.6.1 | Plan for Product Acquisition |  |  |  | Project Manager,Requirements Analyst |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
169 |  |  | 1.4.6.2 | Plan for Supplier Sourcing (Construct through Deploy) |  |  |  | Project Manager,Senior Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
170 |  |  | 1.4.6.3 | Develop Initial Version of Supplier Management Plan | [7 empty] | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
171 |  |  | 1.4.6.4 | Develop RFP and Evaluation Criteria |  |  |  | Project Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
172 |  |  | 1.4.6.5 | Distribute RFP to Suppliers |  |  |  | WWP/Contract Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
173 |  |  | 1.4.6.6 | Evaluate Proposals |  |  |  | Project Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
174 |  |  | 1.4.6.7 | Approve Supplier(s) Down-Select |  |  |  | Senior Manager,Project Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
175 |  |  | 1.4.6.8 | Negotiate Agreement and Select Final Supplier | [7 empty] | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
176 |  |  | 1.4.6.9 | Get Single Sourcing Justification Letter and Obtain Approval |  |  |  | CM Lead[30%],Senior Manager[30%],Project Manager[30%] |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! |  | 0 | #REF!
177 |  | 1.4.7 | Conduct Selection Tollgate
178 |  |  | 1.4.6.10 | Update Plan(s) for Construct, Test and Deploy Phases |  |  |  | Project Manager,CM Lead,QA Analyst |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 10 | 0 | #REF!
179 |  |  | 1.4.6.11 | Request Tollgate Review |  |  |  | Project Manager[30%] |  |  |  | 0.01 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 10 | 0 | #REF!
180 |  |  | 1.4.6.12 | Update and Approve (when applicable) Business Case |  |  |  | Project Manager[30%] |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 10 | 0 | #REF!
181 |  |  | 1.4.6.13 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 10 | 0 | #REF!
182 |  |  | 1.4.6.14 | Conduct Define Phase Tollgate |  |  |  | PMO Prg. Mgr.[50%] |  |  |  | 0.14 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 10 | 0 | #REF!
183 |  |  | 1.4.6.15 | Review Work Product Baseline |  |  |  | QA Analyst |  |  |  | 0.45 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 56 | 23 | #REF!
184 |  |  | 1.4.6.16 | Conduct CM Audits |  |  |  | QA Analyst |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 57 | 24 | #REF!
185 |  |  | 1.4.6.17 | Prepare Define Tollgate Review Report |  |  |  | Project Manager[20%] |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 58 | 0 | #REF!
186 |  |  | 1.4.6.18 | Update and Communicate Define Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 59 | 0 | #REF!
187 |  |  | 1.4.6.19 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 60 | 0 | #REF!
188 |  |  | 1.4.6.20 | Close Selection Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager |  |  |  | 0.05 |  |  |  |  | #REF! | [5 empty] | #REF! | #REF! | 61 | 0 | #REF!
189 |  | 1.4.7 | Select Risk | [12 empty] | #REF! | [6 empty] | #REF! | #REF! |  | 0 | #REF!
190 |  | 1.4.8 | Select Tollgate Conducted | [22 empty] | 0 | 0
191 | 1.5 | Incremental
192 |  | 1.2.1 | (EPIC) Akron Accounts Receivable
193 |  |  | 1.2.1.1 | (Feature)
194 |  |  |  | 1.2.1.1.1 | Define
195 |  |  |  | 1.2.1.1.2 | Design
196 |  |  |  | 1.2.1.1.3 | Construct
197 |  |  |  | 1.2.1.1.4 | Build
198 |  |  |  | 1.2.1.1.5 | QA Test
199 |  |  | 1.2.1.2 | (Feature)
200 |  |  |  | 1.2.1.1.1 | Define
201 |  |  |  | 1.2.1.1.2 | Design
202 |  |  |  | 1.2.1.1.3 | Construct
203 |  |  |  | 1.2.1.1.4 | Build
204 |  |  |  | 1.2.1.1.5 | QA Test
205 |  | 1.2.2 | (EPIC) Vinca Data
206 |  |  | 1.2.2.1 | (Feature) Vinca Test Data Extract
207 |  |  |  | 1.2.2.1.1 | Define
208 |  |  |  | 1.2.2.1.1 | Design
209 |  |  |  | 1.2.2.1.1 | Construct
210 |  |  |  | 1.2.2.1.1 | Build
211 |  |  |  | 1.2.2.1.1 | QA TEst
212 |  |  | 1.2.2.2 | (Feature) Vinca Real Time Data Load
213 |  |  |  | 1.2.2.1.1 | Define
214 |  |  |  | 1.2.2.1.2 | Design
215 |  |  |  | 1.2.2.1.3 | Construct
216 |  |  |  | 1.2.2.1.4 | Build
217 |  |  |  | 1.2.2.1.5 | QA Test
218 |  | 1.2.3 | (EPIC) Historical Data Repository
219 |  |  | 1.2.3.1 | (Feature) Akron Historical Data Repository
220 |  |  |  | 1.2.1.1.1 | Develop Source Code and Conduct Unit Testing
221 |  |  |  | 1.2.1.1.2 | Update Requirements Traceability Matrix (RTM)
222 |  |  |  | 1.2.1.1.3 | Develop Integration Test Cases
223 |  |  | 1.2.3.2 | (Feature) CA, MN Historical Data Repository
224 |  |  |  | 1.2.1.1.1 | Develop Source Code and Conduct Unit Testing
225 |  |  |  | 1.2.1.1.2 | Update Requirements Traceability Matrix (RTM)
226 |  |  |  | 1.2.1.1.3 | Develop Integration Test Cases
227 |  | 1.2.4 | (EPIC) Epicor Pilot Env.
228 |  |  | 1.2.1.2 | (Feature) Build Pilot Env.
229 |  |  |  | 1.2.1.1.1
230 |  |  |  | 1.2.1.1.2
231 |  |  |  | 1.2.1.1.3
232 |  |  | 1.2.1.2 | (Feature) Load Pilot Data
233 |  |  |  | 1.2.1.1.1 | Develop Source Code and Conduct Unit Testing
234 |  |  |  | 1.2.1.1.2 | Update Requirements Traceability Matrix (RTM)
235 |  |  |  | 1.2.1.1.3 | Develop Integration Test Cases
236 |  |  | 1.2.1.2 | (Feature) Configure Pilot
237 |  |  |  | 1.2.1.1.1 | Develop Source Code and Conduct Unit Testing
238 |  |  |  | 1.2.1.1.2 | Update Requirements Traceability Matrix (RTM)
239 |  |  |  | 1.2.1.1.3 | Develop Integration Test Cases
240 |  | 1.2.5 | Release1
241 |  |  | 1.2.5.1 | (Feature) Vinca Test Data Extract
242 |  |  | 1.2.5.2 | (Feature) Akron Historical Data Repository
243 |  | 1.2.6 | Release2
244 |  |  | 1.2.6.1 | (Feature) CA, MN Historical Data Repository
245 |  |  | 1.2.6.2 | (Feature) Build Pilot Env.
246
247 | 1.6 | Define | [7 empty] | 9% | 0.9299 |  |  |  | 140.4 |  |  |  | 14040 |  |  |  | 23.4 | 23.4 | 51 | 18 | 51
|  | 1.5.1 | Process Description Capturing
248 |  | 1.5.1 | Develop Customer Requirements | [7 empty] | 0.2 | 1.7969 |  |  |  | 28.08 | [6 empty] | 4.68 | 4.7 | 51 | 18 | 24
249 |  |  | 1.5.1.1 | Derive Customer Requirements |  |  |  | Senior Manager[30%],Project Manager[50%],Requirements Analyst[50%] |  |  |  | 0.2 |  |  |  |  | 5.616 | [5 empty] | 0.936 | 1 |  | 0 | 0
250 |  |  | 1.5.3.2 | Complete Customer Requirements Document |  |  |  | Project Manager[20%],Requirements Analyst |  |  |  | 0.5 |  |  |  |  | 14.04 | [5 empty] | 2.34 | 2.4 | 68 | 0 | 3
251 |  |  | 1.5.3.3 | Check for Consistency with Process Design Summary |  |  |  | Project Manager[20%],Requirements Analyst[30%],Process Engineer |  |  |  | 0.02 |  |  |  |  | 0.5616 | [5 empty] | 0.0936 | 0.1 | 69 | 0 | 0
252 |  | 1.5.2 | Customer Requirements Peer Review | [8 empty] | 0.0769 | 1 |  |  |  | 2.1594 | [5 empty] | 0.35989 | 0.4 | 69 | 0 | 0
253 |  |  | 1.5.2.1 | Prepare for Customer Requirements Peer Review |  |  |  | Project Manager |  |  |  |  | 0.35 | 1 |  |  |  | 0.75577 |  |  |  |  | 0.12596 | 0.2 |  | 0 | 0
254 |  |  |  | 1.5.2.1.1 | Identify Customer Requirements Peer Review Reviewers |  |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
255 |  |  |  | 1.5.2.1.2 | Check Customer Requirements |  |  | Project Manager | [5 empty] | 0.8 | [8 empty] | #REF! | #REF! | 69 | 0 | #REF!
256 |  |  |  | 1.5.2.1.3 | Schedule Customer Requirements Peer Review Meeting |  |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #REF! | #REF! | 74 | 18 | #REF!
257 |  |  | 1.5.2.2 | Conduct Customer Requirements Peer Review | [8 empty] | 0.2 | 1 | [8 empty] | #VALUE! | #VALUE!
258 |  |  |  | 1.5.2.2.1 | Conduct Customer Requirements Peer Review Meeting | [8 empty] | 0.8 | [8 empty] | #VALUE! | #VALUE!
259 |  |  |  | 1.5.2.2.2 | Review and Log Customer Requirements Feedback | [8 empty] | 0.2 | [8 empty] | #VALUE!
260 |  |  | 1.5.2.3 | Analyze Customer Requirement Peer Review | [8 empty] | 0.45 | 1 | [8 empty] | #VALUE! | #VALUE!
261 |  |  |  | 1.5.2.3.1 | Resolve Customer Requirement Feedback | [8 empty] | 0.35 | [8 empty] | #VALUE! | #VALUE!
262 |  |  |  | 1.5.2.3.2 | Customer Requirement Peer Review Follow Up | [8 empty] | 0.2 |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 4 | 0 | #REF!
263 |  |  |  | 1.5.2.3.3 | Resolve Modifications from Customer Requirement Peer Review |  |  |  | 1 |  |  |  |  | 0.35 |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
264 |  |  |  | 1.5.2.3.4 | Document and Communicate Customer RequirementReview Results | [8 empty] | 0.1 |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 9 | 4 | #REF!
265 |  | 1.5.3 | Review and Approve Customer Requirements | [19 empty] | #VALUE! | #VALUE!
266 |  |  | 1.5.3.1 | Perform Customer Requirements Verification | [7 empty] | 0.4 | 1 |  |  |  | #REF! | [5 empty] | #REF! | #REF!
267 |  |  |  | 1.5.3.1.1 | Identify Customer Requirements Reviewers |  |  |  | 1 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
268 |  |  |  | 1.5.3.1.2 | Schedule Review and Approve Customer Requirements Review |  |  |  | 1 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
269 |  |  |  | 1.5.3.1.3 | Conduct Review and Approve Customer Requirements Meeting |  |  |  | 1 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
270 |  |  |  | 1.5.3.1.4 | Review and Log Customer Requirements Feedback |  |  |  | 1 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
271 |  |  | 1.5.3.2 | Analyze Customer Requirements Verification Results | [7 empty] | 0.6 | 1 |  |  |  | #REF! | [5 empty] | #REF! | #REF!
272 |  |  |  | 1.5.3.2.1 | Resolve Customer Requirements Feedback |  |  |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
273 |  |  |  | 1.5.3.2.2 | Verify Closure of Customer Requirements Feedback |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.3 |  |  |  |  | #REF! |  | 0 |  |  | #REF! | #REF! | 71 | 0 | #REF!
274 |  |  |  | 1.5.3.2.3 | Document and Communicate Customer Requirements Review Results |  |  |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  | 0 |  | #REF! | #REF! |  | 0 | #REF!
275 |  |  |  | 1.5.3.2.4 | Obtain Approval and Baseline Customer Requirements |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
276 |  | 1.5.4 | Customer Requirements Developed | [22 empty] | 0 | 0
277 |  | 1.5.5 | Develop Product Requirements (Features) | [7 empty] | 0.31 | 5.92 |  |  |  | 43.524 | [6 empty] | 7.254 | 7.3 | 71 | 0 | 10
278 |  |  | 1.4.6.1 | Elicit Requirements |  |  |  | Requirements Analyst |  |  |  | 0.14 |  |  |  |  | 6.0934 | [5 empty] | 1.0156 | 1.1 |  | 0 | 2
279 |  |  | 1.4.6.2 | Develop Use Cases |  |  |  | Requirements Analyst |  |  |  | 0.14 |  |  |  |  | 6.0934 | [5 empty] | 1.0156 | 1.1 | 89 | 0 | 2
280 |  |  | 1.4.6.3 | Derive Product Requirements |  |  |  | Project Manager[30%],Requirements Analyst |  |  |  | 0.25 |  |  |  |  | 10.881 | [5 empty] | 1.8135 | 1.9 | 90 | 0 | 2
281 |  |  | 1.4.6.4 | Prioritize Product Requirements |  |  |  | Process Engineer[30%],Requirements Analyst,Project Manager |  |  |  | 0.05 |  |  |  |  | 2.1762 | [5 empty] | 0.3627 | 0.4 | 91 | 0 | 0
Establish Product and Product Component Requirements
Derived product requirements
Prioritize requirements
Derive system requirements
Prioritize system requirements
Allocate product component requirements
Identify interface requirements
282 |  | 1.5.6 | Product Requirements Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
283 |  |  | 1.5.6.1 | Prepare for Product Requirements Peer Review |  |  | Prepare for Product Requirements Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
284 |  |  |  | 1.5.6.1.1 | Identify Product Requirements Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
285 |  |  |  | 1.5.6.1.2 | Check Draft Product Requirements |  | Check Draft Product Requirements | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
286 |  |  |  | 1.5.6.1.3 | Schedule Product Requirements Peer Review Meeting |  | Schedule Product Requirements Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
287 |  |  | 1.5.6.2 | Conduct Product Requirements Peer Review |  |  | Conduct Product Requirements Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
288 |  |  |  | 1.5.6.2.1 | Conduct Product Requirements Plan Review Meeting |  | Conduct Product Requirements Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
289 |  |  |  | 1.5.6.2.2 | Review and Log Product Requirements Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
290 |  |  | 1.5.6.3 | Analyze Product Requirements Peer Review |  |  | Analyze Product Requirements Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
291 |  |  |  | 1.5.6.3.1 | Resolve Product Requirements Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
292 |  |  |  | 1.5.6.3.2 | Product Requirements Peer Review Follow Up |  | Product Requirements Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
293 |  |  |  | 1.5.6.3.3 | Resolve Modifications from Product Requirements Peer Review |  | Resolve Modifications from Product Requirements Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
294 |  |  |  | 1.5.6.3.4 | Document and Communicate Product Requirements Review Results |  | Document and Communicate Product Requirements Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
295 |  | 1.5.7 | Review and Approve Product Requirements |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
296 |  |  | 1.5.7.1 | Perform Product Requirements Verification |  |  | Perform Product Requirements Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
297 |  |  |  | 1.5.7.1.1 | Identify Product Requirements Reviewers |  | Identify Product Requirements Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
298 |  |  |  | 1.5.7.1.2 | Schedule Review and Approve Product Requirements Review |  | Schedule Review and Approve Product Requirements Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
299 |  |  |  | 1.5.7.1.3 | Conduct Review and Approve Product Requirementsn Review Meeting |  | Conduct Review and Approve Product Requirementsn Review Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
300 |  |  |  | 1.5.7.1.4 | Review and Log Product Requirements Feedback |  | Review and Log Product Requirements Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
301 |  |  | 1.5.7.2 | Analyze Product Requirements Verification Results |  |  | Analyze Product Requirements Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
302 |  |  |  | 1.5.7.2.1 | Resolve Define Phase Cost Estimate Feedback |  | Resolve Define Phase Cost Estimate Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
303 |  |  |  | 1.5.7.2.2 | Verify Closure of Define Phase Cost Estimate Feedback |  | Verify Closure of Define Phase Cost Estimate Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
304 |  |  |  | 1.5.7.2.3 | Update Customer Requirements |  |  | Project Manager[50%],Requirements Analyst |  |  |  | 0.05 |  |  |  |  | 2.1762 | [5 empty] | 0.3627 | 0.4 |  | 0 | 0
305 |  |  |  | 1.5.7.2.4 | Document and Communicate Define Phase Cost Estimate Review Results |  | Document and Communicate Define Phase Cost Estimate Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
306 |  |  |  | 1.5.7.2.5 | Obtain Approval and Baseline Define Phase Cost Estimate |  | Obtain Approval and Baseline Define Phase Cost Estimate |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
307 |  | 1.5.8 | Formall Business Requirements Document Review |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  |  | 0.03 | #REF! |  |  |  | 4.212 | [5 empty] | 0.702 | 0.8 | 71 | 0 | 0
308 |  |  | 1.5.7.1 | Perform Business Requirements Document Verification |  |  | Perform Business Requirements Document Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
309 |  |  |  | 1.5.7.2 | Identify Business Requirements Document Reviewers |  | Identify Business Requirements Document Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
310 |  |  |  | 1.5.7.3 | Schedule Review and ApproveBusiness Requirements Document Review |  | Schedule Review and ApproveBusiness Requirements Document Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
311 |  |  |  | 1.5.7.4 | Conduct Review and ApproveBusiness Requirements Document Review Meeting |  | Conduct Review and ApproveBusiness Requirements Document Review Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
312 |  |  |  | 1.5.7.5 | Review and Log Business Requirements Document Feedback |  | Review and Log Business Requirements Document Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
313 |  |  | 1.5.7.2 | Analyze Business Requirements Document Verification Results |  |  | Analyze Business Requirements Document Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
314 |  |  |  | 1.3.2.2.1 | Resolve Business Requirements Document Feedback |  | Resolve Business Requirements Document Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
315 |  |  |  | 1.3.2.2.2 | Verify Closure of Business Requirements Document Feedback |  | Verify Closure of Business Requirements Document Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
316 |  |  |  | 1.3.2.2.3 | Document and Communicate Business Requirements Document Results |  | Document and Communicate Business Requirements Document Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
317 |  |  |  | 1.3.2.2.4 | Obtain Approval and Baseline Business Requirements Document |  | Obtain Approval and Baseline Business Requirements Document |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
318 |  |  | 1.4.6.7 | Check for Consistency in Requirements Work Product |  |  |  | Project Manager[50%],Requirements Analyst |  |  |  | 0.02 |  |  |  |  | 2.808 | [5 empty] | 0.468 | 0.5 |  | 0 | 0
319 |  |  | 1.4.6.8 | Update and Finalize System Requirements Specification (SRS) |  |  |  | Project Manager[50%],Requirements Analyst |  |  |  | 0.05 |  |  |  |  | 7.02 | [5 empty] | 1.17 | 1.2 |  | 0 | 2
320 |  |  | 1.4.6.9 | Update Requirements Traceability Matrix (RTM) |  |  |  | Requirements Analyst |  |  |  | 0.05 |  |  |  |  | 7.02 | [5 empty] | 1.17 | 1.2 |  | 0 | 2
321 |  |  | 1.4.6.10 | Ensure Review of BRD, SRS and RTM |  |  |  | QA Analyst,Process Engineer,Project Manager[50%],Requirements Analyst |  |  |  | 0.05 |  |  |  |  | 7.02 | [5 empty] | 1.17 | 1.2 |  | 0 | 2
322 |  |  | 1.4.6.11 | Peer Review | [7 empty] | 0.05 |  |  |  |  | 7.02 | [5 empty] | 1.17 | 1.2 |  | 0 | 2
323 |  |  |  | 1.4.6.11.1 | Conduct Offline Review | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
324 |  |  |  | 1.4.6.11.2 | Identify Reviewers | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
325 |  |  |  | 1.4.6.11.3 | Schedule Review | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
326 |  |  |  | 1.4.6.11.3 | Review and Log Feedback | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
327 |  |  |  | 1.4.6.11.3 | Fix Defects Detected from Offline Review | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
328 |  |  |  | 1.4.6.11.6 | Verify Closure of Defects | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
329 |  |  |  | 1.4.6.11.7 | Document and Communicate Review Results | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
330 |  |  |  | 1.4.6.11.8 | Approve for Baseline | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
331 |  |  | 1.4.6.12 | Follow up for Review Completion to obtain agreement on requirements by All Reqs Providers |  |  |  | Project Manager[50%],Requirements Analyst |  |  |  | 0.03 |  |  |  |  | 4.212 | [5 empty] | 0.702 | 0.8 |  | 0 | 0
332 |  |  | 1.4.6.13 | Obtain Approval and Baseline BRD, SRS and RTM |  |  |  | CM Lead[30%],Process Engineer,Project Manager,Requirements Analyst[30%] |  |  |  | 0.01 |  |  |  |  | 1.404 | [5 empty] | 0.234 | 0.3 |  | 0 | 0
333 |  | 1.4.9 | Develop Deployment Strategy | [7 empty] | 0.05 |  |  |  |  | 7.02 | [6 empty] | 1.17 | 1.2 | 51 | 18 | #REF!
334 |  |  | 1.4.9.1 | Document Deployment Strategy |  |  |  | System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
335 |  | 1.4.10 | Initial System Deployment Plan (ver 1.0) containing Deployment Strategy created | [19 empty] | #VALUE! | #VALUE! |  | 0 | 0
336 |  | 1.4.12 | Develop Final Project Plan | [7 empty] | 0.04 |  |  |  |  | 5.616 | [6 empty] | 0.936 | 1 | 51 | 18 | 2
337 |  |  | 1.4.12.1 | Tailor Project for Project Characteristics |  |  |  | Project Manager,QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | 2
338 |  |  | 1.4.12.2 | Develop and Record Estimates | [18 empty] | #VALUE! | #VALUE! |  | 0 | 2
339 |  |  |  | 1 | Identify Estimation Team
340 |  |  |  | 2 | Identify Estimation Method
341 |  |  |  | 3 | Estmate Size, Effort, Cost and Forecast Dates
342 |  |  |  | 4 | Ensure Review and Validation of Cost Estimates
343 |  |  |  | 5 | Prepare Estimation Report
344 |  |  | 1.4.12.3 | Develop Test Strategy |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
345 |  |  | 1.4.12.4 | Develop Peer Review Plan |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
346 |  |  | 1.4.12.5 | Update Product Quality Plan |  |  |  | QA Analyst[30%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
347 |  |  |  |  | Set Project Performance Objectives
348 |  |  |  |  | Derive Objectives for Life Cycle Phases
349 |  |  |  |  | Review of Process Performance Capabilites
350 |  |  |  |  | Review Product Quality Plan
351 |  |  | 1.4.12.6 | Identify Resources, Tools and Training Needs |  |  |  | Project Manager,Project Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
352 |  |  | 1.4.12.7 | Document CM Plan |  |  |  | Project Manager,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
353 |  |  | 1.4.12.8 | Document Project Data Management Plan |  |  |  | Project Manager,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
354 |  |  | 1.4.12.9 | Document QA Plan |  |  |  | Project Manager,QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
355 |  |  | 1.4.12.10 | Document Stakeholder(s) Involvement Plan |  |  |  | Project Manager,Project Team,Senior Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
356 |  |  | 1.4.12.11 | Document Project Training Plan |  |  |  | Project Manager,Project Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
357 |  |  | 1.4.12.12 | Identify Critical Dependencies and Issues |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
358 |  |  | 1.4.12.13 | Asess and Create Procurement Plan for acquiring Supplier/Products for System Deployment |  |  |  | Project Manager,Project Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
359 |  |  | 1.4.12.14 | Refine and Optimize Project Schedule |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
360 |  |  | 1.4.12.15 | Document Prelimnary Project Plan |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
361 |  |  | 1.4.12.16 | Check for Consistency in PQP, QA Plan, Risk Mgmt, CM Plan and Schedule |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
362 |  |  | 1.4.15 | Review Project Commitments |  |  |  | Project Manager,Senior Manager |  |  | 0.03 |  |  |  |  | 4.212 | [6 empty] | 0.702 | 0.8 | 51 | 18 | #REF!
363 |  | 1.5.7 | Review and Approve Final Project Plan |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
364 |  |  | 1.5.7.1 | Perform Final Project Plan Verification |  |  | Perform Final Project Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
365 |  |  |  | 1.5.7.2 | Identify Product Requirements Reviewers |  | Identify Product Requirements Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
366 |  |  |  | 1.5.7.3 | Schedule Review and Approve Product Requirements Review |  | Schedule Review and Approve Product Requirements Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
367 |  |  |  | 1.5.7.4 | Conduct Review and Approve Product Requirementsn Review Meeting |  | Conduct Review and Approve Product Requirementsn Review Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
368 |  |  |  | 1.5.7.5 | Review and Log Product Requirements Feedback |  | Review and Log Product Requirements Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
369 |  |  | 1.5.7.2 | Analyze Final Project Plan Verification Results |  |  | Analyze Final Project Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
370 |  |  |  | 1.3.2.2.1 | Resolve Final Project Plan Feedback |  | Resolve Final Project Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
371 |  |  |  | 1.3.2.2.2 | Verify Closure of Final Project Plan Feedback |  | Verify Closure of Final Project Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
372 |  |  |  |  | Update Final Project Plan |  |  | Project Manager[50%],Requirements Analyst |  |  |  | 0.05 |  |  |  |  | 2.1762 | [5 empty] | 0.3627 | 0.4 |  | 0 | 0
373 |  |  |  | 1.3.2.2.3 | Document and Communicate Final Project Plan Review Results |  | Document and Communicate Final Project Plan Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
374 |  |  |  | 1.3.2.2.4 | Obtain Approval and Baseline Final Project Plan |  | Obtain Approval and Baseline Final Project Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
375 |  | 1.4.18 | Orient Project Team on Project Plan |  |  |  |  | Project Manager |  |  | 0.015 |  |  |  |  | 2.106 | [6 empty] | 0.351 | 0.4 | 51 | 18 | #VALUE!
376 |  | 1.4.19 | Conduct Define Tollgate | [7 empty] | 0.03 | 1 |  |  |  | 4.212 | [6 empty] | 0.702 | 0.8 | 51 | 18 | #VALUE!
377 |  |  | 1.4.19.1 | Update Define Plan(s) for Construct, Test and Deploy Phases |  |  |  | Project Manager,CM Lead,QA Analyst |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 10 | 0 | #VALUE!
378 |  |  | 1.4.19.2 | Request Tollgate Review |  |  |  | Project Manager[30%] |  |  |  | 0.01 | [10 empty] | #VALUE! | #VALUE! | 10 | 0 | #VALUE!
379 |  |  | 1.4.19.3 | Update and Approve (when applicable) Business Case |  |  |  | Project Manager[30%] |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 10 | 0 | #VALUE!
380 |  |  | 1.4.19.4 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 10 | 0 | #VALUE!
381 |  |  | 1.4.19.5 | Conduct Define Phase Tollgate |  |  |  | PMO Prg. Mgr.[50%] |  |  |  | 0.14 | [10 empty] | #VALUE! | #VALUE! | 10 | 0 | #VALUE!
382 |  |  | 1.4.19.6 | Review Work Product Baseline |  |  |  | QA Analyst |  |  |  | 0.45 | [10 empty] | #VALUE! | #VALUE! | 56 | 23 | #VALUE!
383 |  |  | 1.4.19.7 | Conduct CM Audits |  |  |  | QA Analyst |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 57 | 24 | #VALUE!
384 |  |  | 1.4.19.8 | Prepare Define Tollgate Review Report |  |  |  | Project Manager[20%] |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 58 | 0 | #VALUE!
385 |  |  | 1.4.19.9 | Update and Communicate Define Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 59 | 0 | #VALUE!
386 |  |  | 1.4.19.10 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 60 | 0 | #VALUE!
387 |  |  | 1.5.19.11 | Close Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager |  |  |  | 0.05 | [10 empty] | #VALUE! | #VALUE! | 61 | 0 | #VALUE!
388 |  | 1.3.20 | Define Risk | [7 empty] | 0.1 | [11 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
389 |  |  | Define Tollgate Conducted
390 | 1.7 | Design | [7 empty] | 12%
391 |  | 1.4.7 | Develop Architectural Design |  |  |  |  | Project Architect |  |  | 0.1507 | 1 |  |  |  | 21.1583 | [6 empty] | 3.5264 | 3.6 | 51 | 18 | 23
392 |  |  | 1.4.7.1 | Design System Architecture |  |  |  | Project Architect |  |  |  | 0.2 |  |  |  |  | 4.2317 | [5 empty] | 0.70528 | 0.8 |  | 0 | #REF!
393 |  |  | 1.4.7.2 | Develop Logical Data Model (LDM) |  |  |  | Project Data Architect |  |  |  | 0.2 |  |  |  |  | 4.2317 | [5 empty] | 0.70528 | 0.8 |  | 0 | #REF!
394 |  |  | 1.4.7.3 | Present to Architectural Review Committee |  |  |  | Project Architect,Project Manager |  |  |  | 0.1 |  |  |  |  | 2.1158 | [5 empty] | 0.35264 | 0.4 |  | 0 | 51
395 |  |  | 1.4.7.4 | Update Architectural Design (AD) Document |  |  |  | Project Architect |  |  |  | 0.1 |  |  |  |  | 2.1158 | [5 empty] | 0.35264 | 0.4 |  | 0 | #REF!
396 |  |  | 1.4.7.5 | Create IT Standards Bill of Material (BoM) |  |  |  | Project Architect,Project Manager |  |  |  | 0.0837 |  |  |  |  | 1.7709 | [5 empty] | 0.29516 | 0.3 |  | 0 | 24
397 |  |  | 1.4.7.6 | Ensure Review of AD and BoM |  |  |  | Project Manager |  |  |  | 0.05 |  |  |  |  | 1.0579 | [5 empty] | 0.17632 | 0.2 |  | 0 | 0
398 |  |  | 1.4.7.7 | Peer Review | [7 empty] | 0.1183 |  |  |  |  | 2.503 | [5 empty] | 0.41717 | 0.5 |  | 0 | 3
399 |  |  | 1.4.7.8 | Obtain Approval and Baseline AD and BoM |  |  |  | Project Manager,PIO Achitect |  |  |  | 0.148 |  |  |  |  | 3.1314 | [5 empty] | 0.5219 | 0.6 |  | 0 | 0
400 |  | 1.5.2 | Architectural Design Peer Review | [8 empty] | 0.0769 | 1 |  |  |  | 2.1594 | [5 empty] | 0.35989 | 0.4 | 69 | 0 | 0
401 |  |  | 1.5.2.1 | Prepare for Architectural Design Peer Review |  |  |  | Project Manager |  |  |  |  | 0.35 | 1 |  |  |  | 0.75577 |  |  |  |  | 0.12596 | 0.2 |  | 0 | 0
402 |  |  |  | 1.5.2.1.1 | Identify Customer Requirements Peer Review Reviewers |  |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
403 |  |  |  | 1.5.2.1.2 | Check Customer Requirements |  |  | Project Manager | [5 empty] | 0.8 | [8 empty] | #REF! | #REF! | 69 | 0 | #REF!
404 |  |  |  | 1.5.2.1.3 | Schedule Customer Requirements Peer Review Meeting |  |  | Project Manager | [5 empty] | 0.1 | [8 empty] | #REF! | #REF! | 74 | 18 | #REF!
405 |  |  | 1.5.2.2 | Conduct Architectural Design Peer Review | [8 empty] | 0.2 | 1 | [8 empty] | #VALUE! | #VALUE!
406 |  |  |  | 1.5.2.2.1 | Conduct Customer Requirements Peer Review Meeting | [8 empty] | 0.8 | [8 empty] | #VALUE! | #VALUE!
407 |  |  |  | 1.5.2.2.2 | Review and Log Customer Requirements Feedback | [8 empty] | 0.2 | [8 empty] | #VALUE!
408 |  |  | 1.5.2.3 | Analyze Architectural Design Plan Peer Review | [8 empty] | 0.45 | 1 | [8 empty] | #VALUE! | #VALUE!
409 |  |  |  | 1.5.2.3.1 | Resolve Project Charter Plan Feedback | [8 empty] | 0.35 | [8 empty] | #VALUE! | #VALUE!
410 |  |  |  | 1.5.2.3.2 | Project Charter Plan Peer Review Follow Up | [8 empty] | 0.2 |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 4 | 0 | #REF!
411 |  |  |  | 1.5.2.3.3 | Resolve Modifications from Project Charter Peer Review |  |  |  | 1 |  |  |  |  | 0.35 |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
412 |  |  |  | 1.5.2.3.4 | Document and Communicate Project Charter Review Results | [8 empty] | 0.1 |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 9 | 4 | #REF!
413 |  | 1.5.5 | Create IT Standards Bill of Material
414 |  | 1.5.3 | Review and Approve Architectural Design and Bill of Material | [19 empty] | #VALUE! | #VALUE!
415 |  |  | 1.5.3.1 | Perform Architectural Design and Bill of Material Verification | [7 empty] | 0.4 | 1 |  |  |  | #REF! | [5 empty] | #REF! | #REF!
416 |  |  |  | 1.5.3.1.1 | Identify Customer Requirements Reviewers |  |  |  | 1 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
417 |  |  |  | 1.5.3.1.2 | Schedule Review and Approve Customer Requirements Review |  |  |  | 1 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
418 |  |  |  | 1.5.3.1.3 | Conduct Review and Approve Customer Requirements Meeting |  |  |  | 1 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
419 |  |  |  | 1.5.3.1.4 | Review and Log Customer Requirements Feedback |  |  |  | 1 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
420 |  |  | 1.5.3.2 | Analyze Architectural Design and Bill of Material Verification Results | [7 empty] | 0.6 | 1 |  |  |  | #REF! | [5 empty] | #REF! | #REF!
421 |  |  |  | 1.5.3.2.1 | Resolve Customer Requirements Feedback |  |  |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
422 |  |  |  | 1.5.3.2.2 | Verify Closure of Customer Requirements Feedback |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.3 |  |  |  |  | #REF! |  | 0 |  |  | #REF! | #REF! | 71 | 0 | #REF!
423 |  |  |  | 1.5.3.2.3 | Document and Communicate Customer Requirements Review Results |  |  |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  | 0 |  | #REF! | #REF! |  | 0 | #REF!
424 |  |  |  | 1.5.3.2.4 | Obtain Approval and Baseline Customer Requirements |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
425 |  | 1.5.4 | Architectural Design Developed | [22 empty] | 0 | 0
426 |  | 1.5.5 | Bill of Material Approved
427
428 | [22 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
429 |  | 1.4.7 | Develop Data Design
430
431 |  | 1.4.7 | Develop Security Design
432
433 | 1.8 | Construct | [7 empty] | 15% | 1.3094 |  |  |  | 234 |  |  |  | 23400 |  |  |  | 39 | 39 |  | 0 | 3
434 |  | 1.8.1 | Conduct Construct Phase Kick-Off |  |  |  |  | Supplier,Project Manager |  |  | 0.005 |  |  |  |  | 1.17 | [6 empty] | 0.195 | 0.2 |  | 0 | #REF!
435 |  | 1.8.2 | Construct Phase Kick-Off Conducted | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
436 |  | 1.8.3 | Develop Test Plans | [7 empty] | 0.25 | 20.94 |  |  |  | 58.5 | [6 empty] | 9.75 | 9.8 |  | 0 | #REF!
437 |  |  | 1.8.3.1 | Identify Pre-Production Environment Requirements | [7 empty] | 0.3 |  |  |  |  | 17.55 | [5 empty] | 2.925 | 3 |  | 0 | 0
438 |  |  | 1.8.3.2 | Identify Pre-Production Environment Requirements | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
439 |  |  | 1.8.3.3 | Identify Test Data Requirements for User Acceptance Testing | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
440 |  |  | 1.8.3.4 | Develop Schedule for User Acceptance Testing |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
441 |  |  | 1.8.3.5 | Document Defect and Problem Reporting Procedures |  |  |  | Project Manager,Supplier[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
442 |  |  | 1.8.3.6 | Document User Acceptance Test Plan | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
443 |  | 1.8.4 | Perform User Acceptance Test Plan Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
444 |  |  | 1.3.4.1 | Prepare for User Acceptance Test Plan Peer Review |  |  | Prepare for User Acceptance Test Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
445 |  |  |  | 1.3.4.1.1 | Identify User Acceptance Test Plan Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
446 |  |  |  | 1.3.4.1.2 | Check Draft User Acceptance Test Plan |  | Check Draft User Acceptance Test Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
447 |  |  |  | 1.3.4.1.3 | Schedule User Acceptance Test Plan Peer Review Meeting |  | Schedule User Acceptance Test Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
448 |  |  | 1.3.4.2 | Conduct User Acceptance Test Plan Peer Review |  |  | Conduct User Acceptance Test Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
449 |  |  |  | 1.3.4.2.1 | Conduct User Acceptance Test Plan Plan Review Meeting |  | Conduct User Acceptance Test Plan Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
450 |  |  |  | 1.3.4.2.2 | Review and Log User Acceptance Test Plan Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
451 |  |  | 1.3.4.3 | Analyze User Acceptance Test Plan Peer Review |  |  | Analyze User Acceptance Test Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
452 |  |  |  | 1.3.4.3.1 | Resolve User Acceptance Test Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
453 |  |  |  | 1.3.4.3.2 | User Acceptance Test Plan Peer Review Follow Up |  | User Acceptance Test Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
454 |  |  |  | 1.3.4.3.3 | Resolve Modifications from User Acceptance Test Plan Peer Review |  | Resolve Modifications from User Acceptance Test Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
455 |  |  |  | 1.3.4.3.4 | Document and Communicate User Acceptance Test Plan Review Results |  | Document and Communicate User Acceptance Test Plan Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
456 |  | 1.8.5 | Review and Approve User Acceptance Test Plan |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
457 |  |  | 1.3.2.1 | Perform User Acceptance Test Plan Verification |  |  | Perform User Acceptance Test Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
458 |  |  |  | 1.3.2.1.1 | Identify User Acceptance Test Plan Reviewers |  | Identify User Acceptance Test Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
459 |  |  |  | 1.3.2.1.2 | Schedule Review and Approve User Acceptance Test Plan Review |  | Schedule Review and Approve User Acceptance Test Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
460 |  |  |  | 1.3.2.1.3 | Conduct Review and Approve User Acceptance Test Plan Plan Meeting |  | Conduct Review and Approve User Acceptance Test Plan Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
461 |  |  |  | 1.3.2.1.4 | Review and Log User Acceptance Test Plan Feedback |  | Review and Log User Acceptance Test Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
462 |  |  | 1.3.2.2 | Analyze User Acceptance Test Plan Verification Results |  |  | Analyze User Acceptance Test Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
463 |  |  |  | 1.3.2.2.1 | Resolve User Acceptance Test Plan Feedback |  | Resolve User Acceptance Test Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
464 |  |  |  | 1.3.2.2.2 | Verify Closure of User Acceptance Test Plan Feedback |  | Verify Closure of User Acceptance Test Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
465 |  |  |  | 1.3.2.2.3 | Document and Communicate User Acceptance Test Plan Review Results |  | Document and Communicate User Acceptance Test Plan Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
466 |  |  |  | 1.3.2.2.4 | Obtain Approval and User Acceptance Test Plan |  | Obtain Approval and User Acceptance Test Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
467 |  | 1.8.6 | Develop User Acceptance Test Cases | [8 empty] | 0.31 |  |  |  |  | 18.135 | [5 empty] | 3.0225 | 3.1 |  | 0 | 0
468 |  |  | 1.4.4.3.1 | Document User Acceptance Test Cases | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
469 |  |  | 1.4.4.3.2 | Update User Acceptance Test Case References in RTM | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
470 |  | 1.8.7 | Perform User Acceptance Test Cases Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
471 |  |  | 1.8.7.1 | Prepare for User Acceptance Cases Plan Peer Review |  |  | Prepare for User Acceptance Cases Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
472 |  |  |  | 1.8.7.1.1 | Identify User Acceptance Test Cases Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
473 |  |  |  | 1.8.7.1.2 | Check Draft User Acceptance Test Cases |  | Check Draft User Acceptance Test Cases | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
474 |  |  |  | 1.8.7.1.3 | Schedule User Acceptance Test Cases Peer Review Meeting |  | Schedule User Acceptance Test Cases Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
475 |  |  | 1.8.7.2 | Conduct User Acceptance Test Cases Peer Review |  |  | Conduct User Acceptance Test Cases Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
476 |  |  |  | 1.8.7.2.1 | Conduct User Acceptance Test Cases Review Meeting |  | Conduct User Acceptance Test Cases Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
477 |  |  |  | 1.8.7.2.2 | Review and Log User Acceptance Test Cases Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
478 |  |  | 1.8.7.3 | Analyze User Acceptance Test Cases Peer Review |  |  | Analyze User Acceptance Test Cases Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
479 |  |  |  | 1.8.7.3.1 | Resolve User Acceptance Test Cases Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
480 |  |  |  | 1.8.7.3.2 | User Acceptance Test Cases Peer Review Follow Up |  | User Acceptance Test Cases Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
481 |  |  |  | 1.8.7.3.3 | Resolve Modifications from User Acceptance Test Cases Peer Review |  | Resolve Modifications from User Acceptance Test Cases Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
482 |  |  |  | 1.8.7.3.4 | Document and Communicate User Acceptance Test Cases Review Results |  | Document and Communicate User Acceptance Test Cases Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
483 |  | 1.8.8 | Review and Approve User Acceptance Test Cases |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
484 |  |  | 1.8.8.1 | Perform User Acceptance Test Cases Verification |  |  | Perform User Acceptance Test Cases Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
485 |  |  |  | 1.8.8.1.1 | Identify User Acceptance Test Cases Reviewers |  | Identify User Acceptance Test Cases Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
486 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve User Acceptance Test Cases Review |  | Schedule Review and Approve User Acceptance Test Cases Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
487 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve User Acceptance Test Cases Plan Meeting |  | Conduct Review and Approve User Acceptance Test Cases Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
488 |  |  |  | 1.8.8.1.4 | Review and Log User Acceptance Test Cases Feedback |  | Review and Log User Acceptance Test Cases Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
489 |  |  | 1.8.8.2 | Analyze User Acceptance Test Cases Verification Results |  |  | Analyze User Acceptance Test Cases Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
490 |  |  |  | 1.8.8.2.1 | Resolve User Acceptance Test Cases Feedback |  | Resolve User Acceptance Test Cases Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
491 |  |  |  | 1.8.8.2.2 | Verify Closure of User Acceptance Test Cases Feedback |  | Verify Closure of User Acceptance Test Cases Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
492 |  |  |  | 1.8.8.2.3 | Document and Communicate User Acceptance Test Cases Review Results |  | Document and Communicate User Acceptance Test Cases Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
493 |  |  |  | 1.8.8.2.4 | Obtain Approval and User Acceptance Test Cases |  | Obtain Approval and User Acceptance Test Cases |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
494 |  | 1.8.9 | Document Non-Functional Test Cases | [13 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
495 |  | 1.8.10 | Update Non-Functional Test Case References in Requirements Traceability Matrix | [13 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
496 |  | 1.8.7 | Perform Non-Functional Test Cases Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
497 |  |  | 1.8.7.1 | Prepare for Non-Functional Cases Plan Peer Review |  |  | Prepare for Non-Functional Cases Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
498 |  |  |  | 1.8.7.1.1 | Identify Non-Functional Test Cases Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
499 |  |  |  | 1.8.7.1.2 | Check Draft Non-Functional Test Cases |  | Check Draft Non-Functional Test Cases | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
500 |  |  |  | 1.8.7.1.3 | Schedule Non-Functional Test Cases Peer Review Meeting |  | Schedule Non-Functional Test Cases Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
501 |  |  | 1.8.7.2 | Conduct Non-Functional Test Cases Peer Review |  |  | Conduct Non-Functional Test Cases Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
502 |  |  |  | 1.8.7.2.1 | Conduct Non-Functional Test Cases Review Meeting |  | Conduct Non-Functional Test Cases Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
503 |  |  |  | 1.8.7.2.2 | Review and Log Non-Functional Test Cases Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
504 |  |  | 1.8.7.3 | Analyze Non-Functional Test Cases Peer Review |  |  | Analyze Non-Functional Test Cases Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
505 |  |  |  | 1.8.7.3.1 | Resolve Non-Functional Test Cases Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
506 |  |  |  | 1.8.7.3.2 | Non-Functional Test Cases Peer Review Follow Up |  | Non-Functional Test Cases Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
507 |  |  |  | 1.8.7.3.3 | Resolve Modifications from Non-Functional Test Cases Peer Review |  | Resolve Modifications from Non-Functional Test Cases Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
508 |  |  |  | 1.8.7.3.4 | Document and Communicate Non-Functional Test Cases Review Results |  | Document and Communicate Non-Functional Test Cases Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
509 |  | 1.8.8 | Review and Approve Non-Functional Test Cases |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
510 |  |  | 1.8.8.1 | Perform Non-Functional Test Cases Verification |  |  | Perform Non-Functional Test Cases Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
511 |  |  |  | 1.8.8.1.1 | Identify Non-Functional Test Cases Reviewers |  | Identify Non-Functional Test Cases Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
512 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve Non-Functional Test Cases Review |  | Schedule Review and Approve Non-Functional Test Cases Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
513 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve Non-Functional Test Cases Plan Meeting |  | Conduct Review and Approve Non-Functional Test Cases Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
514 |  |  |  | 1.8.8.1.4 | Review and Log Non-Functional Test Cases Feedback |  | Review and Log Non-Functional Test Cases Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
515 |  |  | 1.8.8.2 | Analyze Non-Functional Test Cases Verification Results |  |  | Analyze Non-Functional Test Cases Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
516 |  |  |  | 1.8.8.2.1 | Resolve Non-Functional Test Cases Feedback |  | Resolve Non-Functional Test Cases Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
517 |  |  |  | 1.8.8.2.2 | Verify Closure of Non-Functional Test Cases Feedback |  | Verify Closure of Non-Functional Test Cases Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
518 |  |  |  | 1.8.8.2.3 | Document and Communicate Non-Functional Test Cases Review Results |  | Document and Communicate Non-Functional Test Cases Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
519 |  |  |  | 1.8.8.2.4 | Obtain Approval and Non-Functional Test Cases |  | Obtain Approval and Non-Functional Test Cases |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
520 |  | 1.8.9 | Develop System Test Plan | [8 empty] | 0.3 |  |  |  |  | 17.55 | [5 empty] | 2.925 | 3 |  | 0 | #REF!
521 |  |  | 1.8.9.1 | Identify Test Environment Requirements | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
522 |  |  | 1.8.9.1 | Identify Test Data Requirements for System Testing | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
523 |  |  | 1.8.9.1 | Develop Schedule for System Testing | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
524 |  |  | 1.8.9.1 | Document System Test Plan | [12 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
525 |  | 1.8.10 | Perform System Test Plan Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
526 |  |  | 1.8.7.1 | Prepare for System Test Plan Peer Review |  |  | Prepare for System Test Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
527 |  |  |  | 1.8.7.1.1 | Identify System Test Plan Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
528 |  |  |  | 1.8.7.1.2 | Check Draft System Test Plan |  | Check Draft System Test Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
529 |  |  |  | 1.8.7.1.3 | Schedule System Test Plan Peer Review Meeting |  | Schedule System Test Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
530 |  |  | 1.8.7.2 | Conduct System Test Plan Peer Review |  |  | Conduct System Test Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
531 |  |  |  | 1.8.7.2.1 | Conduct System Test Plan Review Meeting |  | Conduct System Test Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
532 |  |  |  | 1.8.7.2.2 | Review and Log System Test Plan Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
533 |  |  | 1.8.7.3 | Analyze System Test Plan Peer Review |  |  | Analyze System Test Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
534 |  |  |  | 1.8.7.3.1 | Resolve System Test Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
535 |  |  |  | 1.8.7.3.2 | System Test Plan Peer Review Follow Up |  | System Test Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
536 |  |  |  | 1.8.7.3.3 | Resolve Modifications from System Test Plan Peer Review |  | Resolve Modifications from System Test Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
537 |  |  |  | 1.8.7.3.4 | Document and Communicate System Test Plan Review Results |  | Document and Communicate System Test Plan Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
538 |  | 1.8.11 | Review and Approve System Test Plan |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
539 |  |  | 1.8.8.1 | Perform System Test Plan Verification |  |  | Perform System Test Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
540 |  |  |  | 1.8.8.1.1 | Identify System Test Plan Reviewers |  | Identify System Test Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
541 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve System Test Plan Review |  | Schedule Review and Approve System Test Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
542 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve System Test Plan Plan Meeting |  | Conduct Review and Approve System Test Plan Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
543 |  |  |  | 1.8.8.1.4 | Review and Log System Test Plan Feedback |  | Review and Log System Test Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
544 |  |  | 1.8.8.2 | Analyze System Test Plan Verification Results |  |  | Analyze System Test Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
545 |  |  |  | 1.8.8.2.1 | Resolve System Test Plan Feedback |  | Resolve System Test Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
546 |  |  |  | 1.8.8.2.2 | Verify Closure of System Test Plan Feedback |  | Verify Closure of System Test Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
547 |  |  |  | 1.8.8.2.3 | Document and Communicate System Test Plan Review Results |  | Document and Communicate System Test Plan Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
548 |  |  |  | 1.8.8.2.4 | Obtain Approval and System Test Plan |  | Obtain Approval and System Test Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
549 |  | 1.8.12 | Identify and Document System Test Cases
550 |  | 1.8.10 | Perform System Test Cases Peer Review | [7 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
551 |  |  | 1.8.7.1 | Prepare for System Test Cases Peer Review |  |  | Prepare for System Test Cases Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
552 |  |  |  | 1.8.7.1.1 | Identify System Test Cases Peer Review Reviewers | [7 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
553 |  |  |  | 1.8.7.1.2 | Check Draft System Test Cases |  | Check Draft System Test Cases | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
554 |  |  |  | 1.8.7.1.3 | Schedule System Test Cases Peer Review Meeting |  | Schedule System Test Cases Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
555 |  |  | 1.8.7.2 | Conduct System Test Cases Peer Review |  |  | Conduct System Test Cases Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
556 |  |  |  | 1.8.7.2.1 | Conduct System Test Cases Review Meeting |  | Conduct System Test Cases Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
557 |  |  |  | 1.8.7.2.2 | Review and Log System Test Cases Peer Review Feedback | [7 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
558 |  |  | 1.8.7.3 | Analyze System Test Cases Peer Review |  |  | Analyze System Test Cases Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
559 |  |  |  | 1.8.7.3.1 | Resolve System Test Cases Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
560 |  |  |  | 1.8.7.3.2 | System Test Cases Peer Review Follow Up |  | System Test Cases Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
561 |  |  |  | 1.8.7.3.3 | Resolve Modifications from System Test Cases Peer Review |  | Resolve Modifications from System Test Cases Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
562 |  |  |  | 1.8.7.3.4 | Document and Communicate System Test Cases Review Results |  | Document and Communicate System Test Cases Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
563 |  | 1.8.11 | Review and Approve System Test Cases |  |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
564 |  |  | 1.8.8.1 | Perform System Test Cases Verification |  |  | Perform System Test Cases Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
565 |  |  |  | 1.8.8.1.1 | Identify System Test Cases Reviewers |  | Identify System Test Cases Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
566 |  |  |  | 1.8.8.1.2 | Schedule Review and Approve System Test Cases Review |  | Schedule Review and Approve System Test Cases Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
567 |  |  |  | 1.8.8.1.3 | Conduct Review and Approve System Test Cases Meeting |  | Conduct Review and Approve System Test Cases Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
568 |  |  |  | 1.8.8.1.4 | Review and Log System Test Cases Feedback |  | Review and Log System Test Cases Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
569 |  |  | 1.8.8.2 | Analyze System Test Cases Verification Results |  |  | Analyze System Test Cases Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
570 |  |  |  | 1.8.8.2.1 | Resolve System Test Cases Feedback |  | Resolve System Test Cases Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
571 |  |  |  | 1.8.8.2.2 | Verify Closure of System Test Cases Feedback |  | Verify Closure of System Test Cases Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
572 |  |  |  | 1.8.8.2.3 | Document and Communicate System Test Cases Review Results |  | Document and Communicate System Test Cases Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
573 |  |  |  | 1.8.8.2.4 | Obtain Approval and System Test Cases |  | Obtain Approval and System Test Cases |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
574 |  | 1.8.12 | Identify and Document System Test Cases |  |  |  |  | Supplier |  |  |  | 0.03 |  |  |  |  | 1.755 | [5 empty] | 0.2925 | 0.3 |  | 0 | #VALUE!
575 |  | 1.8.13 | Complete System Deployment Plan | [7 empty] | 0.08 | 5 |  |  |  | 18.72 | [6 empty] | 3.12 | 3.2 |  | 0 | #VALUE!
576 |  |  | 1.8.13.1 | Develop Training Plan for System Deployment | [7 empty] | 0.273 |  |  |  |  | 5.1106 | [5 empty] | 0.85176 | 0.9 |  | 0 | #VALUE!
577 |  |  | 1.8.13.2 | Develop Pilot Deployment Plan | [7 empty] | 0.273 |  |  |  |  | 5.1106 | [5 empty] | 0.85176 | 0.9 |  | 0 | #VALUE!
578 |  |  |  | 1.8.13.2.1 | Develop Pilot Security Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
579 |  |  |  | 1.8.13.2.2 | Develop Pilot Data Conversion and Load Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
580 |  |  |  | 1.8.13.2.3 | Develop Pilot Deployment Schedule | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
581 |  |  |  | 1.8.13.2.4 | Develop Pilot Test Plans | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
582 |  |  |  | 1.8.13.2.5 | Develop Pilot Operations, Maintenance and Support Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
583 |  |  |  | 1.8.13.2.6 | Develop Pilot Application Disaster Recovery Plan for the Site | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
584 |  |  |  | 1.8.13.2.7 | Document Pilot Deployment Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #VALUE!
585 |  |  | 1.8.13.3 | Perform Pilot Deployment Plan Peer Review | [6 empty] | 0.0549 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 69 | 0 | #REF!
586 |  |  |  | 1.8.13.3.1 | Prepare for Pilot Deployment Plan Peer Review |  | Prepare for Pilot Deployment Plan Peer Review |  |  |  |  | 0.35 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  |  | 0 | 0
587 |  |  |  |  | 1.8.13.1.1 | Identify Pilot Deployment Plan Peer Review Reviewers | [6 empty] | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
588 |  |  |  |  | 1.8.13.1.2 | Check Draft Pilot Deployment Plan | Check Draft Pilot Deployment Plan | Project Manager | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
589 |  |  |  |  | 1.8.13.1.3 | Schedule Pilot Deployment Plan Peer Review Meeting | Schedule Pilot Deployment Plan Peer Review Meeting |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF! |  | 0
590 |  |  |  | 1.8.13.3.2 | Conduct Pilot Deployment Plan Peer Review |  | Conduct Pilot Deployment Plan Peer Review |  |  |  |  | 0.2 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 4 | 0 | 0
591 |  |  |  |  | 1.8.13.3.2.1 | Conduct Pilot Deployment Plan Review Meeting | Conduct Pilot Deployment Plan Review Meeting |  | 1 |  |  |  | 0.8 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
592 |  |  |  |  | 1.8.13.3.2.2 | Review and Log Pilot Deployment Plan Peer Review Feedback | [6 empty] | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
593 |  |  | 1.8.14.3 | Analyze Pilot Deployment Plan Peer Review |  |  | Analyze Pilot Deployment Plan Peer Review |  |  |  |  | 0.45 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  |  | 9 | 4 | 4
594 |  |  |  | 1.8.14.3.1 | Resolve Pilot Deployment Plan Feedback | [7 empty] | 0.35 |  |  |  |  | #REF! |  |  |  |  | #REF! | #REF!
595 |  |  |  | 1.8.14.3.2 | Pilot Deployment Plan Peer Review Follow Up |  | Pilot Deployment Plan Peer Review Follow Up | Project Manager | 1 |  |  |  | 0.2 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
596 |  |  |  | 1.8.14.3.3 | Resolve Modifications from Pilot Deployment Plan Peer Review |  | Resolve Modifications from Pilot Deployment Plan Peer Review | Project Manager | 1 |  |  |  | 0.35 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 12 | 0 | #REF!
597 |  |  |  | 1.8.14.3.4 | Document and Communicate Pilot Deployment Plan Peer Review Results |  | Document and Communicate Pilot Deployment Plan Peer Review Results | Project Manager | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 13 | 0 | #REF!
598 |  |  | 1.8.13.4 | Review and Approve Pilot Deployment Plan |  |  |  | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer |  |  | 0.1 | 1 |  |  |  | #REF! |  |  |  | #REF! |  |  | #REF! | #REF! | 71 | 0 | #REF!
599 |  |  |  | 1.8.13.4.1 | Perform Pilot Deployment Plan Verification |  | Perform Pilot Deployment Plan Verification |  |  |  |  | 0.4 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! |  | 0 | #REF!
600 |  |  |  |  | 1.8.13.4.1 | Identify Pilot Deployment Plan Reviewers | Identify Pilot Deployment Plan Reviewers | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.12 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
601 |  |  |  |  | 1.8.13.4.2 | Schedule Review and Approve Pilot Deployment Plan Review | Schedule Review and Approve Pilot Deployment Plan Review | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.02 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 17 | 0 | #REF!
602 |  |  |  |  | 1.8.13.4.3 | Conduct Review and Approve Pilot Deployment Plan Meeting | Conduct Review and Approve Pilot Deployment Plan Meeting | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.38 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 18 | 0 | #REF!
603 |  |  |  |  | 1.8.13.4.4 | Review and Log Pilot Deployment Plan Feedback | Review and Log Pilot Deployment Plan Feedback | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer | 4 |  |  |  | 0.48 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 19 | 12 | #REF!
604 |  |  |  | 1.8.13.4.2 | Analyze Pilot Deployment Plan Verification Results |  | Analyze Pilot Deployment Plan Verification Results |  |  |  |  | 0.6 | 1 |  |  |  | #REF! |  |  |  | #REF! |  | #REF! | #REF! | 15 | 0 | #REF!
605 |  |  |  |  | 1.8.13.4.1 | Resolve Pilot Deployment Plan Feedback | Resolve Pilot Deployment Plan Feedback |  | 1 |  |  |  | 0.5 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! |  | 0 | #REF!
606 |  |  |  |  | 1.8.13.4.2 | Verify Closure of Pilot Deployment Plan Feedback | Verify Closure of Pilot Deployment Plan Feedback |  | 1 |  |  |  | 0.3 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 22 | 0 | #REF!
607 |  |  |  |  | 1.8.13.4.3 | Document and Communicate Pilot Deployment Plans Review Results | Document and Communicate Pilot Deployment Plans Review Results |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 23 | 0 | #REF!
608 |  |  |  |  | 1.8.13.4.4 | Obtain Approval and Pilot Deployment Plan | Obtain Approval and Pilot Deployment Plan |  | 1 |  |  |  | 0.1 |  |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | 24 | 17 | #REF!
609 |  |  | 1.8.13.5 | Develop Site Deployment Plan | [7 empty] | 0.18 |  |  |  |  | 3.3696 | [5 empty] | 0.5616 | 0.6 |  | 0 | #REF!
610 |  |  |  | 1.8.13.5.1 | DevelopSite Security Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
611 |  |  |  | 1.8.13.5.2 | Develop Site Data Conversion and Load Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 3
612 |  |  |  | 1.8.13.5.3 | Develop Site Deployment Schedule | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
613 |  |  |  | 1.8.13.5.4 | Develop Site Test Plans | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
614 |  |  |  | 1.8.13.5.5 | Develop Site Operations, Maintenance and Support Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
615 |  |  |  | 1.8.13.5.6 | Develop Site Application Disaster Recovery Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
616 |  |  |  | 1.8.13.5.7 | Document Site Deployment Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | 0
617
618 |  |  |  | 1.4.5.3.8 | Review Site Deployment Plan | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
619 |  |  |  | 1.4.5.3.9 | Obtain Approval and Baseline SDP | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
620
621 |  |  | 1.8.13.6 | Develop System Deployment Schedule | [7 empty] | 0.05 |  |  |  |  | 0.936 | [5 empty] | 0.156 | 0.2 |  | 0 | #REF!
622 |  |  | 1.8.13.7 | Document System Deployment Plan | [7 empty] | 0.05 |  |  |  |  | 0.936 | [5 empty] | 0.156 | 0.2 |  | 0 | #REF!
623 |  |  | 1.4.5.6 | Willow will will | [7 empty] | 0.02 |  |  |  |  | 0.3744 | [5 empty] | 0.0624 | 0.1 |  | 0 | #REF!
624
625 |  |  | 1.4.5.7 | Ensure Review System Deployment Plan | [7 empty] | 0.02 |  |  |  |  | 0.3744 | [5 empty] | 0.0624 | 0.1 |  | 0 | #REF!
626 |  |  |  | 1.4.5.7.1 | Identify Reviewers | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
627 |  |  |  | 1.4.5.7.2 | Schedule Review | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
628 |  |  |  | 1.4.5.7.3 | Review and Log Feedback | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
629 |  |  |  | 1.4.5.7.4 | Fix Defects Detected from Review | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
630 |  |  |  | 1.4.5.7.5 | Verify Closure of Defects | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
631 |  |  |  | 1.4.5.7.1 | Document and Communicate Review Results | [11 empty] | 0 | [5 empty] | 0 | 0 |  | 0 | #REF!
632 |  |  | 1.4.4.8 | Obtain Approval and Baseline DP | [7 empty] | 0.134 |  |  |  |  | 2.5085 | [5 empty] | 0.41808 | 0.5 |  | 0 | #REF!
633
634 |  | 1.8.14 | System Deployment Plan Completed | [19 empty] | #VALUE! | #VALUE! |  | 0 | 0
635 |  | 1.8.15 | Configure, Integrate and Deliver System |  |  |  |  | Supplier |  |  | 0.025 |  |  |  |  | 5.85 | [6 empty] | 0.975 | 1 |  | 0 | #REF!
636 |  |  | 1.8.15.1 | Integrate and Build the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
637 |  |  | 1.8.15.2 | Configure the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
638 |  |  | 1.8.15.3 | Conduct Integration Testing | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
639 |  |  | 1.8.15.4 | Update Requirements Traceability Matrix (RTM) | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
640 |  |  | 1.8.15.5 | Develop System Documentation and Training Material for the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
641 |  |  | 1.8.15.6 | Deliver the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
642 |  | 1.8.16 | Conduct System Testing Readiness Review | [7 empty] | 0.01 |  |  |  |  | 2.34 | [6 empty] | 0.39 | 0.4 |  | 0 | #REF!
643 |  |  | 1.8.16.1 | Set Up Test Environment | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
644 |  |  |  | 1.8.16.1.1 | Install Test Environment
645 |  |  |  | 1.8.16.1.2 | Apply Inftrastructure Changes
646 |  |  |  | 1.8.16.1.3 | Apply Security Changes
647 |  |  |  | 1.8.16.1.4 | Convent and Migrate Data
648 |  |  |  | 1.8.16.1.5 | Verity Test Environment
649 |  |  |  | 1.8.16.1.6 | Verify and Audit Test Environment
650 |  |  |  | 1.8.16.1.7 | Fix Gaps Related to Test Environment
651 |  |  | 1.8.16.2 | Test Build and Installation of the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
652 |  |  |  | 1.8.16.2.1 | Verify Installation and System Documentation
653 |  |  |  | 1.8.16.2.2 | Fix Defects and Issues
654 |  |  |  | 1.8.16.2.3 | Update Installation and System Documentation
655 |  |  |  | 1.8.16.2.1 | Build the System
656 |  |  |  | 1.8.16.2.1 | Install and Configure the System
657 |  |  |  | 1.8.16.2.1 | Obtain Approval and Check-in System Documentation, SC and Installation Guide
658 |  |  | 1.8.16.3 | Conduct system test readiness review meeting | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
659 |  |  | 1.8.16.4 | Conduct Release Audit | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
660 |  | 1.4.10 | Conduct Construct Tollgate | [7 empty] | 0.01 |  |  |  |  | 2.34 | [6 empty] | 0.39 | 0.4 |  | 0 | #REF!
661 |  |  | 1.4.10.1 | Update Plan(s) for Test and Deploy Phases |  |  |  | Project Manager,CM Lead,QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
662 |  |  | 1.4.10.2 | Request Tollgate Review |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
663 |  |  | 1.4.10.3 | Update Business Case |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
664 |  |  | 1.4.10.4 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
665 |  |  | 1.4.10.5 | Review Plan(s) for Test and Deploy Phases |  |  |  | PMO Prg. Mgr.[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
666 |  |  | 1.4.10.6 | Review Work Product Baseline and Conduct CM Audit |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
667 |  |  | 1.4.10.7 | Conduct CM Audits |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
668 |  |  | 1.4.10.8 | Prepare Construct Tollgate Review Report |  |  |  | Project Manager[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
669 |  |  | 1.4.10.9 | Update and Communicate Construct Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
670 |  |  | 1.4.10.10 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
671 |  |  | 1.4.10.11 | Close Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
|  | 1.4.11 | Construct Tollgate Conducted
672 | [22 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
673 | 1.5 | Build | [7 empty] | 30%
674 |  |  | Develop Source Code and Conduct Unit Testing
675 |  |  | Update Requirements Traceability Matrix (RTM)
676 |  |  | Develop Integration Test Cases
677 | 1.6 | Test | [7 empty] | 15% |  |  |  |  | 234 |  |  |  | 23400 |  |  |  | 39 | 39 |  | 0 | #VALUE!
678 |  | 1.5.1 | Conduct System Testing | [19 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
679 |  |  | 1.5.1.1 | Develop Test Scripts |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
680 |  |  | 1.5.1.2 | Validate Test Scripts |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
681 |  |  | 1.5.1.3 | Update Requirements Traceability Matrix |  |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
682 |  |  | 1.5.1.4 | Check-In Test Scripts and Requirements Traceability Matrix |  |  |  | Supplier Lead[60%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
683 |  |  | 1.5.1.5 | Set Up Test Environment | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
684 |  |  |  | 1.5.1.5.1 | Install Test Environment |  |  | Project Manager, Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
685 |  |  |  | 1.5.1.5.2 | Apply Infrastructure Changes |  |  | Project Manager,Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
686 |  |  |  | 1.5.1.5.3 | Apply Security Changes |  |  | Project Manager,Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
687 |  |  |  | 1.5.1.5.4 | Convert and Migrate Data |  |  | Project Manager,Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
688 |  |  |  | 1.5.1.5.5 | Verify Test Environment |  |  | Test Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 3
689 |  |  |  | 1.5.1.5.6 | Verify and Audit Test Environment |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
690 |  |  |  | 1.5.1.5.7 | Fix Gaps Related to Test Environment |  |  | Test Manager,Supplier,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
691 |  |  | 1.5.1.6 | Test Build and Installation of the System | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
692 |  |  |  | 1.5.1.6.1 | Build the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
693 |  |  |  | 1.5.1.6.2 | Install and Configure the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
694 |  |  |  | 1.5.1.6.3 | Verify Installation and System Documentation |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
695 |  |  |  | 1.5.1.6.4 | Fix Defects and Issues |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
696 |  |  |  | 1.5.1.6.5 | Update Installation and System Documentation |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
697 |  |  |  | 1.5.1.6.6 | Obtain Approval and Check-In SD, SC and Installation Guide |  |  | CM Lead[30%],Supplier,Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
698 |  |  | 1.5.1.7 | Execute System Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
699 |  |  |  | 1.5.1.7.1 | Prepare System Test Summary Report (STSR) for the Cycle | [20 empty] | 0
700 |  |  |  | 1.5.1.7.1 | Review System Test Summary Report (STSR) for the Cycle
701 |  |  |  | 1.5.1.7.1 | Plan Next Test Cycle
702 |  |  |  | 1.5.1.7.1 | Fix Defects and Issues
703 |  |  |  | 1.5.1.7.1 | Verify System Test Results
704 |  |  |  | 1.5.1.7.1 | Log Defects and Issues
705 |  |  |  | 1.5.1.7.1 | Generate Final System Test Summary Report (STSR)
706 |  |  |  | 1.5.1.7.1 | Check-In System Test Cases and System Test Summary Report (STSR)
707 |  | 1.5.2 | Prepare Pre-Production Environment at Site | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
708 |  |  | 1.5.2.1 | Prepare Site for System Changes | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
709 |  |  |  | 1.5.2.1.1 | Prepare Site for Infrastructure Changes |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
710 |  |  |  | 1.5.2.1.2 | Prepare Site for Security Changes |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
711 |  |  |  | 1.5.2.1.3 | Prepare Site for Application Data Migration |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
712 |  |  | 1.5.2.2 | Create System Migration Plan |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
713 |  |  | 1.5.2.3 | Conduct Test and Site Readiness Review |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
714 |  |  | 1.5.2.4 | Prepare Test Cases for the Sites |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
715 |  |  | 1.5.2.5 | Update System Documentation and Test Plans for the Site |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
716 |  |  | 1.5.2.6 | Update Site Deployment Plan |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
717 |  |  | 1.5.2.7 | Apply Infrastructure Changes |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
718 |  |  | 1.5.2.8 | Apply Security Changes |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
719 |  |  | 1.5.2.9 | Convert and Migrate Data |  |  |  | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
720 |  | 1.5.3 | Conduct Acceptance Testing Readiness Review | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
721 |  |  | 1.5.3.1 | Perform Checks to Verify Pre-Production Environment |  |  |  | Operations and Support Manager,System Deployment Manager,Test Manager,Project Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
722 |  |  | 1.5.3.2 | Fix Gaps Related to Pre-Production Environment |  |  |  | Operations and Support Manager,System Deployment Manager,Test Manager,Project Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
723 |  |  | 1.5.3.3 | Verify and Audit Pre-Production Environment |  |  |  | Test Manager,Project Manager,Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
724 |  |  | 1.5.3.4 | Review and Approve System Documentation |  |  |  | Operations and Support Manager,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
725 |  |  | 1.5.3.5 | Test Build and Installation for Acceptance Testing | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
726 |  |  |  | 1.5.3.5.1 | Build the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
727 |  |  |  | 1.5.3.5.2 | Install and Configure the System |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
728 |  |  |  | 1.5.3.5.3 | Verify Installation and System Documentation |  |  | Supplier,Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
729 |  |  |  | 1.5.3.5.4 | Fix Defects and Issues |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
730 |  |  |  | 1.5.3.5.5 | Update Installation and System Documentation |  |  | Supplier | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
731 |  |  |  | 1.5.3.5.6 | Obtain Approval and Check-In SD, SC and Installation Guide |  |  | Supplier,Project Manager,CM Lead[60%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
732 |  |  | 1.5.3.6 | Conduct Release Audit |  |  |  | Supplier,CM Lead[60%],QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
733 |  |  | 1.5.3.7 | Conduct Acceptance Testing Readiness Review Meeting |  |  |  | Test Manager,System Deployment Manager,Operations and Support Manager,QA Analyst,PMO Prg. Mgr,Project Manager,Senior Manager[40%],End-users | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
734 |  | 1.5.4 | Conduct Acceptance Testing | [19 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
735 |  |  | 1.5.4.1 | Execute User Acceptance Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
736 |  |  | 1.5.4.2 | Verify Acceptance Test Results | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
737 |  |  | 1.5.4.3 | Log Defects and Issues | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
738 |  |  | 1.5.4.4 | Prepare User Acceptance Test Summary Report (UATSR) for the Cycle | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
739 |  |  | 1.5.4.5 | Ensure Review of User Acceptance Test Summary Report | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
740 |  |  | 1.5.4.6 | Plan Next Test Cycle | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
741 |  |  | 1.5.4.7 | Generate Final User Acceptance Test Summary Report | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
742 |  |  | 1.5.4.8 | Sign-off on User Acceptance Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
743 |  |  | 1.5.4.9 | Approve Acceptance Test Results | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
744 |  |  | 1.5.410 | Communicate Final UATSR to Senior Management | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
745 |  |  | 1.5.4.11 | Provide Approval to Baseline Source, Binaries and System Documentation | [18 empty] | #VALUE! | #VALUE! |  | 0 | 3
746 |  |  | 1.5.4.12 | Sign-off on Non-Functional Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
747 |  |  | 1.5.4.13 | Execute Non-Functional Acceptance Tests | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
748 |  | 1.5.5 | Acceptance Testing Conducted | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
749 |  | 1.5.6 | Analyze Defects and Change Requests | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
750 |  | 1.5.7 | Verify Production Readiness | [19 empty] | #VALUE! | #VALUE! |  | 0 | 0
751 |  | 1.5.8 | Conduct Test Tollgate | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
752 |  |  | 1.5.8.1 | Update Plan(s) for Deploy Phase |  |  |  | Project Manager,CM Lead,QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
753 |  |  | 1.5.8.2 | Request Tollgate Review |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
754 |  |  | 1.5.8.3 | Update Business Case |  |  |  | Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
755 |  |  | 1.5.8.4 | Prepare for Project Tollgate Review |  |  |  | Stakeholder[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
756 |  |  | 1.5.8.5 | Review Plan(s) for Deploy Phase |  |  |  | PMO Prg. Mgr.[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
757 |  |  | 1.5.8.6 | Review Work Product Baseline and Conduct CM Audit |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
758 |  |  | 1.5.8.7 | Conduct CM Audits |  |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
759 |  |  | 1.5.8.8 | Prepare Test Tollgate Review Report |  |  |  | Project Manager[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
760 |  |  | 1.5.8.9 | Update and Communicate Test Tollgate Review Report |  |  |  | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
761 |  |  | 1.5.8.10 | Work on Action Plan |  |  |  | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
762 |  |  | 1.5.8.11 | Close Tollgate Observations |  |  |  | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
763 |  | 1.5.9 | Accept Product |  |  |  |  | System Deployment Manager[50%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
764 |  |  | 1.5.8.12.1 | Accept the Acquired Product | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
765 |  |  | 1.5.8.12.2 | Transition product to Operations | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
766 |  |  | 1.5.8.12.3 | Review Supplier Performance | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
767 |  |  | 1.5.8.12.4 | Execute Supplier payment process | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
768 |  | 1.5.9 | Test Tollgate Conducted | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
769 | 1.6 | Deploy | [7 empty] | 6% |  |  |  |  | 93.6 |  |  |  | 9360 |  |  |  | 15.6 | 15.6 |  | 0 | #REF!
770 |  | 1.6.1 | Deploy at Pilot Site | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
771 |  |  | 1.6.1.1 | Migrate to New System at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
772 |  |  |  | 1.6.1.1.1 | Execute Migration |  |  | Pilot Site Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
773 |  |  |  | 1.6.1.1.2 | Perform Checks to Verify Migration |  |  | Pilot Site Lead,Pilot Site Deployment Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
774 |  |  |  | 1.6.1.1.3 | Check Contingency Plan for Alternative(s) |  |  | Pilot Site Lead,Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
775 |  |  |  | 1.6.1.1.4 | Modify System Environment or Components |  |  | Pilot Site Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
776 |  |  |  | 1.6.1.1.5 | Execute Back out Plan |  |  | Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
777 |  |  |  | 1.6.1.1.6 | Communicate To Stakeholders |  |  | Pilot Site Deployment Manager,Senior Manager,Pilot Site Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
778 |  |  |  | 1.6.1.1.7 | Communicate Deployment Status |  |  | System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
779 |  |  | 1.6.1.2 | Migrated to New System at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
780 |  |  | 1.6.1.3 | Update Generic Site Deployment Materials & System Documentation |  |  |  | Pilot Site Deployment Manage,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
781 |  |  | 1.6.1.4 | Transition to Operations at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
782 |  |  |  | 1.6.1.4.1 | Support New System |  |  | Pilot Site Deployment Team Member,Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
783 |  |  |  | 1.6.1.4.2 | Transfer Ownership to System Owner |  |  | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
784 |  |  |  | 1.6.1.4.3 | Archive System Documentation, Training Material & Application/System Components |  |  | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
785 |  |  |  | 1.6.1.4.4 | Train Operations Team |  |  | Pilot Site Operations & Support Team,System Owner,Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
786 |  |  | 1.6.1.5 | De-Install Legacy System at Pilot Site |  |  |  | Pilot Site Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
787 |  |  | 1.6.1.6 | Legacy System De-Installed at Pilot Site | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
788 |  | 1.6.2 | Deploy at Site <1> | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
789 |  |  | 1.6.2.1 | Migrate to New System at at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
790 |  |  |  | 1.6.2.1 | Execute Migration |  |  | Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
791 |  |  |  | 1.6.2.2 | Perform Checks to Verify Migration |  |  | Site1 Deployment Manager[30%],Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
792 |  |  |  | 1.6.2.3 | Check Contingency Plan for Alternative(s) |  |  | Site1 Deployment Manager,Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
793 |  |  |  | 1.6.2.4 | Modify System Environment or Components |  |  | Site1 Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
794 |  |  |  | 1.6.2.5 | Execute Back out Plan |  |  | Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
795 |  |  |  | 1.6.2.6 | Communicate To Stakeholders |  |  | Site1 Manager,Senior Manager,Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
796 |  |  |  | 1.6.2.7 | Communicate Deployment Status |  |  | System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
797 |  |  | 1.6.2.2 | Migrated to New System at at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
798 |  |  | 1.6.2.3 | Update Generic Site Deployment Materials & System Documentation |  |  |  | Site1 Deployment Manage,System Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
799 |  |  | 1.6.2.4 | Transition to Operations at at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
800 |  |  |  | 1.6.2.4.1 | Support New System |  |  | Site1 Deployment Manager,Site1 Deployment Team Member | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
801 |  |  |  | 1.6.2.4.2 | Transfer Ownership to System Owner |  |  | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
802 |  |  |  | 1.6.2.4.3 | Archive System Documentation, Training Material & Application/System Components |  |  | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
803 |  |  |  | 1.6.2.4.4 | Train Operations Team |  |  | Site1 Deployment Manager,System Owner,Site1 Operations & Support Team | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
804 |  |  | 1.6.2.5 | De-Install Legacy System at at Site <1> |  |  |  | Site1 Deployment Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
805 |  |  | 1.6.2.6 | Legacy System De-Installed at Site <1> | [18 empty] | #VALUE! | #VALUE! |  | 0 | 3
806 | 1.7 | Close Project | [7 empty] | 1% | [12 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
807 |  | 1.7.1 | Conduct Post-Project Review | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
808 |  |  | 1.7.1.1 | Develop Post Project Review Breakout Session Topics & Agenda |  |  |  | Project Team,Project Manager,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
809 |  |  | 1.7.1.1 | Conduct Post Project Review Meeting |  |  |  | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
810 |  |  | 1.7.1.1 | Complete Post Project Review Report |  |  |  | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | 0
811 |  |  | 1.7.1.1 | Create Project Role Feedback Forms |  |  |  | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
812 |  | 1.7.2 | Archive Documents |  |  |  |  | Project Manager,Project Team,QA Analyst,CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
813 |  | 1.7.3 | Close Project formally and Communicate |  |  |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
814 |  | 1.7.4 | Project <PTS -ID> Closed | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
815 | 1.8 | Project Support Activities | [20 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
816 |  | 1.11.1 | Manage Requirements | [19 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
817 |  |  |  | n.n.n.n | Understand Change in Requirements |  |  | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
818 |  |  |  | n.n.n.n | Perform Detailed Impact Analysis |  |  | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
819 |  |  |  | n.n.n.n | Raise Requirements Change Request (RCR) Form |  |  | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
820 |  |  |  | n.n.n.n | Review through Requirements Change Control Board (RCCB) |  |  | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
821 |  |  |  | n.n.n.n | Re-Estimate & Re-Plan the Project |  |  | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
822 |  |  |  | n.n.n.n | Obtain Approval from Senior Manager for Change in Cost & Schedule |  |  | Senior Manager,Project Manager[30%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
823 |  |  |  | n.n.n.n | Update & Baseline Project Plan |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
824 |  |  |  | n.n.n.n | Communicate Changes in Project Plan |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
825 |  |  | n.n.n | Change Control | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
826 |  |  |  | n.n.n.n | Review Impact on CM Repository |  |  | CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
827 |  |  |  | n.n.n.n | Review Impact on Work Products |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
828 |  |  |  | n.n.n.n | Update Change Register |  |  | CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
829 |  |  |  | n.n.n.n | Review through Change Control Board (CCB) |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
830 |  |  |  | n.n.n.n | Update Change Register |  |  | CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
831 |  |  |  | n.n.n.n | Update Change Register with Closure Details |  |  | Project Manager,CM Lead,Project Team Member[40%] | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
832 |  |  | n.n.n | Project Monitoring and Control | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
833 |  |  |  | n.n.n.n | Monitor Supplier Status | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
834 |  |  |  | n.n.n.n | Update Project Log , Project Plan and Project Schedule | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
835 |  |  |  | n.n.n.n | Provide Measurement Results Based on Project Metrics |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
836 |  |  |  | n.n.n.n | Update Project Tracking System (PTS) | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
837 |  |  |  | n.n.n.n | Conduct Milestone Reviews | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
838 |  |  |  | n.n.n.n | Conduct Senior Management Review (SMR) |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
839 |  |  |  | n.n.n.n | Conduct Progress Review Meetings |  |  | Project Manager | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
840 |  |  |  | n.n.n.n | Monitor Project Plan and Schedule | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
841 |  |  |  | n.n.n.n | Monitor Project Risks | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
842 |  |  |  | n.n.n.n | Monitor Stakeholder Involvement Plan | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
843 |  |  |  | n.n.n.n | Monitor Data Management Plan | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
844 |  |  |  | Project Quality Assurance | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
845 |  |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) |  |  | QA Analyst | [14 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
846 |  |  |  |  | Track and Verify NC Closure | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
847 |  |  |  |  | Verify Closure of Review Defect found in Work Product Review(s) | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
848 |  |  |  |  | Review Supplier's Process | [17 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
849 |  |  |  | Configuration Management | [18 empty] | #VALUE! | #VALUE! |  | 0 | #REF!
850 |  |  |  |  | Update Change Register with Status of CR's |  |  | CM Lead | [14 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
851 |  |  |  |  | Create Baselines of the CIs | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
852 |  |  |  |  | Generate Configuration Status Accounting Report | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
853 |  |  |  |  | Verify Backup and Disaster Recovery | [17 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
854 | [22 empty] | #VALUE! | #VALUE! |  | 0 | #VALUE!
Formulas:
End date = (WORKDAY([Start date],Sheet2!C2*5))
End date = (WORKDAY([Start date],[Estimated Duration]))
Start date = IF(ISBLANK([Depend]),,WORKDAY(VLOOKUP([Depend],A2:AB876,26),0))

## AppDev
WBS | Line Number | [5 empty] | Task Name | Resource Names
1 | 1 | Project Schedule App Dev Template
| 2 | 1.1 | Entrance Criteria
| 3 |  | 1.1.1 | Approved Project Business Case
1.2 | 4 | 1.2 | Plan
1.2.1 | 5 |  | 1.2.1 |  |  |  | Develop Plan for Plan Phase | Project Manager
1.2.2 | 6 |  | 1.2.2 |  |  |  | Develop Process Design | Requirements Analyst[50%],Project Manager[50%],Process Engineer
1.2.3 | 7 |  | 1.2.3 |  |  |  | Develop Project Charter
1.2.3.1 | 8 |  |  | 1.2.3.1 |  |  | Define Project Scope
1.2.3.2 | 9 |  |  | 1.2.3.2 |  |  | Complete Project Charter (PC) Document
1.2.4 | 10 |  | 1.2.4 |  |  |  | Estimate Effort for Define Phase | Requirements Analyst,Project Manager
1.2.5 | 11 |  | 1.2.5 |  |  |  | Develop Plan for Define Phase
1.2.5.1 | 12 |  |  | 1.2.5.1 |  |  | Develop and Release RFI | WWP/Contract Manager,Project Manager
1.2.5.2 | 13 |  |  | 1.2.5.2 |  |  | Orient QA with Project Background | Project Manager,QA Analyst
1.2.5.3 | 14 |  |  | 1.2.5.3 |  |  | Document Preliminary Project Plan | Project Manager
1.2.5.3.1 | 15 |  |  |  | 1.2.5.3.1 |  | Identify Customer Deliverables | Project Manager,Project Team
1.2.5.3.2 | 16 |  |  |  | 1.2.5.3.2 |  | Identify Reusable Components | Project Manager[50%]
1.2.5.3.3 | 17 |  |  |  | 1.2.5.3.3 |  | Orient QA with Project Background | QA Analyst,Project Manager
1.2.5.3.4 | 18 |  |  |  | 1.2.5.3.4 |  | Tailor SDP-21 for Project Characteristics | Project Manager,QA Analyst
1.2.5.3.5 | 19 |  |  |  | 1.2.5.3.5 |  | Develop Peer Review Plan | Project Manager
1.2.5.3.6 | 20 |  |  |  | 1.2.5.3.6 |  | Identify Resources, Tools and Training Needs | Project Manager,Project Team
1.2.5.3.7 | 21 |  |  |  | 1.2.5.3.7 |  | Document CM Plan | Project Manager,CM Lead
1.2.5.3.8 | 22 |  |  |  | 1.2.5.3.8 |  | Document Project Data Management Plan | Project Manager,CM Lead
1.2.5.3.9 | 23 |  |  |  | 1.2.5.3.9 |  | Document QA Plan | Project Manager,QA Analyst
1.2.5.3.10 | 24 |  |  |  | 1.2.5.3.10 |  | Document Stakeholder(s) Involvement Plan | Project Manager,Project Team,Senior Manager
1.2.5.3.11 | 25 |  |  |  | 1.2.5.3.11 |  | Document Project Training Plan | Project Manager,Project Team
1.2.5.3.12 | 26 |  |  |  | 1.2.5.3.12 |  | Identify Critical Dependencies and Issues | Project Manager
1.2.5.3.13 | 27 |  |  |  | 1.2.5.3.13 |  | Asess and Create Procurement Plan for acquiring Supplier/Products for System Deployment | Project Manager,Project Team
1.2.5.3.14 | 28 |  |  |  | 1.2.5.3.14 |  | Refine and Optimize Project Schedule | Project Manager
1.2.5.3.15 | 29 |  |  |  | 1.2.5.3.15 |  | Document Prelimnary Project Plan | Project Manager
1.2.5.3.16 | 30 |  |  |  | 1.2.5.3.16 |  | Check for Consistency in PQP, QA Plan, Risk Mgmt, CM Plan and Schedule | Project Manager
1.2.5.3.17 | 31 |  |  |  | 1.2.5.3.17 |  | Ensure Review of Project Plan
1.2.5.3.17.1 | 32 |  |  |  |  | 1.2.5.3.17.1 | Identify Reviewers
1.2.5.3.17.2 | 33 |  |  |  |  | 1.2.5.3.17.2 | Schedule Review
1.2.5.3.17.3 | 34 |  |  |  |  | 1.2.5.3.17.3 | Review and Log Feedback
1.2.5.3.17.4 | 35 |  |  |  |  | 1.2.5.3.17.4 | Fix Defects Detected from Review
1.2.5.3.17.5 | 36 |  |  |  |  | 1.2.5.3.17.5 | Verify Closure of Defects
1.2.5.3.17.6 | 37 |  |  |  |  | 1.2.5.3.17.6 | Document and Communicate Review Results
1.2.5.3.18 | 38 |  |  |  | 1.2.5.3.18 |  | Update Project Plan | Project Manager
1.2.5.3.19 | 39 |  |  |  | 1.2.5.3.19 |  | Review Project Commitments | Project Manager,Senior Manager
1.2.5.3.20 | 40 |  |  |  | 1.2.5.3.20 |  | Obtain Approval and Baseline Project Plan | Project Manager[30%],CM Lead[30%]
1.2.5.3.21 | 41 |  |  |  | 1.2.5.3.21 |  | Communicate Project Plan | Project Manager
1.2.5.3.22 | 42 |  |  |  | 1.2.5.3.22 |  | Orient Project Team on Project Plan | Project Manager
1.2.5.4 | 43 |  |  | 1.2.5.4 |  |  | Procure Resources for Define Phase
1.2.5.4.1 | 44 |  |  |  | 1.2.5.4.1 |  | Engage Time and Material Resources | Project Manager,PMO Prg. Mgr.,WWP/Contract Manager
1.2.5.4.2 | 45 |  |  |  | 1.2.5.4.2 |  | Allocate Resources for Define Phase | Project Manager
1.2.5.4.3 | 46 |  |  |  | 1.2.5.4.3 |  | Develop Initial Version of Supplier Management Plan
1.2.5.4.4 | 47 |  |  |  | 1.2.5.4.4 |  | Develop RFP and Evaluation Criteria | Project Manager
1.2.5.4.5 | 48 |  |  |  | 1.2.5.4.5 |  | Distribute RFP to Suppliers | WWP/Contract Manager
1.2.5.4.6 | 49 |  |  |  | 1.2.5.4.6 |  | Evaluate Proposals | Project Manager
1.2.5.4.7 | 50 |  |  |  | 1.2.5.4.7 |  | Approve Supplier(s) Down-Select | Senior Manager,Project Manager
1.2.5.4.8 | 51 |  |  |  | 1.2.5.4.8 |  | Negotiate Agreement and Select Final Supplier
1.2.5.4.9 | 52 |  |  |  | 1.2.5.4.9 |  | Get Single Sourcing Justification Letter and Obtain Approval | CM Lead[30%],Senior Manager[30%],Project Manager[30%]
1.2.6 | 53 |  | 1.2.6 |  |  |  | Conduct Plan Tollgate
1.2.6.1 | 54 |  |  | 1.2.6.1 |  |  | Update Plan(s) for Define, Construct, Test and Deploy Phases | Project Manager,CM Lead,QA Analyst
1.2.6.2 | 55 |  |  | 1.2.6.2 |  |  | Request Tollgate Review | Project Manager[30%]
1.2.6.3 | 56 |  |  | 1.2.6.3 |  |  | Update Business Case | Project Manager[30%]
1.2.6.4 | 57 |  |  | 1.2.6.4 |  |  | Prepare for Project Tollgate Review | Stakeholder[30%]
1.2.6.5 | 58 |  |  | 1.2.6.5 |  |  | Review Plan(s) for Define, Construct, Test and Deploy Phases | PMO Prg. Mgr.[50%]
1.2.6.6 | 59 |  |  | 1.2.6.6 |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.2.6.7 | 60 |  |  | 1.2.6.7 |  |  | Conduct CM Audits | QA Analyst
1.2.6.8 | 61 |  |  | 1.2.6.8 |  |  | Prepare Tollgate Review Report | Project Manager[20%]
1.2.6.9 | 62 |  |  | 1.2.6.9 |  |  | Update and Communicate Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.2.6.10 | 63 |  |  | 1.2.6.10 |  |  | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.2.6.11 | 64 |  |  | 1.2.6.11 |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.3 | 65 | 1.3 |  |  |  |  | Plan Tollgate Conducted
1.4 | 66 | 1.4 |  |  |  |  | Define
1.4.1 | 67 |  | 1.4.1 |  |  |  | Communicate Final Supplier Management Plan
1.4.2 | 68 |  | 1.4.2 |  |  |  | Develop Business Requirements
1.4.2.1 | 69 |  | 1.4.2.1 |  |  |  | Derive Business Requirements | Senior Manager[30%],Project Manager[50%],Requirements Analyst[50%]
1.4.2.2 | 70 |  | 1.4.2.2 |  |  |  | Complete Business Requirements Document (BRD) | Project Manager[20%],Requirements Analyst
1.4.2.3 | 71 |  | 1.4.2.3 |  |  |  | Check for Consistency with Process Design Summary | Project Manager[20%],Requirements Analyst[30%],Process Engineer
1.4.2.4 | 72 |  | 1.4.2.4 |  |  |  | Ensure Review of BRD | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer
1.4.2.5 | 73 |  | 1.4.2.5 |  |  |  | Peer Review
1.4.2.6 | 74 |  | 1.4.2.6 |  |  |  | Obtain Approval and Baseline BRD | CM Lead[30%],Process Engineer,Project Manager[30%]
1.4.3 | 75 |  | 1.4.3 |  |  |  | Business Requirements Developed
1.4.4 | 76 |  | 1.4.4 |  |  |  | Develop System Requirements
1.4.4.1 | 77 |  | 1.4.4.1 |  |  |  | Elicit Requirements | Requirements Analyst
1.4.4.2 | 78 |  | 1.4.4.2 |  |  |  | Develop Use Cases | Requirements Analyst
1.4.4.3 | 79 |  | 1.4.4.3 |  |  |  | Derive System Requirements | Project Manager[30%],Requirements Analyst
1.4.4.4 | 80 |  | 1.4.4.4 |  |  |  | Prioritize System Requirements | Process Engineer[30%],Requirements Analyst,Project Manager
1.4.4.5 | 81 |  | 1.4.4.5 |  |  |  | Obtain Agreement for Requirements | Process Engineer,Project Manager,Requirements Analyst[30%]
1.4.4.6 | 82 |  | 1.4.4.6 |  |  |  | Update Business Requirements Document (BRD) | Project Manager[50%],Requirements Analyst
1.4.4.7 | 83 |  | 1.4.4.7 |  |  |  | Manage Requirements
1.4.4.7.1 | 84 |  | 1.4.4.7.1 |  |  |  | Understand Change in Requirements | Project Manager[50%],Requirements Analyst
1.4.4.7.2 | 85 |  | 1.4.4.7.2 |  |  |  | Perform Detailed Impact Analysis | Project Manager[50%],Requirements Analyst
1.4.4.7.3 | 86 |  | 1.4.4.7.3 |  |  |  | Complete Requirements Change Request (RCR) Form | Project Manager[50%],Requirements Analyst
1.4.4.7.4 | 87 |  | 1.4.4.7.4 |  |  |  | Review through Requirements Change Control Board | Project Manager[50%],Requirements Analyst
1.4.4.7.5 | 88 |  | 1.4.4.7.5 |  |  |  | Re-plan the Project
1.4.4.7.5.1 | 89 |  | 1.4.4.7.5.1 |  |  |  | Re-estimate and Re-plan | Project Manager[50%],Requirements Analyst
1.4.4.7.5.2 | 90 |  | 1.4.4.7.5.2 |  |  |  | Derive New Schedule | Project Manager[50%],Requirements Analyst
1.4.4.7.5.3 | 91 |  | 1.4.4.7.5.3 |  |  |  | Communicate Changes in Project Plan | Project Manager[50%],Requirements Analyst
1.4.4.7.6 | 92 |  | 1.4.4.7.6 |  |  |  | Update RCR Form | Project Manager[50%],Requirements Analyst
1.4.4.7.7 | 93 |  | 1.4.4.7.7 |  |  |  | Update Change Register | Project Manager[50%],Requirements Analyst
1.4.4.7.8 | 94 |  | 1.4.4.7.8 |  |  |  | Communicate to Requirements Providers | Project Manager[50%],Requirements Analyst
1.4.4.7.9 | 95 |  | 1.4.4.7.9 |  |  |  | Incorporate Changes
1.4.4.7.9.1 | 96 |  | 1.4.4.7.9.1 |  |  |  | Identify Author | Project Manager[50%],Requirements Analyst
1.4.4.7.9.2 | 97 |  | 1.4.4.7.9.2 |  |  |  | Check-Out Configuration Items (CIs) | Project Manager[50%],Requirements Analyst
1.4.4.7.9.3 | 98 |  | 1.4.4.7.9.3 |  |  |  | Incorporate Changes in Work Products | Project Manager[50%],Requirements Analyst
1.4.4.8 | 99 |  | 1.4.4.8 |  |  |  | Check for Consistency in Requirements Work Product | Project Manager[50%],Requirements Analyst
1.4.4.9 | 100 |  | 1.4.4.9 |  |  |  | Update and Finalize System Requirements Specification (SRS) | Project Manager[50%],Requirements Analyst
1.4.4.10 | 101 |  | 1.4.4.10 |  |  |  | Update Requirements Traceability Matrix (RTM) | Requirements Analyst
1.4.4.11 | 102 |  | 1.4.4.11 |  |  |  | Ensure Review of BRD, SRS and RTM | QA Analyst,Process Engineer,Project Manager[50%],Requirements Analyst
1.4.4.12 | 103 |  | 1.4.4.12 |  |  |  | Peer Review
1.4.4.12.1 | 104 |  | 1.4.4.12.1 |  |  |  | Conduct Offline Review
1.4.4.12.2 | 105 |  | 1.4.4.12.2 |  |  |  | Identify Reviewers
1.4.4.12.3 | 106 |  | 1.4.4.12.3 |  |  |  | Schedule Review
1.4.4.12.4 | 107 |  | 1.4.4.12.4 |  |  |  | Review and Log Feedback
1.4.4.12.5 | 108 |  | 1.4.4.12.5 |  |  |  | Fix Defects Detected from Offline Review
1.4.4.12.6 | 109 |  | 1.4.4.12.6 |  |  |  | Verify Closure of Defects
1.4.4.12.7 | 110 |  | 1.4.4.12.7 |  |  |  | Document and Communicate Review Results
1.4.4.12.8 | 111 |  | 1.4.4.12.8 |  |  |  | Approve for Baseline
1.4.4.13 | 112 |  | 1.4.4.13 |  |  |  | Follow up for Review Completion to obtain agreement on requirements by All Reqs Providers | Project Manager[50%],Requirements Analyst
1.4.4.14 | 113 |  | 1.4.4.14 |  |  |  | Obtain Approval and Baseline BRD, SRS and RTM | CM Lead[30%],Process Engineer,Project Manager,Requirements Analyst[30%]
1.4.5 | 114 |  | 1.4.5 |  |  |  | Develop Architectural Design | Project Architect
1.4.5.1 | 115 |  | 1.4.5.1 |  |  |  | Design System Architecture | Project Architect
1.4.5.2 | 116 |  | 1.4.5.2 |  |  |  | Develop Logical Data Model (LDM) | Project Data Architect
1.4.5.3 | 117 |  | 1.4.5.3 |  |  |  | Present to Architectural Review Committee | Project Architect,Project Manager
1.4.5.4 | 118 |  | 1.4.5.4 |  |  |  | Update Architectural Design (AD) Document | Project Architect
1.4.5.5 | 119 |  | 1.4.5.5 |  |  |  | Create IT Standards Bill of Material (BoM) | Project Architect,Project Manager
1.4.5.6 | 120 |  | 1.4.5.6 |  |  |  | Ensure Review of AD and BoM | Project Manager
1.4.5.7 | 121 |  | 1.4.5.7 |  |  |  | Peer Review
1.4.5.7.1 | 122 |  | 1.4.5.7.1 |  |  |  | Conduct Review | Project Manager
1.4.5.7.2 | 123 |  | 1.4.5.7.2 |  |  |  | Identify Reviewers | Project Manager
1.4.5.7.3 | 124 |  | 1.4.5.7.3 |  |  |  | Schedule Review | Project Manager
1.4.5.7.4 | 125 |  | 1.4.5.7.4 |  |  |  | Review and Log Feedback | Project Manager
1.4.5.7.5 | 126 |  | 1.4.5.7.5 |  |  |  | Fix Defects Detected from Offline Review | Project Manager
1.4.5.7.6 | 127 |  | 1.4.5.7.6 |  |  |  | Verify Closure of Defects | Project Manager
1.4.5.7.7 | 128 |  | 1.4.5.7.7 |  |  |  | Document and Communicate Review Results | Project Manager
1.4.5.7.8 | 129 |  | 1.4.5.7.8 |  |  |  | Approve for Baseline | Project Manager
1.4.5.8 | 130 |  | 1.4.5.8 |  |  |  | Obtain Approval and Baseline AD and BoM | Project Manager,PIO Architect
1.4.6 | 131 |  | 1.4.6 |  |  |  | Architectural Design Developed
1.4.7 | 132 |  | 1.4.7 |  |  |  | Make Build/Buy/Reuse Decision | Project Architect,Project Manager
1.4.7.1 | 133 |  | 1.4.7.1 |  |  |  | Verify Reuse Options | Project Architect,Project Manager
1.4.7.2 | 134 |  | 1.4.7.2 |  |  |  | Conduct Market Analysis | Project Architect,Project Manager
1.4.7.3 | 135 |  | 1.4.7.3 |  |  |  | Compare Multiple Products | Project Architect,Project Manager
1.4.7.4 | 136 |  | 1.4.7.4 |  |  |  | Selected? | Project Architect,Project Manager
1.4.7.5 | 137 |  | 1.4.7.5 |  |  |  | Communicate Build/Buy/Reuse Recommendation | CM Lead[30%],Project Architect,Project Manager
1.4.7.6 | 138 |  | 1.4.7.6 |  |  |  | Make Build/Buy/Reuse Analysis | Project Architect,Project Manager
1.4.8 | 139 |  | 1.4.8 |  |  |  | Develop Deployment Strategy
1.4.8.1 | 140 |  | 1.4.8.1 |  |  |  | Document Deployment Strategy | System Deployment Manager
1.4.9 | 141 |  | 1.4.9 |  |  |  | Initial System Deployment Plan (ver 1.0) containing Deployment Strategy created
1.4.10 | 142 |  | 1.4.10 |  |  |  | Conduct Bid Evaluations
1.4.10.1 | 143 |  | 1.4.10.1 |  |  |  | Plan for Product Acquisition | Project Manager,Requirements Analyst
1.4.10.2 | 144 |  | 1.4.10.2 |  |  |  | Plan for Supplier Sourcing (Construct through Deploy) | Project Manager,Senior Manager
1.4.10.3 | 145 |  | 1.4.10.3 |  |  |  | Develop Initial Version of Supplier Management Plan
1.4.10.4 | 146 |  | 1.4.10.4 |  |  |  | Develop RFP and Evaluation Criteria | Project Manager
1.4.10.5 | 147 |  | 1.4.10.5 |  |  |  | Distribute RFP to Suppliers | WWP/Contract Manager
1.4.10.6 | 148 |  | 1.4.10.6 |  |  |  | Evaluate Proposals | Project Manager
1.4.10.7 | 149 |  | 1.4.10.7 |  |  |  | Approve Supplier(s) Down-Select | Senior Manager,Project Manager
1.4.10.8 | 150 |  | 1.4.10.8 |  |  |  | Negotiate Agreement and Select Final Supplier
1.4.10.9 | 151 |  | 1.4.10.9 |  |  |  | Get Single Sourcing Justification Letter and Obtain Approval | CM Lead[30%],Senior Manager[30%],Project Manager[30%]
1.4.11 | 152 |  | 1.4.11 |  |  |  | Develop Final Project Plan
1.4.11.1 | 153 |  | 1.4.11.1 |  |  |  | Tailor SDP-21 for Project Characteristics | Project Manager,QA Analyst
1.4.11.2 | 154 |  | 1.4.11.2 |  |  |  | Develop and Record Estimates
1.4.11.2.1 | 155 |  | 1.4.11.2.1 |  |  |  | Identify Estimation Team | PMO Prg. Mgr.[20%],Project Manager
1.4.11.2.2 | 156 |  | 1.4.11.2.2 |  |  |  | Identify Estimation Method | QA Analyst[10%],PMO Prg. Mgr.[10%],Project Manager
1.4.11.2.3 | 157 |  | 1.4.11.2.3 |  |  |  | Estimate Size, Effort, Cost and Forecast Dates
1.4.11.2.4 | 158 |  | 1.4.11.2.4 |  |  |  | Ensure Review and Validation of Cost Estimates | Senior Manager[30%],Project Manager,PMO Prg. Mgr.[50%]
1.4.11.2.5 | 159 |  | 1.4.11.2.5 |  |  |  | Prepare Estimation Report | Project Manager
1.4.11.3 | 160 |  | 1.4.11.3 |  |  |  | Develop Test Strategy | Project Manager
1.4.11.4 | 161 |  | 1.4.11.4 |  |  |  | Develop Peer Review Plan | Project Manager
1.4.11.5 | 162 |  | 1.4.11.5 |  |  |  | Update Product Quality Plan (Level 4) | QA Analyst[30%],Project Manager
1.4.11.5.1 | 163 |  | 1.4.11.5.1 |  |  |  | Set Project Performance Objectives (Level 4) | Project Manager
1.4.11.5.2 | 164 |  | 1.4.11.5.2 |  |  |  | Derive Objectives for Life Cycle Phases (Level 4) | Project Manager
1.4.11.5.3 | 165 |  | 1.4.11.5.3 |  |  |  | Review of Process Performance Capabilities | QA Analyst[30%],Project Manager[50%],IO SEPG Manager
1.4.11.5.4 | 166 |  | 1.4.11.5.4 |  |  |  | Review Product Quality Plan (Level 4) | Project Manager[50%],QA Analyst[30%],IO SEPG Manager
1.4.11.5.5 | 167 |  | 1.4.11.5.5 |  |  |  | Obtain Approval and Baseline PQP (Level 4) | QA Analyst[30%],Project Manager[50%],IO SEPG Manager
1.4.11.6 | 168 |  | 1.4.11.6 |  |  |  | Identify Resources, Tools and Training Needs | Project Manager,Project Team
1.4.11.7 | 169 |  | 1.4.11.7 |  |  |  | Document CM Plan | Project Manager,CM Lead
1.4.11.8 | 170 |  | 1.4.11.8 |  |  |  | Document Project Data Management Plan | Project Manager,CM Lead
1.4.11.9 | 171 |  | 1.4.11.9 |  |  |  | Document QA Plan | Project Manager,QA Analyst
1.4.11.10 | 172 |  | 1.4.11.10 |  |  |  | Document Stakeholder(s) Involvement Plan | Project Manager,Project Team,Senior Manager
1.4.11.11 | 173 |  | 1.4.11.11 |  |  |  | Document Project Training Plan | Project Manager,Project Team
1.4.11.12 | 174 |  | 1.4.11.12 |  |  |  | Identify Critical Dependencies and Issues | Project Manager
1.4.11.13 | 175 |  | 1.4.11.13 |  |  |  | Asess and Create Procurement Plan for acquiring Supplier/Products for System Deployment | Project Manager,Project Team
1.4.11.14 | 176 |  | 1.4.11.14 |  |  |  | Refine and Optimize Project Schedule | Project Manager
1.4.11.15 | 177 |  | 1.4.11.15 |  |  |  | Document Prelimnary Project Plan | Project Manager
1.4.11.16 | 178 |  | 1.4.11.16 |  |  |  | Check for Consistency in PQP, QA Plan, Risk Mgmt, CM Plan and Schedule | Project Manager
1.4.12 | 179 |  | 1.4.12 |  |  |  | Ensure Review of Project Plan
1.4.12.1 | 180 |  | 1.4.12.1 |  |  |  | Identify Reviewers
1.4.12.2 | 181 |  | 1.4.12.2 |  |  |  | Schedule Review
1.4.12.3 | 182 |  | 1.4.12.3 |  |  |  | Review and Log Feedback
1.4.12.4 | 183 |  | 1.4.12.4 |  |  |  | Fix Defects Detected from Review
1.4.12.5 | 184 |  | 1.4.12.5 |  |  |  | Verify Closure of Defects
1.4.12.6 | 185 |  | 1.4.12.6 |  |  |  | Document and Communicate Review Results
1.4.13 | 186 |  | 1.4.13 |  |  |  | Update Project Plan | Project Manager
1.4.14 | 187 |  | 1.4.14 |  |  |  | Review Project Commitments | Project Manager,Senior Manager
1.4.15 | 188 |  | 1.4.15 |  |  |  | Obtain Approval and Baseline Project Plan | Project Manager[30%],CM Lead[30%]
1.4.16 | 189 |  | 1.4.16 |  |  |  | Communicate Project Plan | Project Manager
1.4.17 | 190 |  | 1.4.17 |  |  |  | Orient Project Team on Project Plan | Project Manager
1.4.18 | 191 |  | 1.4.18 |  |  |  | Conduct Define Tollgate
1.4.18.1 | 192 |  | 1.4.18.1 |  |  |  | Update Plan(s) for Construct, Test and Deploy Phases | Project Manager,CM Lead,QA Analyst
1.4.18.2 | 193 |  | 1.4.18.2 |  |  |  | Request Tollgate Review | Project Manager[30%]
1.4.18.3 | 194 |  | 1.4.18.3 |  |  |  | Update Business Case | Project Manager[30%]
1.4.18.4 | 195 |  | 1.4.18.4 |  |  |  | Prepare for Project Tollgate Review | Stakeholder[30%]
1.4.18.5 | 196 |  | 1.4.18.5 |  |  |  | Review Plan(s) for Construct, Test and Deploy Phases | PMO Prg. Mgr.[50%]
1.4.18.6 | 197 |  | 1.4.18.6 |  |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.4.18.7 | 198 |  | 1.4.18.7 |  |  |  | Conduct CM Audits | QA Analyst
1.4.18.8 | 199 |  | 1.4.18.8 |  |  |  | Prepare Define Tollgate Review Report | Project Manager[20%]
1.4.18.9 | 200 |  | 1.4.18.9 |  |  |  | Update and Communicate Define Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.4.18.10 | 201 |  | 1.4.18.10 |  |  |  | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.4.18.11 | 202 |  | 1.4.18.11 |  |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.5 | 203 |  | 1.5 |  |  |  | Define Tollgate Conducted
1.6 | 204 |  | 1.6 |  |  |  | Construct
1.6.1 | 205 |  | 1.6.1 |  |  |  | Communicate Final Supplier Management Plan
1.6.2 | 206 |  | 1.6.2 |  |  |  | Conduct Construct Phase Kick-Off | Supplier,Project Manager
1.6.3 | 207 |  | 1.6.3 |  |  |  | Construct Phase Kick-Off Conducted
1.6.4 | 208 |  | 1.6.4 |  |  |  | Develop Detailed Design
1.6.4.1 | 209 |  | 1.6.4.1 |  |  |  | Develop Detailed Architecture | Supplier,Project Architect
1.6.4.2 | 210 |  | 1.6.4.2 |  |  |  | Identify Product Components and Interfaces | Supplier,Project Architect[30%]
1.6.4.3 | 211 |  | 1.6.4.3 |  |  |  | Develop and Analyze Design Alternatives | Project Architect,Supplier
1.6.4.4 | 212 |  | 1.6.4.4 |  |  |  | Develop Operational Design
1.6.4.5 | 213 |  | 1.6.4.5 |  |  |  | Conduct Detail Design Review | Supplier,Project Architect
1.6.4.6 | 214 |  | 1.6.4.6 |  |  |  | Document System Design Document (SDD) | Supplier
1.6.4.7 | 215 |  | 1.6.4.7 |  |  |  | Update Requirements Traceability Matrix (RTM) | Project Architect[50%],Supplier
1.6.4.8 | 216 |  | 1.6.4.8 |  |  |  | Check for Consistency in Work Product | Project Manager,Project Architect
1.6.4.9 | 217 |  | 1.6.4.9 |  |  |  | Review System Design Document | Project Manager,Supplier[50%]
1.6.4.9.1 | 218 |  | 1.6.4.9.1 |  |  |  | Identify Reviewers
1.6.4.9.2 | 219 |  | 1.6.4.9.2 |  |  |  | Schedule Review
1.6.4.9.3 | 220 |  | 1.6.4.9.3 |  |  |  | Review and Log Feedback
1.6.4.9.4 | 221 |  | 1.6.4.9.4 |  |  |  | Fix Defects Detected from Review
1.6.4.9.5 | 222 |  | 1.6.4.9.5 |  |  |  | Verify Closure of Defects
1.6.4.9.6 | 223 |  | 1.6.4.9.6 |  |  |  | Document and Communicate Review Results
1.6.4.10 | 224 |  | 1.6.4.10 |  |  |  | Obtain Approval and Baseline SDD | Supplier[30%],Project Manager,CM Lead[30%]
1.6.4.11 | 225 |  | 1.6.4.11 |  |  |  | Develop Physical Data Model (PDM) | DBA Supplier,Project Manager
1.6.5 | 226 |  | 1.6.5 |  |  |  | Develop Test Plans
1.6.5.1 | 227 |  | 1.6.5.1 |  |  |  | Develop User Acceptance Test Plan (UATP)
1.6.5.1.1 | 228 |  | 1.6.5.1.1 |  |  |  | Identify Pre-Production Environment Requirements
1.6.5.1.2 | 229 |  | 1.6.5.1.2 |  |  |  | Identify Test Data Requirements for User Acceptance Testing
1.6.5.1.3 | 230 |  | 1.6.5.1.3 |  |  |  | Develop Schedule for User Acceptance Testing | Supplier
1.6.5.1.4 | 231 |  | 1.6.5.1.4 |  |  |  | Document Defect and Problem Reporting Procedures | Project Manager,Supplier[50%]
1.6.5.1.5 | 232 |  | 1.6.5.1.5 |  |  |  | Document User Acceptance Test Plan (UATP)
1.6.5.1.6 | 233 |  | 1.6.5.1.6 |  |  |  | Ensure Review of UATP
1.6.5.1.6.1 | 234 |  | 1.6.5.1.6.1 |  |  |  | Identify Reviewers
1.6.5.1.6.2 | 235 |  | 1.6.5.1.6.2 |  |  |  | Schedule Review
1.6.5.1.6.3 | 236 |  | 1.6.5.1.6.3 |  |  |  | Review and Log Feedback
1.6.5.1.6.4 | 237 |  | 1.6.5.1.6.4 |  |  |  | Fix Defects Detected from Review
1.6.5.1.6.5 | 238 |  | 1.6.5.1.6.5 |  |  |  | Verify Closure of Defects
1.6.5.1.6.6 | 239 |  | 1.6.5.1.6.6 |  |  |  | Document and Communicate Review Results
1.6.5.2 | 240 |  | 1.6.5.2 |  |  |  | Obtain Approval and Baseline UATP | CM Lead[30%],Project Manager,Test Manager,Supplier[30%]
1.6.5.3 | 241 |  | 1.6.5.3 |  |  |  | Develop Acceptance Test Cases
1.6.5.3.1 | 242 |  | 1.6.5.3.1 |  |  |  | Document User Acceptance Test (UAT) Cases
1.6.5.3.2 | 243 |  | 1.6.5.3.2 |  |  |  | Update UAT Case References in RTM
1.6.5.3.3 | 244 |  | 1.6.5.3.3 |  |  |  | Ensure Review of UAT Cases
1.6.5.3.3.1 | 245 |  | 1.6.5.3.3.1 |  |  |  | Identify Reviewers
1.6.5.3.3.2 | 246 |  | 1.6.5.3.3.2 |  |  |  | Schedule Review
1.6.5.3.3.3 | 247 |  | 1.6.5.3.3.3 |  |  |  | Review and Log Feedback
1.6.5.3.3.4 | 248 |  | 1.6.5.3.3.4 |  |  |  | Fix Defects Detected from Review
1.6.5.3.3.5 | 249 |  | 1.6.5.3.3.5 |  |  |  | Verify Closure of Defects
1.6.5.3.3.6 | 250 |  | 1.6.5.3.3.6 |  |  |  | Document and Communicate Review Results
1.6.5.3.4 | 251 |  | 1.6.5.3.4 |  |  |  | Obtain Approval and Baseline Acceptance Test Cases | Project Manager,CM Lead[30%]
1.6.5.3.5 | 252 |  | 1.6.5.3.5 |  |  |  | Document Non-Functional Test Cases
1.6.5.3.6 | 253 |  | 1.6.5.3.6 |  |  |  | Update Non-Functional Test Case References in Requirements Traceability Matrix (RTM)
1.6.5.3.7 | 254 |  | 1.6.5.3.7 |  |  |  | Ensure Review of Non-Functional Test Cases
1.6.5.3.7.1 | 255 |  | 1.6.5.3.7.1 |  |  |  | Identify Reviewers
1.6.5.3.7.2 | 256 |  | 1.6.5.3.7.2 |  |  |  | Schedule Review
1.6.5.3.7.3 | 257 |  | 1.6.5.3.7.3 |  |  |  | Review and Log Feedback
1.6.5.3.7.4 | 258 |  | 1.6.5.3.7.4 |  |  |  | Fix Defects Detected from Review
1.6.5.3.7.5 | 259 |  | 1.6.5.3.7.5 |  |  |  | Verify Closure of Defects
1.6.5.3.7.6 | 260 |  | 1.6.5.3.7.6 |  |  |  | Document and Communicate Review Results
1.6.5.4 | 261 |  | 1.6.5.4 |  |  |  | Develop System Test Plan (STP)
1.6.5.4.1 | 262 |  | 1.6.5.4.1 |  |  |  | Identify Test Environment Requirements
1.6.5.4.2 | 263 |  | 1.6.5.4.2 |  |  |  | Identify Test Data Requirements for System Testing
1.6.5.4.3 | 264 |  | 1.6.5.4.3 |  |  |  | Develop Schedule for System Testing
1.6.5.4.4 | 265 |  | 1.6.5.4.4 |  |  |  | Document System Test Plan (STP)
1.6.5.5 | 266 |  | 1.6.5.5 |  |  |  | Obtain Approval and Baseline STP | Supplier[30%],Test Manager,Project Manager,CM Lead[30%]
1.6.5.6 | 267 |  | 1.6.5.6 |  |  |  | Identify and Document System Test Cases | Supplier
1.6.6 | 268 |  | 1.6.6 |  |  |  | Complete System Deployment Plan
1.6.6.1 | 269 |  | 1.6.6.1 |  |  |  | Develop Training Plan for System Deployment
1.6.6.2 | 270 |  | 1.6.6.2 |  |  |  | Develop Pilot Deployment Plan
1.6.6.2.1 | 271 |  | 1.6.6.2.1 |  |  |  | Develop Security Plan
1.6.6.2.2 | 272 |  | 1.6.6.2.2 |  |  |  | Develop Data Conversion and Load Plan
1.6.6.2.3 | 273 |  | 1.6.6.2.3 |  |  |  | Develop Site Deployment Schedule
1.6.6.2.4 | 274 |  | 1.6.6.2.4 |  |  |  | Develop Test Plans for the Site
1.6.6.2.5 | 275 |  | 1.6.6.2.5 |  |  |  | Develop Operations, Maintenance and Support Plan
1.6.6.2.6 | 276 |  | 1.6.6.2.6 |  |  |  | Develop Application Disaster Recovery Plan for the Site
1.6.6.2.7 | 277 |  | 1.6.6.2.7 |  |  |  | Document Site Deployment Plan (SDP)
1.6.6.2.8 | 278 |  | 1.6.6.2.8 |  |  |  | Review Site Deployment Plan
1.6.6.2.9 | 279 |  | 1.6.6.2.9 |  |  |  | Obtain Approval and Baseline SDP
1.6.6.3 | 280 |  | 1.6.6.3 |  |  |  | Develop Site Deployment Plan (SDP)
1.6.6.3.1 | 281 |  | 1.6.6.3.1 |  |  |  | Develop Security Plan
1.6.6.3.2 | 282 |  | 1.6.6.3.2 |  |  |  | Develop Data Conversion and Load Plan
1.6.6.3.3 | 283 |  | 1.6.6.3.3 |  |  |  | Develop Site Deployment Schedule
1.6.6.3.4 | 284 |  | 1.6.6.3.4 |  |  |  | Develop Test Plans for the Site
1.6.6.3.5 | 285 |  | 1.6.6.3.5 |  |  |  | Develop Operations, Maintenance and Support Plan
1.6.6.3.6 | 286 |  | 1.6.6.3.6 |  |  |  | Develop Application Disaster Recovery Plan for the Site
1.6.6.3.7 | 287 |  | 1.6.6.3.7 |  |  |  | Document Site Deployment Plan (SDP)
1.6.6.3.8 | 288 |  | 1.6.6.3.8 |  |  |  | Review Site Deployment Plan
1.6.6.3.9 | 289 |  | 1.6.6.3.9 |  |  |  | Obtain Approval and Baseline SDP
1.6.6.4 | 290 |  | 1.6.6.4 |  |  |  | Develop System Deployment Schedule
1.6.6.5 | 291 |  | 1.6.6.5 |  |  |  | Document System Deployment Plan (DP)
1.6.6.6 | 292 |  | 1.6.6.6 |  |  |  | Check for Consistency with SDP(s)
1.6.6.7 | 293 |  | 1.6.6.7 |  |  |  | Ensure Review System Deployment Plan
1.6.6.7.1 | 294 |  | 1.6.6.7.1 |  |  |  | Identify Reviewers
1.6.6.7.2 | 295 |  | 1.6.6.7.2 |  |  |  | Schedule Review
1.6.6.7.3 | 296 |  | 1.6.6.7.3 |  |  |  | Review and Log Feedback
1.6.6.7.4 | 297 |  | 1.6.6.7.4 |  |  |  | Fix Defects Detected from Review
1.6.6.7.5 | 298 |  | 1.6.6.7.5 |  |  |  | Verify Closure of Defects
1.6.6.7.6 | 299 |  | 1.6.6.7.6 |  |  |  | Document and Communicate Review Results
1.6.6.8 | 300 |  | 1.6.6.8 |  |  |  | Obtain Approval and Baseline DP
1.6.7 | 301 |  | 1.6.7 |  |  |  | System Deployment Plan Completed
1.6.8 | 302 |  | 1.6.8 |  |  |  | Code and Unit Test | Supplier
1.6.8.1 | 303 |  | 1.6.8.1 |  |  |  | Develop Source Code and Conduct Unit Testing
1.6.8.2 | 304 |  | 1.6.8.2 |  |  |  | Update Requirements Traceability Matrix (RTM)
1.6.8.3 | 305 |  | 1.6.8.3 |  |  |  | Develop Integration Test Cases
1.6.9 | 306 |  | 1.6.9 |  |  |  | Configure, Integrate and Deliver System | Supplier
1.6.9.1 | 307 |  | 1.6.9.1 |  |  |  | Integrate and Build the System
1.6.9.2 | 308 |  | 1.6.9.2 |  |  |  | Configure the System
1.6.9.3 | 309 |  | 1.6.9.3 |  |  |  | Conduct Integration Testing
1.6.9.4 | 310 |  | 1.6.9.4 |  |  |  | Update Requirements Traceability Matrix (RTM)
1.6.9.5 | 311 |  | 1.6.9.5 |  |  |  | Develop System Documentation and Training Material for the System
1.6.9.6 | 312 |  | 1.6.9.6 |  |  |  | Deliver the System
1.6.10 | 313 |  | 1.6.10 |  |  |  | Conduct System Testing Readiness Review
1.6.10.1 | 314 |  | 1.6.10.1 |  |  |  | Set Up Test Environment
1.6.10.1.1 | 315 |  | 1.6.10.1.1 |  |  |  | Install Test Environment
1.6.10.1.2 | 316 |  | 1.6.10.1.2 |  |  |  | Apply Infrastructure Changes
1.6.10.1.3 | 317 |  | 1.6.10.1.3 |  |  |  | Apply Security Changes
1.6.10.1.4 | 318 |  | 1.6.10.1.4 |  |  |  | Convert and Migrate Data
1.6.10.1.5 | 319 |  | 1.6.10.1.5 |  |  |  | Verify Test Environment
1.6.10.1.6 | 320 |  | 1.6.10.1.6 |  |  |  | Verify and Audit Test Environment
1.6.10.1.7 | 321 |  | 1.6.10.1.7 |  |  |  | Fix Gaps Related to Test Environment
1.6.10.2 | 322 |  | 1.6.10.2 |  |  |  | Test Build and Installation of the System
1.6.10.2.1 | 323 |  | 1.6.10.2.1 |  |  |  | Verify Installation and System Documentation
1.6.10.2.2 | 324 |  | 1.6.10.2.2 |  |  |  | Fix Defects and Issues
1.6.10.2.3 | 325 |  | 1.6.10.2.3 |  |  |  | Update Installation and System Documentation
1.6.10.2.4 | 326 |  | 1.6.10.2.4 |  |  |  | Build the System
1.6.10.2.5 | 327 |  | 1.6.10.2.5 |  |  |  | Install and Configure the System
1.6.10.2.6 | 328 |  | 1.6.10.2.6 |  |  |  | Obtain Approval and Check-In SD, SC and Installation Guide | CM Lead[30%]
1.6.10.3 | 329 |  | 1.6.10.3 |  |  |  | Conduct System Testing Readiness Review Meeting
1.6.10.4 | 330 |  | 1.6.10.4 |  |  |  | Conduct Release Audit
1.6.11 | 331 |  | 1.6.11 |  |  |  | Conduct Construct Tollgate
1.6.11.1 | 332 |  | 1.6.11.1 |  |  |  | Update Plan(s) for Test and Deploy Phases | Project Manager,CM Lead,QA Analyst
1.6.11.2 | 333 |  | 1.6.11.2 |  |  |  | Request Tollgate Review | Project Manager[30%]
1.6.11.3 | 334 |  | 1.6.11.3 |  |  |  | Update Business Case | Project Manager[30%]
1.6.11.4 | 335 |  | 1.6.11.4 |  |  |  | Prepare for Project Tollgate Review | Stakeholder[30%]
1.6.11.5 | 336 |  | 1.6.11.5 |  |  |  | Review Plan(s) for Test and Deploy Phases | PMO Prg. Mgr.[50%]
1.6.11.6 | 337 |  | 1.6.11.6 |  |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.6.11.7 | 338 |  | 1.6.11.7 |  |  |  | Conduct CM Audits | QA Analyst
1.6.11.8 | 339 |  | 1.6.11.8 |  |  |  | Prepare Construct Tollgate Review Report | Project Manager[20%]
1.6.11.9 | 340 |  | 1.6.11.9 |  |  |  | Update and Communicate Construct Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.6.11.10 | 341 |  | 1.6.11.10 |  |  |  | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.6.11.11 | 342 |  | 1.6.11.11 |  |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.7 | 343 |  | 1.7 |  |  |  | Construct Tollgate Conducted
1.8 | 344 |  | 1.8 |  |  |  | Test
1.8.1 | 345 |  | 1.8.1 |  |  |  | Conduct System Testing
1.8.1.1 | 346 |  | 1.8.1.1 |  |  |  | Develop Test Scripts | Supplier
1.8.1.2 | 347 |  | 1.8.1.2 |  |  |  | Validate Test Scripts | Supplier
1.8.1.3 | 348 |  | 1.8.1.3 |  |  |  | Update Requirements Traceability Matrix (RTM) | Supplier
1.8.1.4 | 349 |  | 1.8.1.4 |  |  |  | Check-In Test Scripts and RTM | Supplier,CM Lead[60%]
1.8.1.5 | 350 |  | 1.8.1.5 |  |  |  | Set Up Test Environment
1.8.1.5.1 | 351 |  | 1.8.1.5.1 |  |  |  | Install Test Environment | Project Manager,Test Manager,Supplier,System Deployment Manager
1.8.1.5.2 | 352 |  | 1.8.1.5.2 |  |  |  | Apply Infrastructure Changes | Project Manager,Test Manager,Supplier,System Deployment Manager
1.8.1.5.3 | 353 |  | 1.8.1.5.3 |  |  |  | Apply Security Changes | Project Manager,Test Manager,Supplier,System Deployment Manager
1.8.1.5.4 | 354 |  | 1.8.1.5.4 |  |  |  | Convert and Migrate Data | Project Manager,Test Manager,Supplier,System Deployment Manager
1.8.1.5.5 | 355 |  | 1.8.1.5.5 |  |  |  | Verify Test Environment | Test Manager,Supplier
1.8.1.5.6 | 356 |  | 1.8.1.5.6 |  |  |  | Verify and Audit Test Environment | Project Manager
1.8.1.5.7 | 357 |  | 1.8.1.5.7 |  |  |  | Fix Gaps Related to Test Environment | Test Manager,Supplier,System Deployment Manager
1.8.1.6 | 358 |  | 1.8.1.6 |  |  |  | Test Build and Installation of the System
1.8.1.6.1 | 359 |  | 1.8.1.6.1 |  |  |  | Build the System | Supplier
1.8.1.6.2 | 360 |  | 1.8.1.6.2 |  |  |  | Install and Configure the System | Supplier
1.8.1.6.3 | 361 |  | 1.8.1.6.3 |  |  |  | Verify Installation and System Documentation | Supplier
1.8.1.6.4 | 362 |  | 1.8.1.6.4 |  |  |  | Fix Defects and Issues | Supplier
1.8.1.6.5 | 363 |  | 1.8.1.6.5 |  |  |  | Update Installation and System Documentation | Supplier
1.8.1.6.6 | 364 |  | 1.8.1.6.6 |  |  |  | Obtain Approval and Check-In SD, SC and Installation Guide | CM Lead[30%],Supplier,Project Manager
1.8.1.7 | 365 |  | 1.8.1.7 |  |  |  | Execute System Tests
1.8.1.7.1 | 366 |  | 1.8.1.7.1 |  |  |  | Run Test Scripts | Supplier
1.8.1.7.2 | 367 |  | 1.8.1.7.2 |  |  |  | Record Test Results | Supplier
1.8.1.7.3 | 368 |  | 1.8.1.7.3 |  |  |  | Run Test Cases | Supplier
1.8.1.8 | 369 |  | 1.8.1.8 |  |  |  | Prepare System Test Summary Report (STSR) for the Cycle | Supplier
1.8.1.9 | 370 |  | 1.8.1.9 |  |  |  | Review System Test Summary Report (STSR) for the Cycle | Project Manager,Test Manager,Supplier
1.8.1.10 | 371 |  | 1.8.1.10 |  |  |  | Plan Next Test Cycle | Project Manager,Test Manager,Supplier
1.8.1.11 | 372 |  | 1.8.1.11 |  |  |  | Fix Defects and Issues | Project Manager,Test Manager,Supplier
1.8.1.12 | 373 |  | 1.8.1.12 |  |  |  | Verify System Test Results | Project Manager,Test Manager,Supplier
1.8.1.13 | 374 |  | 1.8.1.13 |  |  |  | Log Defects and Issues | Project Manager,Test Manager,Supplier
1.8.1.14 | 375 |  | 1.8.1.14 |  |  |  | Generate Final System Test Summary Report (STSR) | Project Manager,Test Manager,Supplier
1.8.1.15 | 376 |  | 1.8.1.15 |  |  |  | Check-In System Test Cases and System Test Summary Report (STSR) | Project Manager,Test Manager,Supplier,CM Lead[60%]
1.8.2 | 377 |  | 1.8.2 |  |  |  | Prepare Pre-Production Environment at Site
1.8.2.1 | 378 |  | 1.8.2.1 |  |  |  | Prepare Site for System Changes
1.8.2.1.1 | 379 |  | 1.8.2.1.1 |  |  |  | Prepare Site for Infrastructure Changes | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.1.2 | 380 |  | 1.8.2.1.2 |  |  |  | Prepare Site for Security Changes | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.1.3 | 381 |  | 1.8.2.1.3 |  |  |  | Prepare Site for Application Data Migration | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.2 | 382 |  | 1.8.2.2 |  |  |  | Create System Migration Plan | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.3 | 383 |  | 1.8.2.3 |  |  |  | Conduct Test and Site Readiness Review | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.4 | 384 |  | 1.8.2.4 |  |  |  | Prepare Test Cases for the Sites | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.5 | 385 |  | 1.8.2.5 |  |  |  | Update System Documentation and Test Plans for the Site | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.6 | 386 |  | 1.8.2.6 |  |  |  | Update Site Deployment Plan | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.7 | 387 |  | 1.8.2.7 |  |  |  | Apply Infrastructure Changes | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.8 | 388 |  | 1.8.2.8 |  |  |  | Apply Security Changes | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.2.9 | 389 |  | 1.8.2.9 |  |  |  | Convert and Migrate Data | Site Operations and Support Manager,System Deployment Manager,Site Deployment Manager
1.8.3 | 390 |  | 1.8.3 |  |  |  | Conduct Acceptance Testing Readiness Review
1.8.3.1 | 391 |  | 1.8.3.1 |  |  |  | Perform Checks to Verify Pre-Production Environment | Operations and Support Manager,System Deployment Manager,Test Manager,Project Manager,Supplier
1.8.3.2 | 392 |  | 1.8.3.2 |  |  |  | Fix Gaps Related to Pre-Production Environment | Operations and Support Manager,System Deployment Manager,Test Manager,Project Manager,Supplier
1.8.3.3 | 393 |  | 1.8.3.3 |  |  |  | Verify and Audit Pre-Production Environment | Test Manager,Project Manager,Supplier
1.8.3.4 | 394 |  | 1.8.3.4 |  |  |  | Review and Approve System Documentation | Operations and Support Manager,System Deployment Manager
1.8.3.5 | 395 |  | 1.8.3.5 |  |  |  | Test Build and Installation for Acceptance Testing
1.8.3.5.1 | 396 |  | 1.8.3.5.1 |  |  |  | Build the System | Supplier
1.8.3.5.2 | 397 |  | 1.8.3.5.2 |  |  |  | Install and Configure the System | Supplier
1.8.3.5.3 | 398 |  | 1.8.3.5.3 |  |  |  | Verify Installation and System Documentation | Supplier,Project Manager
1.8.3.5.4 | 399 |  | 1.8.3.5.4 |  |  |  | Fix Defects and Issues | Supplier
1.8.3.5.5 | 400 |  | 1.8.3.5.5 |  |  |  | Update Installation and System Documentation | Supplier
1.8.3.5.6 | 401 |  | 1.8.3.5.6 |  |  |  | Obtain Approval and Check-In SD, SC and Installation Guide | Supplier,Project Manager,CM Lead[60%]
1.8.3.6 | 402 |  | 1.8.3.6 |  |  |  | Conduct Release Audit | Supplier,CM Lead[60%],QA Analyst
1.8.3.7 | 403 |  | 1.8.3.7 |  |  |  | Conduct Acceptance Testing Readiness Review Meeting | Test Manager,System Deployment Manager,Operations and Support Manager,QA Analyst,PMO Prg. Mgr.,Project Manager,Senior Manager[40%],Endusers
1.8.4 | 404 |  | 1.8.4 |  |  |  | Conduct Acceptance Testing
1.8.4.1 | 405 |  | 1.8.4.1 |  |  |  | Execute User Acceptance Tests
1.8.4.2 | 406 |  | 1.8.4.2 |  |  |  | Verify Acceptance Test Results
1.8.4.3 | 407 |  | 1.8.4.3 |  |  |  | Log Defects and Issues
1.8.4.4 | 408 |  | 1.8.4.4 |  |  |  | Prepare User Acceptance Test Summary Report (UATSR) for the Cycle
1.8.4.5 | 409 |  | 1.8.4.5 |  |  |  | Ensure Review of User Acceptance Test Summary Report
1.8.4.6 | 410 |  | 1.8.4.6 |  |  |  | Plan Next Test Cycle
1.8.4.7 | 411 |  | 1.8.4.7 |  |  |  | Generate Final User Acceptance Test Summary Report
1.8.4.8 | 412 |  | 1.8.4.8 |  |  |  | Sign-off on User Acceptance Tests
1.8.4.9 | 413 |  | 1.8.4.9 |  |  |  | Approve Acceptance Test Results
1.8.4.10 | 414 |  | 1.8.4.10 |  |  |  | Communicate Final UATSR to Senior Management
1.8.4.11 | 415 |  | 1.8.4.11 |  |  |  | Provide Approval to Baseline Source, Binaries and System Documentation
1.8.4.12 | 416 |  | 1.8.4.12 |  |  |  | Sign-off on Non-Functional Tests
1.8.4.13 | 417 |  | 1.8.4.13 |  |  |  | Execute Non-Functional Acceptance Tests
1.8.5 | 418 |  | 1.8.5 |  |  |  | Acceptance Testing Conducted
1.8.6 | 419 |  | 1.8.6 |  |  |  | Analyze Defects and Change Requests
1.8.7 | 420 |  | 1.8.7 |  |  |  | Verify Production Readiness
1.8.8 | 421 |  | 1.8.8 |  |  |  | Conduct Test Tollgate
1.8.8.1 | 422 |  | 1.8.8.1 |  |  |  | Review Plan(s) for Deploy Phase | PMO Prg. Mgr.[50%]
1.8.9 | 423 |  | 1.8.9 |  |  |  | Conduct Test Phase Tollgate
1.8.9.1 | 424 |  | 1.8.9.1 |  |  |  | Update Plan(s) for Deploy Phase | Project Manager,CM Lead,QA Analyst
1.8.9.2 | 425 |  | 1.8.9.2 |  |  |  | Request Tollgate Review | Project Manager[30%]
1.8.9.3 | 426 |  | 1.8.9.3 |  |  |  | Update Business Case | Project Manager[30%]
1.8.9.4 | 427 |  | 1.8.9.4 |  |  |  | Prepare for Project Tollgate Review | Stakeholder[30%]
1.8.9.5 | 428 |  | 1.8.9.5 |  |  |  | Review Plan(s) for Deploy Phase | PMO Prg. Mgr.[50%]
1.8.9.6 | 429 |  | 1.8.9.6 |  |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.8.9.7 | 430 |  | 1.8.9.7 |  |  |  | Conduct CM Audits | QA Analyst
1.8.9.8 | 431 |  | 1.8.9.8 |  |  |  | Prepare Test Tollgate Review Report | Project Manager[20%]
1.8.9.9 | 432 |  | 1.8.9.9 |  |  |  | Update and Communicate Test Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.8.9.10 | 433 |  | 1.8.9.10 |  |  |  | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.8.9.11 | 434 |  | 1.8.9.11 |  |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.8.9.12 | 435 |  | 1.8.9.12 |  |  |  | Accept Product | System Deployment Manager[50%]
1.8.9.12.1 | 436 |  | 1.8.9.12.1 |  |  |  | Accept the acquired product
1.8.9.12.2 | 437 |  | 1.8.9.12.2 |  |  |  | Transition product to Operations
1.8.9.12.3 | 438 |  | 1.8.9.12.3 |  |  |  | Review Supplier Performance
1.8.9.12.4 | 439 |  | 1.8.9.12.4 |  |  |  | Execute Supplier payment process
1.9 | 440 |  | 1.9 |  |  |  | Test Tollgate Conducted
1.1 | 441 |  | 1.1 |  |  |  | Deploy
1.10.1 | 442 |  | 1.10.1 |  |  |  | Deploy at Pilot Site
1.10.1.1 | 443 |  | 1.10.1.1 |  |  |  | Migrate to New System at Pilot Site
1.10.1.1.1 | 444 |  | 1.10.1.1.1 |  |  |  | Execute Migration | Pilot Site Lead
1.10.1.1.2 | 445 |  | 1.10.1.1.2 |  |  |  | Perform Checks to Verify Migration | Pilot Site Lead,Pilot Site Deployment Manager[30%]
1.10.1.1.3 | 446 |  | 1.10.1.1.3 |  |  |  | Check Contingency Plan for Alternative(s) | Pilot Site Lead,Pilot Site Deployment Manager
1.10.1.1.4 | 447 |  | 1.10.1.1.4 |  |  |  | Modify System Environment or Components | Pilot Site Lead
1.10.1.1.5 | 448 |  | 1.10.1.1.5 |  |  |  | Execute Back out Plan | Pilot Site Deployment Manager
1.10.1.1.6 | 449 |  | 1.10.1.1.6 |  |  |  | Communicate To Stakeholders | Pilot Site Deployment Manager,Senior Manager,Pilot Site Manager
1.10.1.1.7 | 450 |  | 1.10.1.1.7 |  |  |  | Communicate Deployment Status
1.10.1.2 | 451 |  | 1.10.1.2 |  |  |  | Migrated to New System at Pilot Site
1.10.1.3 | 452 |  | 1.10.1.3 |  |  |  | Update Generic Site Deployment Materials & System Documentation | System Deployment Manager
1.10.1.4 | 453 |  | 1.10.1.4 |  |  |  | Transition to Operations at Pilot Site
1.10.1.4.1 | 454 |  | 1.10.1.4.1 |  |  |  | Support New System | Pilot Site Deployment Team Member,Pilot Site Deployment Manager
1.10.1.4.2 | 455 |  | 1.10.1.4.2 |  |  |  | Transfer Ownership to System Owner | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team
1.10.1.4.3 | 456 |  | 1.10.1.4.3 |  |  |  | Archive System Documentation, Training Material & Application/System Components | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team
1.10.1.4.4 | 457 |  | 1.10.1.4.4 |  |  |  | Train Operations Team | Pilot Site Operations & Support Team,System Owner,Pilot Site Deployment Manager
1.10.1.5 | 458 |  | 1.10.1.5 |  |  |  | De-Install Legacy System at Pilot Site | Pilot Site Deployment Manager
1.10.1.6 | 459 |  | 1.10.1.6 |  |  |  | Legacy System De-Installed at Pilot Site
1.10.2 | 460 |  | 1.10.2 |  |  |  | Deploy at Site <1>
1.10.2.1 | 461 |  | 1.10.2.1 |  |  |  | Migrate to New System at at Site <1>
1.10.2.1.1 | 462 |  | 1.10.2.1.1 |  |  |  | Execute Migration | Site1 Lead
1.10.2.1.2 | 463 |  | 1.10.2.1.2 |  |  |  | Perform Checks to Verify Migration | Site1 Deployment Manager[30%],Site1 Lead
1.10.2.1.3 | 464 |  | 1.10.2.1.3 |  |  |  | Check Contingency Plan for Alternative(s) | Site1 Deployment Manager,Site1 Lead
1.10.2.1.4 | 465 |  | 1.10.2.1.4 |  |  |  | Modify System Environment or Components | Site1 Lead
1.10.2.1.5 | 466 |  | 1.10.2.1.5 |  |  |  | Execute Back out Plan | Site1 Deployment Manager
1.10.2.1.6 | 467 |  | 1.10.2.1.6 |  |  |  | Communicate To Stakeholders | Site1 Manager,Senior Manager,Site1 Deployment Manager
1.10.2.1.7 | 468 |  | 1.10.2.1.7 |  |  |  | Communicate Deployment Status
1.10.2.2 | 469 |  | 1.10.2.2 |  |  |  | Migrated to New System at at Site <1>
1.10.2.3 | 470 |  | 1.10.2.3 |  |  |  | Update Generic Site Deployment Materials & System Documentation | System Deployment Manager
1.10.2.4 | 471 |  | 1.10.2.4 |  |  |  | Transition to Operations at at Site <1>
1.10.2.4.1 | 472 |  | 1.10.2.4.1 |  |  |  | Support New System | Site1 Deployment Manager,Site1 Deployment Team Member
1.10.2.4.2 | 473 |  | 1.10.2.4.2 |  |  |  | Transfer Ownership to System Owner | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.10.2.4.3 | 474 |  | 1.10.2.4.3 |  |  |  | Archive System Documentation, Training Material & Application/System Components | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.10.2.4.4 | 475 |  | 1.10.2.4.4 |  |  |  | Train Operations Team | Site1 Deployment Manager,System Owner,Site1 Operations & Support Team
1.10.2.5 | 476 |  | 1.10.2.5 |  |  |  | De-Install Legacy System at at Site <1> | Site1 Deployment Manager
1.10.2.6 | 477 |  | 1.10.2.6 |  |  |  | Legacy System De-Installed at Site <1>
1.10.3 | 478 |  | 1.10.3 |  |  |  | Close Project
1.10.3.1 | 479 |  | 1.10.3.1 |  |  |  | Conduct Post-Project Review
1.10.3.1.1 | 480 |  | 1.10.3.1.1 |  |  |  | Develop Post Project Review Breakout Session Topics & Agenda | Project Team,Project Manager,System Deployment Manager,QA Analyst,CM Lead
1.10.3.1.2 | 481 |  | 1.10.3.1.2 |  |  |  | Conduct Post Project Review Meeting | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead
1.10.3.1.3 | 482 |  | 1.10.3.1.3 |  |  |  | Complete Post Project Review Report | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead
1.10.3.1.4 | 483 |  | 1.10.3.1.4 |  |  |  | Create Project Role Feedback Forms | Project Manager,Project Team,System Deployment Manager,QA Analyst,CM Lead
1.10.3.2 | 484 |  | 1.10.3.2 |  |  |  | Archive Documents | Project Manager,Project Team,QA Analyst,CM Lead
1.10.3.3 | 485 |  | 1.10.3.3 |  |  |  | Close Project formally and Communicate | Project Manager
1.11 | 486 |  | 1.11 |  |  |  | Project <PTS -ID> Closed
1.12 | 487 |  | 1.12 |  |  |  | Project Support Activities
1.12.1 | 488 |  | 1.12.1 |  |  |  | Manage Requirements
1.12.1.1 | 489 |  | 1.12.1.1 |  |  |  | Understand Change in Requirements | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.2 | 490 |  | 1.12.1.2 |  |  |  | Perform Detailed Impact Analysis | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.3 | 491 |  | 1.12.1.3 |  |  |  | Raise Requirements Change Request (RCR) Form | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.4 | 492 |  | 1.12.1.4 |  |  |  | Review through Requirements Change Control Board (RCCB) | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.5 | 493 |  | 1.12.1.5 |  |  |  | Re-Estimate & Re-Plan the Project | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.6 | 494 |  | 1.12.1.6 |  |  |  | Obtain Approval from Senior Manager for Change in Cost & Schedule | Senior Manager,Project Manager[30%]
1.12.1.7 | 495 |  | 1.12.1.7 |  |  |  | Update & Baseline Project Plan | Project Manager
1.12.1.8 | 496 |  | 1.12.1.8 |  |  |  | Communicate Changes in Project Plan | Project Manager
1.12.2 | 497 |  | 1.12.2 |  |  |  | Change Control
1.12.2.1 | 498 |  | 1.12.2.1 |  |  |  | Review Impact on CM Repository | CM Lead
1.12.2.2 | 499 |  | 1.12.2.2 |  |  |  | Review Impact on Work Products | Project Manager
1.12.2.3 | 500 |  | 1.12.2.3 |  |  |  | Update Change Register | CM Lead
1.12.2.4 | 501 |  | 1.12.2.4 |  |  |  | Review through Change Control Board (CCB) | Project Manager
1.12.2.5 | 502 |  | 1.12.2.5 |  |  |  | Update Change Register | CM Lead
1.12.2.6 | 503 |  | 1.12.2.6 |  |  |  | Update Change Register with Closure Details | Project Manager,CM Lead,Project Team Member[40%]
1.12.3 | 504 |  | 1.12.3 |  |  |  | Project Monitoring and Control
1.12.3.1 | 505 |  | 1.12.3.1 |  |  |  | Monitor Supplier Status
1.12.3.1.1 | 506 |  | 1.12.3.1.1 |  |  |  | Monitor Supplier Status 1 | Project Manager
1.12.3.1.2 | 507 |  | 1.12.3.1.2 |  |  |  | Monitor Supplier Status 2 | Project Manager
1.12.3.1.3 | 508 |  | 1.12.3.1.3 |  |  |  | Monitor Supplier Status 3 | Project Manager
1.12.3.1.4 | 509 |  | 1.12.3.1.4 |  |  |  | Monitor Supplier Status 4 | Project Manager
1.12.3.1.5 | 510 |  | 1.12.3.1.5 |  |  |  | Monitor Supplier Status 5 | Project Manager
1.12.3.2 | 511 |  | 1.12.3.2 |  |  |  | Update Project Log , Project Plan and Project Schedule
1.12.3.2.1 | 512 |  | 1.12.3.2.1 |  |  |  | Update Project Log , Project Plan and Project Schedule 1 | Project Manager
1.12.3.2.2 | 513 |  | 1.12.3.2.2 |  |  |  | Update Project Log , Project Plan and Project Schedule 2 | Project Manager
1.12.3.2.3 | 514 |  | 1.12.3.2.3 |  |  |  | Update Project Log , Project Plan and Project Schedule 3 | Project Manager
1.12.3.2.4 | 515 |  | 1.12.3.2.4 |  |  |  | Update Project Log , Project Plan and Project Schedule 4 | Project Manager
1.12.3.2.5 | 516 |  | 1.12.3.2.5 |  |  |  | Update Project Log , Project Plan and Project Schedule 5 | Project Manager
1.12.3.2.6 | 517 |  | 1.12.3.2.6 |  |  |  | Update Project Log , Project Plan and Project Schedule 6 | Project Manager
1.12.3.2.7 | 518 |  | 1.12.3.2.7 |  |  |  | Update Project Log , Project Plan and Project Schedule 7 | Project Manager
1.12.3.2.8 | 519 |  | 1.12.3.2.8 |  |  |  | Update Project Log , Project Plan and Project Schedule 8 | Project Manager
1.12.3.2.9 | 520 |  | 1.12.3.2.9 |  |  |  | Update Project Log , Project Plan and Project Schedule 9 | Project Manager
1.12.3.2.10 | 521 |  | 1.12.3.2.10 |  |  |  | Update Project Log , Project Plan and Project Schedule 10 | Project Manager
1.12.3.2.11 | 522 |  | 1.12.3.2.11 |  |  |  | Update Project Log , Project Plan and Project Schedule 11 | Project Manager
1.12.3.2.12 | 523 |  | 1.12.3.2.12 |  |  |  | Update Project Log , Project Plan and Project Schedule 12 | Project Manager
1.12.3.3 | 524 |  | 1.12.3.3 |  |  |  | Provide Measurement Results Based on SDP-21 Metrics | Project Manager
1.12.3.3.1 | 525 |  | 1.12.3.3.1 |  |  |  | Submit SDP-21 Standard Metrics
1.12.3.3.1.1 | 526 |  | 1.12.3.3.1.1 |  |  |  | Submit SDP-21 Standard Metrics 1 | Project Manager
1.12.3.3.1.2 | 527 |  | 1.12.3.3.1.2 |  |  |  | Submit SDP-21 Standard Metrics 2 | Project Manager
1.12.3.3.1.3 | 528 |  | 1.12.3.3.1.3 |  |  |  | Submit SDP-21 Standard Metrics 3 | Project Manager
1.12.3.3.1.4 | 529 |  | 1.12.3.3.1.4 |  |  |  | Submit SDP-21 Standard Metrics 4 | Project Manager
1.12.3.3.1.5 | 530 |  | 1.12.3.3.1.5 |  |  |  | Submit SDP-21 Standard Metrics 5 | Project Manager
1.12.3.4 | 531 |  | 1.12.3.4 |  |  |  | Update Project Tracking System (PTS)
1.12.3.4.1 | 532 |  | 1.12.3.4.1 |  |  |  | Update Project Tracking System (PTS) 1 | Project Manager
1.12.3.4.2 | 533 |  | 1.12.3.4.2 |  |  |  | Update Project Tracking System (PTS) 2 | Project Manager
1.12.3.4.3 | 534 |  | 1.12.3.4.3 |  |  |  | Update Project Tracking System (PTS) 3 | Project Manager
1.12.3.4.4 | 535 |  | 1.12.3.4.4 |  |  |  | Update Project Tracking System (PTS) 4 | Project Manager
1.12.3.4.5 | 536 |  | 1.12.3.4.5 |  |  |  | Update Project Tracking System (PTS) 5 | Project Manager
1.12.3.5 | 537 |  | 1.12.3.5 |  |  |  | Conduct Milestone Reviews
1.12.3.5.1 | 538 |  | 1.12.3.5.1 |  |  |  | Conduct Milestone Reviews 1 | Project Team,Operations and Support Manager,CM Lead,QA Analyst,Project Manager
1.12.3.5.2 | 539 |  | 1.12.3.5.2 |  |  |  | Conduct Milestone Reviews 2 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.3 | 540 |  | 1.12.3.5.3 |  |  |  | Conduct Milestone Reviews 3 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.4 | 541 |  | 1.12.3.5.4 |  |  |  | Conduct Milestone Reviews 4 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.5 | 542 |  | 1.12.3.5.5 |  |  |  | Conduct Milestone Reviews 5 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.6 | 543 |  | 1.12.3.6 |  |  |  | Conduct Senior Management Review (SMR) | Project Manager
1.12.3.6.1 | 544 |  | 1.12.3.6.1 |  |  |  | Conduct SMR meeting for the Project
1.12.3.6.1.1 | 545 |  | 1.12.3.6.1.1 |  |  |  | Conduct SMR meeting for the Project 1 | Project Manager,Senior Manager
1.12.3.6.1.2 | 546 |  | 1.12.3.6.1.2 |  |  |  | Conduct SMR meeting for the Project 2 | Project Manager,Senior Manager
1.12.3.6.1.3 | 547 |  | 1.12.3.6.1.3 |  |  |  | Conduct SMR meeting for the Project 3 | Project Manager,Senior Manager
1.12.3.6.1.4 | 548 |  | 1.12.3.6.1.4 |  |  |  | Conduct SMR meeting for the Project 4 | Project Manager,Senior Manager
1.12.3.6.1.5 | 549 |  | 1.12.3.6.1.5 |  |  |  | Conduct SMR meeting for the Project 5 | Project Manager,Senior Manager
1.12.3.7 | 550 |  | 1.12.3.7 |  |  |  | Conduct Progress Review Meetings | Project Manager
1.12.3.7.1 | 551 |  | 1.12.3.7.1 |  |  |  | Conduct Progress Review Meetings 1 | Project Manager
1.12.3.7.2 | 552 |  | 1.12.3.7.2 |  |  |  | Conduct Progress Review Meetings 2 | Project Manager
1.12.3.7.3 | 553 |  | 1.12.3.7.3 |  |  |  | Conduct Progress Review Meetings 3 | Project Manager
1.12.3.7.4 | 554 |  | 1.12.3.7.4 |  |  |  | Conduct Progress Review Meetings 4 | Project Manager
1.12.3.7.5 | 555 |  | 1.12.3.7.5 |  |  |  | Conduct Progress Review Meetings 5 | Project Manager
1.12.3.7.6 | 556 |  | 1.12.3.7.6 |  |  |  | Conduct Review with Stakeholders | Project Manager
1.12.3.8 | 557 |  | 1.12.3.8 |  |  |  | Monitor Project Plan and Schedule
1.12.3.8.1 | 558 |  | 1.12.3.8.1 |  |  |  | Monitor Project Plan and Schedule 1 | Project Manager
1.12.3.8.2 | 559 |  | 1.12.3.8.2 |  |  |  | Monitor Project Plan and Schedule 2 | Project Manager
1.12.3.8.3 | 560 |  | 1.12.3.8.3 |  |  |  | Monitor Project Plan and Schedule 3 | Project Manager
1.12.3.8.4 | 561 |  | 1.12.3.8.4 |  |  |  | Monitor Project Plan and Schedule 4 | Project Manager
1.12.3.8.5 | 562 |  | 1.12.3.8.5 |  |  |  | Monitor Project Plan and Schedule 5 | Project Manager
1.12.3.8.6 | 563 |  | 1.12.3.8.6 |  |  |  | Monitor Project Plan and Schedule 6 | Project Manager
1.12.3.8.7 | 564 |  | 1.12.3.8.7 |  |  |  | Monitor Project Plan and Schedule 7 | Project Manager
1.12.3.8.8 | 565 |  | 1.12.3.8.8 |  |  |  | Monitor Project Plan and Schedule 8 | Project Manager
1.12.3.8.9 | 566 |  | 1.12.3.8.9 |  |  |  | Monitor Project Plan and Schedule 9 | Project Manager
1.12.3.8.10 | 567 |  | 1.12.3.8.10 |  |  |  | Monitor Project Plan and Schedule 10 | Project Manager
1.12.3.9 | 568 |  | 1.12.3.9 |  |  |  | Monitor Project Risks
1.12.3.9.1 | 569 |  | 1.12.3.9.1 |  |  |  | Monitor Project Risks 1 | Project Manager
1.12.3.9.2 | 570 |  | 1.12.3.9.2 |  |  |  | Monitor Project Risks 2 | Project Manager
1.12.3.9.3 | 571 |  | 1.12.3.9.3 |  |  |  | Monitor Project Risks 3 | Project Manager
1.12.3.9.4 | 572 |  | 1.12.3.9.4 |  |  |  | Monitor Project Risks 4 | Project Manager
1.12.3.9.5 | 573 |  | 1.12.3.9.5 |  |  |  | Monitor Project Risks 5 | Project Manager
1.12.3.10 | 574 |  | 1.12.3.10 |  |  |  | Monitor Stakeholder Involvement Plan
1.12.3.10.1 | 575 |  | 1.12.3.10.1 |  |  |  | Monitor Stakeholder Involvement Plan 1 | Project Manager
1.12.3.10.2 | 576 |  | 1.12.3.10.2 |  |  |  | Monitor Stakeholder Involvement Plan 2 | Project Manager
1.12.3.10.3 | 577 |  | 1.12.3.10.3 |  |  |  | Monitor Stakeholder Involvement Plan 3 | Project Manager
1.12.3.10.4 | 578 |  | 1.12.3.10.4 |  |  |  | Monitor Stakeholder Involvement Plan 4 | Project Manager
1.12.3.10.5 | 579 |  | 1.12.3.10.5 |  |  |  | Monitor Stakeholder Involvement Plan 5 | Project Manager
1.12.3.11 | 580 |  | 1.12.3.11 |  |  |  | Monitor Data Management Plan
1.12.3.11.1 | 581 |  | 1.12.3.11.1 |  |  |  | Monitor Data Management Plan 1 | Project Manager
1.12.3.11.2 | 582 |  | 1.12.3.11.2 |  |  |  | Monitor Data Management Plan 2 | Project Manager
1.12.3.11.3 | 583 |  | 1.12.3.11.3 |  |  |  | Monitor Data Management Plan 3 | Project Manager
1.12.3.11.4 | 584 |  | 1.12.3.11.4 |  |  |  | Monitor Data Management Plan 4 | Project Manager
1.12.3.11.5 | 585 |  | 1.12.3.11.5 |  |  |  | Monitor Data Management Plan 5 | Project Manager
1.12.4 | 586 |  | 1.12.4 |  |  |  | Project Quality Assurance
1.12.4.1 | 587 |  | 1.12.4.1 |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) | QA Analyst
1.12.4.1.1 | 588 |  | 1.12.4.1.1 |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 1 | QA Analyst
1.12.4.1.2 | 589 |  | 1.12.4.1.2 |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 2 | QA Analyst
1.12.4.1.3 | 590 |  | 1.12.4.1.3 |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 3 | QA Analyst
1.12.4.1.4 | 591 |  | 1.12.4.1.4 |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 4 | QA Analyst
1.12.4.1.5 | 592 |  | 1.12.4.1.5 |  |  |  | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 5 | QA Analyst
1.12.4.2 | 593 |  | 1.12.4.2 |  |  |  | Track and Verify NC Closure
1.12.4.2.1 | 594 |  | 1.12.4.2.1 |  |  |  | Track and Verify NC Closure 1 | Project Manager
1.12.4.2.2 | 595 |  | 1.12.4.2.2 |  |  |  | Track and Verify NC Closure 22 | Project Manager
1.12.4.2.3 | 596 |  | 1.12.4.2.3 |  |  |  | Track and Verify NC Closure 23 | Project Manager
1.12.4.3 | 597 |  | 1.12.4.3 |  |  |  | Verify Closure of Review Defect found in Work Product Review(s)
1.12.4.3.1 | 598 |  | 1.12.4.3.1 |  |  |  | Verify Closure of Review Defect found in Work Product Review(s) 1 | QA Analyst
1.12.4.3.2 | 599 |  | 1.12.4.3.2 |  |  |  | Verify Closure of Review Defect found in Work Product Review(s) 21 | QA Analyst
1.12.4.3.3 | 600 |  | 1.12.4.3.3 |  |  |  | Verify Closure of Review Defect found in Work Product Review(s) 22 | QA Analyst
1.12.4.3.4 | 601 |  | 1.12.4.3.4 |  |  |  | Verify Closure of Review Defect found in Work Product Review(s) 23 | QA Analyst
1.12.4.4 | 602 |  | 1.12.4.4 |  |  |  | Review Supplier's Process
1.12.4.4.1 | 603 |  | 1.12.4.4.1 |  |  |  | Review Supplier's Process 1 | QA Analyst,Project Manager
1.12.4.4.2 | 604 |  | 1.12.4.4.2 |  |  |  | Review Supplier's Process 2 | QA Analyst,Project Manager
1.12.4.4.3 | 605 |  | 1.12.4.4.3 |  |  |  | Review Supplier's Process 3 | QA Analyst,Project Manager
1.12.4.4.4 | 606 |  | 1.12.4.4.4 |  |  |  | Review Supplier's Process 4 | QA Analyst,Project Manager
1.12.4.4.5 | 607 |  | 1.12.4.4.5 |  |  |  | Review Supplier's Process 5 | QA Analyst,Project Manager
1.12.5 | 608 |  | 1.12.5 |  |  |  | Configuration Management
1.12.5.1 | 609 |  | 1.12.5.1 |  |  |  | Update Change Register with Status of CR's | CM Lead
1.12.5.1.1 | 610 |  | 1.12.5.1.1 |  |  |  | Update Change Register with Status of CR's 1 | CM Lead
1.12.5.1.2 | 611 |  | 1.12.5.1.2 |  |  |  | Update Change Register with Status of CR's 2 | CM Lead
1.12.5.1.3 | 612 |  | 1.12.5.1.3 |  |  |  | Update Change Register with Status of CR's 3 | CM Lead
1.12.5.1.4 | 613 |  | 1.12.5.1.4 |  |  |  | Update Change Register with Status of CR's 4 | CM Lead
1.12.5.1.5 | 614 |  | 1.12.5.1.5 |  |  |  | Update Change Register with Status of CR's 5 | CM Lead
1.12.5.2 | 615 |  | 1.12.5.2 |  |  |  | Create Baselines of the CIs
1.12.5.2.1 | 616 |  | 1.12.5.2.1 |  |  |  | Create Baselines of the CIs 1 | CM Lead
1.12.5.2.2 | 617 |  | 1.12.5.2.2 |  |  |  | Create Baselines of the CIs 2 | CM Lead
1.12.5.2.3 | 618 |  | 1.12.5.2.3 |  |  |  | Create Baselines of the CIs 3 | CM Lead
1.12.5.2.4 | 619 |  | 1.12.5.2.4 |  |  |  | Create Baselines of the CIs 4 | CM Lead
1.12.5.3 | 620 |  | 1.12.5.3 |  |  |  | Generate Configuration Status Accounting Report
1.12.5.3.1 | 621 |  | 1.12.5.3.1 |  |  |  | Generate Configuration Status Accounting Report 1 | CM Lead
1.12.5.3.2 | 622 |  | 1.12.5.3.2 |  |  |  | Generate Configuration Status Accounting Report 2 | CM Lead
1.12.5.3.3 | 623 |  | 1.12.5.3.3 |  |  |  | Generate Configuration Status Accounting Report 12 | CM Lead
1.12.5.4 | 624 |  | 1.12.5.4 |  |  |  | Verify Backup and Disaster Recovery
1.12.5.4.1 | 625 |  | 1.12.5.4.1 |  |  |  | Verify Backup and Disaster Recovery 1 | CM Lead
1.12.5.4.2 | 626 |  | 1.12.5.4.2 |  |  |  | Verify Backup and Disaster Recovery 2 | CM Lead

## Site Deployment
WBS | Task Name | Resource Names
1 | Project Schedule for Site Deployment <Site Name>
1.1 | Understand Deployment Scope of the System | Site1 Deployment Manager
1.2 | Identify Site-Specific Gaps - <Site Name>
1.2.1 | Review Application & System Documentation | Site1 Deployment Manager
1.2.2 | Identify Infrastructure Changes | Site1 Deployment Manager
1.2.3 | Identify Security Gaps | Site1 Deployment Manager
1.2.4 | Identify Migration Gaps | Site1 Deployment Manager
1.2.5 | Document Site Specific Gap Analysis | Site1 Deployment Manager
1.3 | Site-Specific Gaps Analyzed and Docuemented
1.4 | Procure Supplier/Products for System Deployment at Site
1.4.1 | Engage Time and Material Resources | Site1 Deployment Manager,Senior Manager,WWP/Contract Manager
1.4.2 | Get Single Sourcing Justification Letter and Obtain Approval | Site1 Deployment Manager[30%],Senior Manager[30%]
1.4.3 | Procure Products | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.4 | Define Sourcing Requirements
1.4.4.1 | Determine Acquisition Type | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.4.2 | Establish Cross-Functional Team | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.4.3 | Define Requirements | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.4.4 | Create and Approve Acquisition Document | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.5 | Select Suppliers
1.4.5.1 | Develop RFP | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.5.2 | Develop Supplier evaluation criteria | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.5.3 | Identify potential suppliers | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.5.4 | Distribute proposals | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.5.5 | Evaluate proposals | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.5.6 | Approve Supplier Downselect | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.6 | Establish Agreement
1.4.6.1 | Develop Negotiation Strategy | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.6.2 | Negotiate Agreement | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.6.3 | Evaluate and select final supplier | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.6.4 | Create and approve agreement | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.6.5 | Communicate agreement | Site1 Deployment Manager,WWP/Contract Manager,SAM Analyst
1.5 | Prepare Site <1>
1.5.1 | Prepare Site for System Changes
1.5.1.1 | Prepare Site for Infrastructure Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.1.2 | Prepare Site for Security Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.1.3 | Prepare for Application Data Migration | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.2 | Create System Migration Plan for Site 1 | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.3 | Prepare Test Cases for the Site 1 | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.4 | Apply Infrastructure Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.5 | Apply Security Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.6 | Convert and Migrate Data | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.7 | Update System Documentation and Test Plans for Site1 | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.8 | Update Site Deployment Plan | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.5.9 | Conduct Test and Site Readiness Review | QA Analyst,Site1 Deployment Manager,Site1Test Manager,Senior Manager,System Owner,Site1 Lead
1.6 | Testing and Site Readiness Review Conducted for Site 1
1.7 | Testing of Site <1>
1.7.1 | Conduct System Testing at Site <1>
1.7.1.1 | Execute System Tests | Site1 Lead,Site1 Deployment Manager[20%],Site1 Deployment Team Member[20%]
1.7.1.2 | Log Defects and Issues | Site1 Test Manager
1.7.1.3 | Prepare System Test Summary Report (STSR) at End of Cycle | Site1 Test Manager
1.7.1.4 | Review System Test Summary Report | Site1 Test Manager
1.7.1.5 | Generate Final STSR | Site1 Test Manager,Site1 Deployment Manager[20%]
1.7.1.6 | Plan Next Test Cycle | Site1 Test Manager
1.7.1.7 | Fix Defects and Issues | Site1 Deployment Manager
1.7.1.8 | Install and Configure System | Site1 Deployment Manager
1.7.1.9 | Verify System Installation and Configuration | Site1 Test Manager[30%],Site1 Deployment Manager,Site1 Lead[30%]
1.7.1.10 | Execute System Tests | Site1 Lead,Site1 Deployment Manager[20%],Site1 Deployment Team Member[20%]
1.7.1.11 | Verify Test Results | Site1 Deployment Team Member,Site1 Lead
1.7.2 | Conduct Acceptance Testing Readiness Review - Site <1>
1.7.2.1 | Setup Test Environment at Site<1>
1.7.2.1.1 | Install Test Environment | Site1 Test Manager
1.7.2.1.2 | Apply Infrastructure Changes | Site1 Lead,Site1 Test Manager
1.7.2.1.3 | Apply Security Changes | Site1 Test Manager,Site1 Lead
1.7.2.1.4 | Convert & Migrate Data | Site1 Test Manager,Site1 Lead
1.7.2.1.5 | Perform Checks to Verify Test Environment | Site1 Test Manager
1.7.2.1.6 | Fix Gaps Related to Test Environment | Site1 Test Manager
1.7.2.1.7 | Verify / Audit Test Environment | Site1 Lead[30%],Site1 Deployment Manager,Site1 Test Manager[30%]
1.7.2.2 | Test Build & Installation of System at Site <>
1.7.2.2.1 | Fix Defects & Issues | Site1 Deployment Team Member[20%],Site1 Deployment Manager[20%],Site1 Lead
1.7.2.2.2 | Update Installation & System Documentation | Site1 Deployment Team Member[20%],Site1 Lead,Site1 Deployment Manager[20%]
1.7.2.2.3 | Verify Installation & System Documentation | Site1 Test Manager
1.7.2.2.4 | Obtain Approval & Check In System Documentation, Installation Guide & Source | CM Lead,Site1 Test Manager[30%],Site1 Deployment Manager
1.7.2.2.5 | Install & Configure Application | Site1Test Manager,Site1 Lead[30%]
1.7.2.3 | Conduct Acceptance Testing Readiness Review Meeting of System at Site <> | Senior Manager,System Owner,End User,Site1 Lead,Site1 Test Manager,QA Analyst,Piot Site Deployment Manager
1.7.3 | Conduct Acceptance Testing at Site <1>
1.7.3.1 | Execute User Acceptance Tests | Site1 Deployment Manager[30%],Site1 Deployment Team Member[30%],End User
1.7.3.2 | Verify Test Results | Site1 Deployment Manager
1.7.3.3 | Log Defects & Issues | End User[30%],Site1 Deployment Manage
1.7.3.4 | Prepare Test Summary Report at End of Cycle | Site1 Deployment Manager
1.7.3.5 | Review Test Summary Report | Site1 Deployment Manage,End User[30%]
1.7.3.6 | Generate Final Test Summary Report | Site1 Deployment Manager
1.7.3.7 | Sign-off on User Acceptance Tests | Site1 Deployment Manage,End User[30%]
1.7.4 | Acceptance Testing Conducted for Site <1>
1.7.5 | Plan Next Cycle | Site1 Deployment Team Member[20%],Site1 Lead,Site1 Deployment Manager[20%]
1.7.6 | Analyze Defects & Change Requests at Site <1> | End User[30%],Site1 Deployment Manager,Site1 Test Manager[30%],Site1 Lead[30%]
1.7.7 | Verify Production Readiness at Site <1> | Site1 Lead,Site1 Test Manager
1.8 | Site 1 Tested and Ready for System Migration
1.9 | Deploy at Site <1>
1.9.1 | Migrate to New System at at Site <1>
1.9.1.1 | Execute Migration | Site1 Lead
1.9.1.2 | Perform Checks to Verify Migration | Site1 Deployment Manager[30%],Site1 Lead
1.9.1.3 | Check Contingency Plan for Alternative(s) | Site1 Deployment Manager,Site1 Lead
1.9.1.4 | Modify System Environment or Components | Site1 Lead
1.9.1.5 | Execute Back out Plan | Site1 Deployment Manager
1.9.1.6 | Communicate To Stakeholders | Site1 Manager,Senior Manager,Site1 Deployment Manager
1.9.1.7 | Communicate Deployment Status | System Deployment Manager
1.9.2 | Migrated to New System at at Site <1>
1.9.3 | Update Generic Site Deployment Materials & System Documentation | Site1 Deployment Manage,System Deployment Manager
1.9.4 | Transition to Operations at at Site <1>
1.9.4.1 | Support New System | Site1 Deployment Manager,Site1 Deployment Team Member
1.9.4.2 | Transfer Ownership to System Owner | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.9.4.3 | Archive System Documentation, Training Material & Application/System Components | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.9.4.4 | Train Operations Team | Site1 Deployment Manager,System Owner,Site1 Operations & Support Team
1.9.5 | De-Install Legacy System at at Site <1> | Site1 Deployment Manager
1.9.6 | Legacy System De-Installed at Site <1>
1.1 | System Deployed at Site <1>
1.11 | Project Support Activities
1.11.1 | Manage Requirements
1.11.1.1 | Understand Change in Requirements
1.11.1.2 | Perform Detailed Impact Analysis
1.11.1.3 | Raise Requirements Change Request (RCR) Form
1.11.1.4 | Review through Requirements Change Control Board (RCCB)
1.11.1.5 | Re-Estimate & Re-Plan the Project
1.11.1.6 | Obtain Approval from Senior Manager for Change in Cost & Schedule | Senior Manager,Site1 Deployment Manager[30%]
1.11.1.7 | Update & Baseline Project Plan
1.11.1.8 | Communicate Changes in Project Plan
1.11.2 | Change Control
1.11.2.1 | Review Impact on CM Repository | CM Lead
1.11.2.2 | Review Impact on Work Products | Site1 Deployment Manager
1.11.2.3 | Update Change Register | CM Lead
1.11.2.4 | Review through Change Control Board (CCB) | Site1 Deployment Manager
1.11.2.5 | Update Change Register
1.11.2.6 | Update Change Register with Closure Details
1.11.3 | Project Monitoring and Control
1.11.3.1 | Monitor Supplier Status
1.11.3.1.1 | Monitor Supplier Status 1 | Site1 Deployment Manager
1.11.3.1.2 | Monitor Supplier Status 2 | Site1 Deployment Manager
1.11.3.1.3 | Monitor Supplier Status 3 | Site1 Deployment Manager
1.11.3.1.4 | Monitor Supplier Status 4 | Site1 Deployment Manager
1.11.3.1.5 | Monitor Supplier Status 5 | Site1 Deployment Manager
1.11.3.2 | Update Project Log , Project Plan and Project Schedule | Site1 Deployment Manager
1.11.3.2.1 | Update Project Log , Project Plan and Project Schedule 1 | Site1 Deployment Manager
1.11.3.2.2 | Update Project Log , Project Plan and Project Schedule 2 | Site1 Deployment Manager
1.11.3.2.3 | Update Project Log , Project Plan and Project Schedule 3 | Site1 Deployment Manager
1.11.3.2.4 | Update Project Log , Project Plan and Project Schedule 4 | Site1 Deployment Manager
1.11.3.2.5 | Update Project Log , Project Plan and Project Schedule 5
1.11.3.2.6 | Update Project Log , Project Plan and Project Schedule 6
1.11.3.2.7 | Update Project Log , Project Plan and Project Schedule 7
1.11.3.2.8 | Update Project Log , Project Plan and Project Schedule 8
1.11.3.2.9 | Update Project Log , Project Plan and Project Schedule 9
1.11.3.2.10 | Update Project Log , Project Plan and Project Schedule 10
1.11.3.2.11 | Update Project Log , Project Plan and Project Schedule 11
1.11.3.2.12 | Update Project Log , Project Plan and Project Schedule 12
1.11.3.3 | Provide Measurement Results Based on SDP-21 Metrics | Site1 Deployment Manager
1.11.3.3.1 | Submit SDP-21 Standard Metrics
1.11.3.3.1.1 | Submit SDP-21 Standard Metrics 1
1.11.3.3.1.2 | Submit SDP-21 Standard Metrics 2
1.11.3.3.1.3 | Submit SDP-21 Standard Metrics 3
1.11.3.3.1.4 | Submit SDP-21 Standard Metrics 4
1.11.3.3.1.5 | Submit SDP-21 Standard Metrics 5
1.11.3.4 | Update Project Tracking System (PTS)
1.11.3.4.1 | Update Project Tracking System (PTS) 1
1.11.3.4.2 | Update Project Tracking System (PTS) 2
1.11.3.4.3 | Update Project Tracking System (PTS) 3
1.11.3.4.4 | Update Project Tracking System (PTS) 4
1.11.3.4.5 | Update Project Tracking System (PTS) 5
1.11.3.5 | Conduct Milestone Reviews
1.11.3.6 | Conduct Senior Management Review (SMR) | Site1 Deployment Manager
1.11.3.6.1 | Conduct SMR meeting for the Project
1.11.3.6.1.1 | Conduct SMR meeting for the Project 1
1.11.3.6.1.2 | Conduct SMR meeting for the Project 2
1.11.3.6.1.3 | Conduct SMR meeting for the Project 3
1.11.3.6.1.4 | Conduct SMR meeting for the Project 4
1.11.3.6.1.5 | Conduct SMR meeting for the Project 5
1.11.3.7 | Conduct Progress Review Meetings | Site1 Deployment Manager
1.11.3.7.1 | Conduct Progress Review Meetings 1 | Site1 Deployment Manager
1.11.3.7.2 | Conduct Progress Review Meetings 2 | Site1 Deployment Manager
1.11.3.7.3 | Conduct Progress Review Meetings 3 | Site1 Deployment Manager
1.11.3.7.4 | Conduct Progress Review Meetings 4 | Site1 Deployment Manager
1.11.3.7.5 | Conduct Progress Review Meetings 5 | Site1 Deployment Manager
1.11.3.7.6 | Conduct Review with Stakeholders | Site1 Deployment Manager
1.11.3.8 | Monitor Project Plan and Schedule
1.11.3.8.1 | Monitor Project Plan and Schedule 1
1.11.3.8.2 | Monitor Project Plan and Schedule 2
1.11.3.8.3 | Monitor Project Plan and Schedule 3
1.11.3.8.4 | Monitor Project Plan and Schedule 4
1.11.3.8.5 | Monitor Project Plan and Schedule 5
1.11.3.8.6 | Monitor Project Plan and Schedule 6
1.11.3.8.7 | Monitor Project Plan and Schedule 7
1.11.3.8.8 | Monitor Project Plan and Schedule 8
1.11.3.8.9 | Monitor Project Plan and Schedule 9
1.11.3.8.10 | Monitor Project Plan and Schedule 10
1.11.3.9 | Monitor Project Risks
1.11.3.9.1 | Monitor Project Risks 1
1.11.3.9.2 | Monitor Project Risks 2
1.11.3.9.3 | Monitor Project Risks 3
1.11.3.9.4 | Monitor Project Risks 4
1.11.3.9.5 | Monitor Project Risks 5
1.11.3.10 | Monitor Stakeholder Involvement Plan
1.11.3.10.1 | Monitor Stakeholder Involvement Plan 1
1.11.3.10.2 | Monitor Stakeholder Involvement Plan 2
1.11.3.10.3 | Monitor Stakeholder Involvement Plan 3
1.11.3.10.4 | Monitor Stakeholder Involvement Plan 4
1.11.3.10.5 | Monitor Stakeholder Involvement Plan 5
1.11.3.11 | Monitor Data Management Plan
1.11.3.11.1 | Monitor Data Management Plan 1
1.11.3.11.2 | Monitor Data Management Plan 2
1.11.3.11.3 | Monitor Data Management Plan 3
1.11.3.11.4 | Monitor Data Management Plan 4
1.11.3.11.5 | Monitor Data Management Plan 5
1.11.4 | Project Quality Assurance
1.11.4.1 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) | QA Analyst
1.11.4.1.1 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 1
1.11.4.1.2 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 2
1.11.4.1.3 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 3
1.11.4.1.4 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 4
1.11.4.1.5 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 5
1.11.4.2 | Track and Verify NC Closure
1.11.4.2.1 | Track and Verify NC Closure 1
1.11.4.2.2 | Track and Verify NC Closure 22
1.11.4.2.3 | Track and Verify NC Closure 23
1.11.4.3 | Verify Closure of Review Defect found in Work Product Review(s)
1.11.4.3.1 | Verify Closure of Review Defect found in Work Product Review(s) 1
1.11.4.3.2 | Verify Closure of Review Defect found in Work Product Review(s) 21
1.11.4.3.3 | Verify Closure of Review Defect found in Work Product Review(s) 22
1.11.4.3.4 | Verify Closure of Review Defect found in Work Product Review(s) 23
1.11.4.4 | Review Supplier's Process | QA Analyst
1.11.4.4.1 | Review Supplier's Process 1
1.11.4.4.2 | Review Supplier's Process 2
1.11.4.4.3 | Review Supplier's Process 3
1.11.4.4.4 | Review Supplier's Process 4
1.11.4.4.5 | Review Supplier's Process 5
1.11.5 | Configuration Management
1.11.5.1 | Update Change Register with Status of CR's | CM Lead
1.11.5.2 | Create Baselines of the CIs | CM Lead
1.11.5.3 | Generate Configuration Status Accounting Report | CM Lead
1.11.5.4 | Verify Backup and Disaster Recovery | CM Lead

## Enhancement
WBS | Task Name | Resource Names
1 | Project Schedule for <PTS-Id. Project Name>
1.1 | Project Start
1.2 | Plan
1.2.1 | Develop Plan for Plan Phase | Project Manager
1.2.2 | Develop Process Design | Requirements Analyst[50%],Project Manager[50%],Process Engineer
1.2.3 | Develop Project Charter
1.2.3.1 | Define Project Scope
1.2.3.2 | Complete Project Charter (PC) Document
1.2.4 | Estimate Effort for Define Phase | Requirements Analyst,Project Manager
1.2.5 | Develop Plan for Define Phase
1.2.5.1 | Develop and Release RFI | WWP/Contract Manager,Project Manager
1.2.5.2 | Orient QA with Project Background | Project Manager,QA Analyst
1.2.5.3 | Document Preliminary Project Plan | Project Manager
1.2.5.3.1 | Identify Customer Deliverables | Project Manager,Project Team
1.2.5.3.2 | Identify Reusable Components | Project Manager[50%]
1.2.5.3.3 | Orient QA with Project Background | QA Analyst,Project Manager
1.2.5.3.4 | Tailor SDP-21 for Project Characteristics | Project Manager,QA Analyst
1.2.5.3.5 | Develop Peer Review Plan | Project Manager
1.2.5.3.6 | Identify Resources, Tools and Training Needs | Project Manager,Project Team
1.2.5.3.7 | Document CM Plan | Project Manager,CM Lead
1.2.5.3.8 | Document Project Data Management Plan | Project Manager,CM Lead
1.2.5.3.9 | Document QA Plan | Project Manager,QA Analyst
1.2.5.3.10 | Document Stakeholder(s) Involvement Plan | Project Manager,Project Team,Senior Manager
1.2.5.3.11 | Document Project Training Plan | Project Manager,Project Team
1.2.5.3.12 | Identify Critical Dependencies and Issues | Project Manager
1.2.5.3.13 | Asess and Create Procurement Plan for acquiring Supplier/Products for System Deployment | Project Manager,Project Team
1.2.5.3.14 | Refine and Optimize Project Schedule | Project Manager
1.2.5.3.15 | Document Prelimnary Project Plan | Project Manager
1.2.5.3.16 | Check for Consistency in PQP, QA Plan, Risk Mgmt, CM Plan and Schedule | Project Manager
1.2.5.3.17 | Ensure Review of Project Plan
1.2.5.3.18 | Update Project Plan | Project Manager
1.2.5.3.19 | Review Project Commitments | Project Manager,Senior Manager
1.2.5.3.20 | Obtain Approval and Baseline Project Plan | Project Manager[30%],CM Lead[30%]
1.2.5.3.21 | Communicate Project Plan | Project Manager
1.2.5.3.22 | Orient Project Team on Project Plan | Project Manager
1.2.5.4 | Procure Resources for Define Phase
1.2.5.4.1 | Engage Time and Material Resources | Project Manager,PMO Prg. Mgr.,WWP/Contract Manager
1.2.5.4.2 | Allocate Resources for Define Phase | Project Manager
1.2.5.4.3 | Develop Initial Version of Supplier Management Plan
1.2.5.4.4 | Develop RFP and Evaluation Criteria | Project Manager
1.2.5.4.5 | Distribute RFP to Suppliers | WWP/Contract Manager
1.2.5.4.6 | Evaluate Proposals | Project Manager
1.2.5.4.7 | Approve Supplier(s) Down-Select | Senior Manager,Project Manager
1.2.5.4.8 | Negotiate Agreement and Select Final Supplier
1.2.5.4.9 | Get Single Sourcing Justification Letter and Obtain Approval | CM Lead[30%],Senior Manager[30%],Project Manager[30%]
1.2.6 | Conduct Plan Tollgate
1.2.6.1 | Update Plan(s) for Define, Construct, Test and Deploy Phases | Project Manager,CM Lead,QA Analyst
1.2.6.2 | Request Tollgate Review | Project Manager[30%]
1.2.6.3 | Update Business Case | Project Manager[30%]
1.2.6.4 | Prepare for Project Tollgate Review | Stakeholder[30%]
1.2.6.5 | Review Plan(s) for Define, Construct, Test and Deploy Phases | PMO Prg. Mgr.[50%]
1.2.6.6 | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.2.6.7 | Conduct CM Audits | QA Analyst
1.2.6.8 | Prepare Tollgate Review Report | Project Manager[20%]
1.2.6.9 | Update and Communicate Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.2.6.10 | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.2.6.11 | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.3 | Plan Tollgate Conducted
1.4 | Define
1.4.1 | Communicate Final Supplier Management Plan
1.4.2 | Develop Business Requirements
1.4.2.1 | Derive Business Requirements | Senior Manager[30%],Project Manager[50%],Requirements Analyst[50%]
1.4.2.2 | Complete Business Requirements Document (BRD) | Project Manager[20%],Requirements Analyst
1.4.2.3 | Check for Consistency with Process Design Summary | Project Manager[20%],Requirements Analyst[30%],Process Engineer
1.4.2.4 | Ensure Review of BRD | Project Manager,QA Analyst,Requirements Analyst[50%],Process Engineer
1.4.2.5 | Peer Review
1.4.2.5.1 | Conduct Review | Project Manager
1.4.2.5.2 | Identify Reviewers | Project Manager
1.4.2.5.3 | Schedule Review | Project Manager
1.4.2.5.4 | Review and Log Feedback | Project Manager
1.4.2.5.5 | Fix Defects Detected from Offline Review | Project Manager
1.4.2.5.6 | Verify Closure of Defects | Project Manager
1.4.2.5.7 | Document and Communicate Review Results | Project Manager
1.4.2.5.8 | Approve for Baseline | Project Manager
1.4.2.6 | Obtain Approval and Baseline BRD | CM Lead[30%],Process Engineer,Project Manager[30%]
1.4.3 | Business Requirements Developed
1.4.4 | Develop System Requirements
1.4.4.1 | Elicit Requirements | Requirements Analyst
1.4.4.2 | Develop Use Cases | Requirements Analyst
1.4.4.3 | Derive System Requirements | Project Manager[30%],Requirements Analyst
1.4.4.4 | Prioritize System Requirements | Process Engineer[30%],Requirements Analyst,Project Manager
1.4.4.5 | Obtain Agreement for Requirements | Process Engineer,Project Manager,Requirements Analyst[30%]
1.4.4.6 | Update Business Requirements Document (BRD) | Project Manager[50%],Requirements Analyst
1.4.4.7 | Manage Requirements
1.4.4.7.1 | Understand Change in Requirements | Project Manager[50%],Requirements Analyst
1.4.4.7.2 | Perform Detailed Impact Analysis | Project Manager[50%],Requirements Analyst
1.4.4.7.3 | Complete Requirements Change Request (RCR) Form | Project Manager[50%],Requirements Analyst
1.4.4.7.4 | Review through Requirements Change Control Board | Project Manager[50%],Requirements Analyst
1.4.4.7.5 | Re-plan the Project
1.4.4.7.5.1 | Re-estimate and Re-plan | Project Manager[50%],Requirements Analyst
1.4.4.7.5.2 | Derive New Schedule | Project Manager[50%],Requirements Analyst
1.4.4.7.5.3 | Communicate Changes in Project Plan | Project Manager[50%],Requirements Analyst
1.4.4.7.6 | Update RCR Form | Project Manager[50%],Requirements Analyst
1.4.4.7.7 | Update Change Register | Project Manager[50%],Requirements Analyst
1.4.4.7.8 | Communicate to Requirements Providers | Project Manager[50%],Requirements Analyst
1.4.4.7.9 | Incorporate Changes
1.4.4.7.9.1 | Identify Author | Project Manager[50%],Requirements Analyst
1.4.4.7.9.2 | Check-Out Configuration Items (CIs) | Project Manager[50%],Requirements Analyst
1.4.4.7.9.3 | Incorporate Changes in Work Products | Project Manager[50%],Requirements Analyst
1.4.4.8 | Check for Consistency in Requirements Work Product | Project Manager[50%],Requirements Analyst
1.4.4.9 | Update and Finalize System Requirements Specification (SRS) | Project Manager[50%],Requirements Analyst
1.4.4.10 | Update Requirements Traceability Matrix (RTM) | Requirements Analyst
1.4.4.11 | Ensure Review of BRD, SRS and RTM | QA Analyst,Process Engineer,Project Manager[50%],Requirements Analyst
1.4.4.12 | Peer Review
1.4.4.12.1 | Conduct Offline Review
1.4.4.12.2 | Identify Reviewers
1.4.4.12.3 | Schedule Review
1.4.4.12.4 | Review and Log Feedback
1.4.4.12.5 | Fix Defects Detected from Offline Review
1.4.4.12.6 | Verify Closure of Defects
1.4.4.12.7 | Document and Communicate Review Results
1.4.4.12.8 | Approve for Baseline
1.4.4.13 | Follow up for Review Completion to obtain agreement on requirements by All Reqs Providers | Project Manager[50%],Requirements Analyst
1.4.4.14 | Obtain Approval and Baseline BRD, SRS and RTM | CM Lead[30%],Process Engineer,Project Manager,Requirements Analyst[30%]
1.4.5 | Develop Architectural Design | Project Architect
1.4.5.1 | Design System Architecture | Project Architect
1.4.5.2 | Develop Logical Data Model (LDM) | Project Data Architect
1.4.5.3 | Present to Architectural Review Committee | Project Architect,Project Manager
1.4.5.4 | Update Architectural Design (AD) Document | Project Architect
1.4.5.5 | Create IT Standards Bill of Material (BoM) | Project Architect,Project Manager
1.4.5.6 | Ensure Review of AD and BoM | Project Manager
1.4.5.7 | Peer Review
1.4.5.7.1 | Conduct Review | Project Manager
1.4.5.7.2 | Identify Reviewers | Project Manager
1.4.5.7.3 | Schedule Review | Project Manager
1.4.5.7.4 | Review and Log Feedback | Project Manager
1.4.5.7.5 | Fix Defects Detected from Offline Review | Project Manager
1.4.5.7.6 | Verify Closure of Defects | Project Manager
1.4.5.7.7 | Document and Communicate Review Results | Project Manager
1.4.5.7.8 | Approve for Baseline | Project Manager
1.4.5.8 | Obtain Approval and Baseline AD and BoM | Project Manager,PIO Achitect
1.4.6 | Architectural Design Developed
1.4.7 | Develop Deployment Strategy
1.4.7.1 | Document Deployment Strategy
1.4.8 | Initial System Deployment Plan (ver 1.0) containing Deployment Strategy created
1.4.9 | Conduct Bid Evaluations
1.4.9.1 | Plan for Product Acquisition | Project Manager,Requirements Analyst
1.4.9.2 | Plan for Supplier Sourcing (Construct through Deploy) | Project Manager,Senior Manager
1.4.9.3 | Develop Initial Version of Supplier Management Plan
1.4.9.4 | Develop RFP and Evaluation Criteria | Project Manager
1.4.9.5 | Distribute RFP to Suppliers | WWP/Contract Manager
1.4.9.6 | Evaluate Proposals | Project Manager
1.4.9.7 | Approve Supplier(s) Down-Select | Senior Manager,Project Manager
1.4.9.8 | Negotiate Agreement and Select Final Supplier
1.4.9.9 | Get Single Sourcing Justification Letter and Obtain Approval | CM Lead[30%],Senior Manager[30%],Project Manager[30%]
1.4.10 | Develop Final Project Plan
1.4.10.1 | Tailor SDP-21 for Project Characteristics | Project Manager,QA Analyst
1.4.10.2 | Develop and Record Estimates
1.4.10.2.1 | Identify Estimation Team | PMO Prg. Mgr.[20%],Project Manager
1.4.10.2.2 | Identify Estimation Method | QA Analyst[10%],PMO Prg. Mgr.[10%],Project Manager
1.4.10.2.3 | Estimate Size, Effort, Cost and Forecast Dates
1.4.10.2.4 | Ensure Review and Validation of Cost Estimates | Senior Manager[30%],Project Manager,PMO Prg. Mgr.[50%]
1.4.10.2.5 | Prepare Estimation Report | Project Manager
1.4.10.3 | Develop Test Strategy | Project Manager
1.4.10.4 | Develop Peer Review Plan | Project Manager
1.4.10.5 | Update Product Quality Plan (Level 4) | QA Analyst[30%],Project Manager
1.4.10.5.1 | Set Project Performance Objectives (Level 4) | Project Manager
1.4.10.5.2 | Derive Objectives for Life Cycle Phases (Level 4) | Project Manager
1.4.10.5.3 | Review of Process Performance Capabilities | QA Analyst[30%],Project Manager[50%],IO SEPG Manager
1.4.10.5.4 | Review Product Quality Plan (Level 4) | Project Manager[50%],QA Analyst[30%],IO SEPG Manager
1.4.10.5.5 | Obtain Approval and Baseline PQP (Level 4) | QA Analyst[30%],Project Manager[50%],IO SEPG Manager
1.4.10.6 | Identify Resources, Tools and Training Needs | Project Manager,Project Team
1.4.10.7 | Document CM Plan | Project Manager,CM Lead
1.4.10.8 | Document Project Data Management Plan | Project Manager,CM Lead
1.4.10.9 | Document QA Plan | Project Manager,QA Analyst
1.4.10.10 | Document Stakeholder(s) Involvement Plan | Project Manager,Project Team,Senior Manager
1.4.10.11 | Document Project Training Plan | Project Manager,Project Team
1.4.10.12 | Identify Critical Dependencies and Issues | Project Manager
1.4.10.13 | Asess and Create Procurement Plan for acquiring Supplier/Products for System Deployment | Project Manager,Project Team
1.4.10.14 | Refine and Optimize Project Schedule | Project Manager
1.4.10.15 | Document Prelimnary Project Plan | Project Manager
1.4.10.16 | Check for Consistency in PQP, QA Plan, Risk Mgmt, CM Plan and Schedule | Project Manager
1.4.11 | Ensure Review of Project Plan
1.4.11.1 | Identify Reviewers
1.4.11.2 | Schedule Review
1.4.11.3 | Review and Log Feedback
1.4.11.4 | Fix Defects Detected from Review
1.4.11.5 | Verify Closure of Defects
1.4.11.6 | Document and Communicate Review Results
1.4.12 | Update Project Plan | Project Manager
1.4.13 | Review Project Commitments | Project Manager,Senior Manager
1.4.14 | Obtain Approval and Baseline Project Plan | Project Manager[30%],CM Lead[30%]
1.4.15 | Communicate Project Plan | Project Manager
1.4.16 | Orient Project Team on Project Plan | Project Manager
1.4.17 | Conduct Define Tollgate
1.4.17.1 | Update Plan(s) for Construct, Test and Deploy Phases | Project Manager,CM Lead,QA Analyst
1.4.17.2 | Request Tollgate Review | Project Manager[30%]
1.4.17.3 | Update Business Case | Project Manager[30%]
1.4.17.4 | Prepare for Project Tollgate Review | Stakeholder[30%]
1.4.17.5 | Review Plan(s) for Construct, Test and Deploy Phases | PMO Prg. Mgr.[50%]
1.4.17.6 | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.4.17.7 | Conduct CM Audits | QA Analyst
1.4.17.8 | Prepare Define Tollgate Review Report | Project Manager[20%]
1.4.17.9 | Update and Communicate Define Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.4.17.10 | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.4.17.11 | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.5 | Define Tollgate Conducted
1.6 | Construct
1.6.1 | Communicate Final Supplier Management Plan
1.6.2 | Conduct Construct Phase Kick-Off | Supplier,Project Manager
1.6.3 | Construct Phase Kick-Off Conducted
1.6.4 | Develop Detailed Design
1.6.4.1 | Develop Detailed Architecture | Supplier,Project Architect
1.6.4.2 | Identify Product Components and Interfaces | Supplier,Project Architect[30%]
1.6.4.3 | Develop and Analyze Design Alternatives | Project Architect,Supplier
1.6.4.4 | Develop Operational Design
1.6.4.5 | Conduct Detail Design Review | Supplier,Project Architect
1.6.4.6 | Document System Design Document (SDD) | Supplier
1.6.4.7 | Update Requirements Traceability Matrix (RTM) | Project Architect[50%],Supplier
1.6.4.8 | Check for Consistency in Work Product | Project Manager,Project Architect
1.6.4.9 | Review System Design Document | Project Manager,Supplier[50%]
1.6.4.10 | Obtain Approval and Baseline SDD | Supplier[30%],Project Manager,CM Lead[30%]
1.6.4.11 | Develop Physical Data Model (PDM) | DBA Supplier,Project Manager
1.6.5 | Develop Test Plans
1.6.5.1 | Develop User Acceptance Test Plan (UATP)
1.6.5.1.1 | Identify Pre-Production Environment Requirements
1.6.5.1.2 | Identify Test Data Requirements for User Acceptance Testing
1.6.5.1.3 | Develop Schedule for User Acceptance Testing | Supplier
1.6.5.1.4 | Document Defect and Problem Reporting Procedures | Project Manager,Supplier[50%]
1.6.5.1.5 | Document User Acceptance Test Plan (UATP)
1.6.5.1.6 | Ensure Review of UATP
1.6.5.1.6.1 | Identify Reviewers
1.6.5.1.6.2 | Schedule Review
1.6.5.1.6.3 | Review and Log Feedback
1.6.5.1.6.4 | Fix Defects Detected from Review
1.6.5.1.6.5 | Verify Closure of Defects
1.6.5.1.6.6 | Document and Communicate Review Results
1.6.5.2 | Obtain Approval and Baseline UATP | CM Lead[30%],Project Manager,Test Manager,Supplier[30%]
1.6.5.3 | Develop Acceptance Test Cases
1.6.5.3.1 | Document User Acceptance Test (UAT) Cases
1.6.5.3.2 | Update UAT Case References in RTM
1.6.5.3.3 | Ensure Review of UAT Cases
1.6.5.3.3.1 | Identify Reviewers
1.6.5.3.3.2 | Schedule Review
1.6.5.3.3.3 | Review and Log Feedback
1.6.5.3.3.4 | Fix Defects Detected from Review
1.6.5.3.3.5 | Verify Closure of Defects
1.6.5.3.3.6 | Document and Communicate Review Results
1.6.5.3.4 | Obtain Approval and Baseline Acceptance Test Cases | Project Manager,CM Lead[30%]
1.6.5.3.5 | Document Non-Functional Test Cases
1.6.5.3.6 | Update Non-Functional Test Case References in Requirements Traceability Matrix (RTM)
1.6.5.3.7 | Ensure Review of Non-Functional Test Cases
1.6.5.3.7.1 | Identify Reviewers
1.6.5.3.7.2 | Schedule Review
1.6.5.3.7.3 | Review and Log Feedback
1.6.5.3.7.4 | Fix Defects Detected from Review
1.6.5.3.7.5 | Verify Closure of Defects
1.6.5.3.7.6 | Document and Communicate Review Results
1.6.5.4 | Develop System Test Plan (STP)
1.6.5.4.1 | Identify Test Environment Requirements
1.6.5.4.2 | Identify Test Data Requirements for System Testing
1.6.5.4.3 | Develop Schedule for System Testing
1.6.5.4.4 | Document System Test Plan (STP)
1.6.5.5 | Obtain Approval and Baseline STP | Supplier[30%],Test Manager,Project Manager,CM Lead[30%]
1.6.5.6 | Identify and Document System Test Cases | Supplier
1.6.6 | Complete System Deployment Plan
1.6.6.1 | Develop Training Plan for System Deployment
1.6.6.2 | Develop Pilot Deployment Plan
1.6.6.2.1 | Develop Security Plan
1.6.6.2.2 | Develop Data Conversion and Load Plan
1.6.6.2.3 | Develop Site Deployment Schedule
1.6.6.2.4 | Develop Test Plans for the Site
1.6.6.2.5 | Develop Operations, Maintenance and Support Plan
1.6.6.2.6 | Develop Application Disaster Recovery Plan for the Site
1.6.6.2.7 | Document Site Deployment Plan (SDP)
1.6.6.2.8 | Review Site Deployment Plan
1.6.6.2.9 | Obtain Approval and Baseline SDP
1.6.6.3 | Develop Site Deployment Plan (SDP)
1.6.6.3.1 | Develop Security Plan
1.6.6.3.2 | Develop Data Conversion and Load Plan
1.6.6.3.3 | Develop Site Deployment Schedule
1.6.6.3.4 | Develop Test Plans for the Site
1.6.6.3.5 | Develop Operations, Maintenance and Support Plan
1.6.6.3.6 | Develop Application Disaster Recovery Plan for the Site
1.6.6.3.7 | Document Site Deployment Plan (SDP)
1.6.6.3.8 | Review Site Deployment Plan
1.6.6.3.9 | Obtain Approval and Baseline SDP
1.6.6.4 | Develop System Deployment Schedule
1.6.6.5 | Document System Deployment Plan (DP)
1.6.6.6 | Check for Consistency with SDP(s)
1.6.6.7 | Ensure Review System Deployment Plan
1.6.6.7.1 | Identify Reviewers
1.6.6.7.2 | Schedule Review
1.6.6.7.3 | Review and Log Feedback
1.6.6.7.4 | Fix Defects Detected from Review
1.6.6.7.5 | Verify Closure of Defects
1.6.6.7.6 | Document and Communicate Review Results
1.6.6.8 | Obtain Approval and Baseline DP
1.6.7 | System Deployment Plan Completed
1.6.8 | Code and Unit Test | Supplier
1.6.8.1 | Develop Source Code and Conduct Unit Testing
1.6.8.2 | Update Requirements Traceability Matrix (RTM)
1.6.8.3 | Develop Integration Test Cases
1.6.9 | Configure, Integrate and Deliver System | Supplier
1.6.9.1 | Integrate and Build the System
1.6.9.2 | Configure the System
1.6.9.3 | Conduct Integration Testing
1.6.9.4 | Update Requirements Traceability Matrix (RTM)
1.6.9.5 | Develop System Documentation and Training Material for the System
1.6.9.6 | Deliver the System
1.6.10 | Conduct System Testing Readiness Review
1.6.10.1 | Set Up Test Environment
1.6.10.1.1 | Install Test Environment
1.6.10.1.2 | Apply Infrastructure Changes
1.6.10.1.3 | Apply Security Changes
1.6.10.1.4 | Convert and Migrate Data
1.6.10.1.5 | Verify Test Environment
1.6.10.1.6 | Verify and Audit Test Environment
1.6.10.1.7 | Fix Gaps Related to Test Environment
1.6.10.2 | Test Build and Installation of the System
1.6.10.2.1 | Verify Installation and System Documentation
1.6.10.2.2 | Fix Defects and Issues
1.6.10.2.3 | Update Installation and System Documentation
1.6.10.2.4 | Build the System
1.6.10.2.5 | Install and Configure the System
1.6.10.2.6 | Obtain Approval and Check-In SD, SC and Installation Guide | CM Lead[30%]
1.6.10.3 | Conduct System Testing Readiness Review Meeting
1.6.10.4 | Conduct Release Audit
1.6.11 | Conduct Construct Tollgate
1.6.11.1 | Update Plan(s) for Test and Deploy Phases | Project Manager,CM Lead,QA Analyst
1.6.11.2 | Request Tollgate Review | Project Manager[30%]
1.6.11.3 | Update Business Case | Project Manager[30%]
1.6.11.4 | Prepare for Project Tollgate Review | Stakeholder[30%]
1.6.11.5 | Review Plan(s) for Test and Deploy Phases | PMO Prg. Mgr.[50%]
1.6.11.6 | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.6.11.7 | Conduct CM Audits | QA Analyst
1.6.11.8 | Prepare Construct Tollgate Review Report | Project Manager[20%]
1.6.11.9 | Update and Communicate Construct Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.6.11.10 | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.6.11.11 | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.7 | Construct Tollgate Conducted
1.8 | Test
1.8.1 | Conduct System Testing
1.8.1.1 | Develop Test Scripts | Supplier
1.8.1.2 | Validate Test Scripts | Supplier
1.8.1.3 | Update Requirements Traceability Matrix (RTM) | Supplier
1.8.1.4 | Check-In Test Scripts and RTM | Supplier,CM Lead[60%]
1.8.1.5 | Set Up Test Environment
1.8.1.5.1 | Install Test Environment | Project Manager,Test Manager,Supplier
1.8.1.5.2 | Apply Infrastructure Changes | Project Manager,Test Manager,Supplier
1.8.1.5.3 | Apply Security Changes | Project Manager,Test Manager,Supplier
1.8.1.5.4 | Convert and Migrate Data | Project Manager,Test Manager,Supplier
1.8.1.5.5 | Verify Test Environment | Test Manager,Supplier
1.8.1.5.6 | Verify and Audit Test Environment | Project Manager
1.8.1.5.7 | Fix Gaps Related to Test Environment | Test Manager,Supplier
1.8.1.6 | Test Build and Installation of the System
1.8.1.6.1 | Build the System | Supplier
1.8.1.6.2 | Install and Configure the System | Supplier
1.8.1.6.3 | Verify Installation and System Documentation | Supplier
1.8.1.6.4 | Fix Defects and Issues | Supplier
1.8.1.6.5 | Update Installation and System Documentation | Supplier
1.8.1.6.6 | Obtain Approval and Check-In SD, SC and Installation Guide | CM Lead[30%],Supplier,Project Manager
1.8.1.7 | Execute System Tests
1.8.1.7.1 | Run Test Scripts | Supplier
1.8.1.7.2 | Record Test Results | Supplier
1.8.1.7.3 | Run Test Cases | Supplier
1.8.1.8 | Prepare System Test Summary Report (STSR) for the Cycle | Supplier
1.8.1.9 | Review System Test Summary Report (STSR) for the Cycle | Project Manager,Test Manager,Supplier
1.8.1.10 | Plan Next Test Cycle | Project Manager,Test Manager,Supplier
1.8.1.11 | Fix Defects and Issues | Project Manager,Test Manager,Supplier
1.8.1.12 | Verify System Test Results | Project Manager,Test Manager,Supplier
1.8.1.13 | Log Defects and Issues | Project Manager,Test Manager,Supplier
1.8.1.14 | Generate Final System Test Summary Report (STSR) | Project Manager,Test Manager,Supplier
1.8.1.15 | Check-In System Test Cases and System Test Summary Report (STSR) | Project Manager,Test Manager,Supplier,CM Lead[60%]
1.8.2 | Prepare Pre-Production Environment at Site
1.8.2.1 | Prepare Site for System Changes
1.8.2.1.1 | Prepare Site for Infrastructure Changes | Site Operations and Support Manager,Site Deployment Manager
1.8.2.1.2 | Prepare Site for Security Changes | Site Operations and Support Manager,Site Deployment Manager
1.8.2.1.3 | Prepare Site for Application Data Migration | Site Operations and Support Manager,Site Deployment Manager
1.8.2.2 | Create System Migration Plan | Site Operations and Support Manager,Site Deployment Manager
1.8.2.3 | Conduct Test and Site Readiness Review | Site Operations and Support Manager,Site Deployment Manager
1.8.2.4 | Prepare Test Cases for the Sites | Site Operations and Support Manager,Site Deployment Manager
1.8.2.5 | Update System Documentation and Test Plans for the Site | Site Operations and Support Manager,Site Deployment Manager
1.8.2.6 | Update Site Deployment Plan | Site Operations and Support Manager,Site Deployment Manager
1.8.2.7 | Apply Infrastructure Changes | Site Operations and Support Manager,Site Deployment Manager
1.8.2.8 | Apply Security Changes | Site Operations and Support Manager,Site Deployment Manager
1.8.2.9 | Convert and Migrate Data | Site Operations and Support Manager,Site Deployment Manager
1.8.3 | Conduct Acceptance Testing Readiness Review
1.8.3.1 | Perform Checks to Verify Pre-Production Environment | Operations and Support Manager,Test Manager,Project Manager,Supplier
1.8.3.2 | Fix Gaps Related to Pre-Production Environment | Operations and Support Manager,Test Manager,Project Manager,Supplier
1.8.3.3 | Verify and Audit Pre-Production Environment | Test Manager,Project Manager,Supplier
1.8.3.4 | Review and Approve System Documentation | Operations and Support Manager
1.8.3.5 | Test Build and Installation for Acceptance Testing
1.8.3.5.1 | Build the System | Supplier
1.8.3.5.2 | Install and Configure the System | Supplier
1.8.3.5.3 | Verify Installation and System Documentation | Supplier,Project Manager
1.8.3.5.4 | Fix Defects and Issues | Supplier
1.8.3.5.5 | Update Installation and System Documentation | Supplier
1.8.3.5.6 | Obtain Approval and Check-In SD, SC and Installation Guide | Supplier,Project Manager,CM Lead[60%]
1.8.3.6 | Conduct Release Audit | Supplier,CM Lead[60%],QA Analyst
1.8.3.7 | Conduct Acceptance Testing Readiness Review Meeting | Test Manager,Operations and Support Manager,QA Analyst,Project Manager,Senior Manager[40%],Endusers
1.8.4 | Conduct Acceptance Testing
1.8.4.1 | Execute User Acceptance Tests
1.8.4.2 | Verify Acceptance Test Results
1.8.4.3 | Log Defects and Issues
1.8.4.4 | Prepare User Acceptance Test Summary Report (UATSR) for the Cycle
1.8.4.5 | Ensure Review of User Acceptance Test Summary Report
1.8.4.6 | Plan Next Test Cycle
1.8.4.7 | Generate Final User Acceptance Test Summary Report
1.8.4.8 | Sign-off on User Acceptance Tests
1.8.4.9 | Approve Acceptance Test Results
1.8.4.10 | Communicate Final UATSR to Senior Management
1.8.4.11 | Provide Approval to Baseline Source, Binaries and System Documentation
1.8.4.12 | Sign-off on Non-Functional Tests
1.8.4.13 | Execute Non-Functional Acceptance Tests
1.8.5 | Acceptance Testing Conducted
1.8.6 | Analyze Defects and Change Requests
1.8.7 | Verify Production Readiness
1.8.8 | Conduct Test Tollgate
1.8.8.1 | Review Plan(s) for Deploy Phase | PMO Prg. Mgr.[50%]
1.8.9 | Conduct Test Phase Tollgate
1.8.9.1 | Update Plan(s) for Deploy Phase | Project Manager,CM Lead,QA Analyst
1.8.9.2 | Request Tollgate Review | Project Manager[30%]
1.8.9.3 | Update Business Case | Project Manager[30%]
1.8.9.4 | Prepare for Project Tollgate Review | Stakeholder[30%]
1.8.9.5 | Review Plan(s) for Deploy Phase | PMO Prg. Mgr.[50%]
1.8.9.6 | Review Work Product Baseline and Conduct CM Audit | QA Analyst
1.8.9.7 | Conduct CM Audits | QA Analyst
1.8.9.8 | Prepare Test Tollgate Review Report | Project Manager[20%]
1.8.9.9 | Update and Communicate Test Tollgate Review Report | Senior Manager[20%],Project Manager[20%],Supplier[20%],Stakeholder[20%],Test Manager[20%],PMO Prg. Mgr.[20%],Operations and Support Manager[20%],Process Engineer[20%],QA Analyst[20%]
1.8.9.10 | Work on Action Plan | PMO Prg. Mgr.[50%],Supplier[50%],Project Manager
1.8.9.11 | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%],Project Manager
1.8.9.12 | Accept Product
1.8.9.12.1 | Accept the acquired product
1.8.9.12.2 | Transition product to Operations
1.8.9.12.3 | Review Supplier Performance
1.8.9.12.4 | Execute Supplier payment process
1.9 | Test Tollgate Conducted
1.1 | Deploy
1.10.1 | Deploy at Pilot Site
1.10.1.1 | Migrate to New System at Pilot Site
1.10.1.1.1 | Execute Migration | Pilot Site Lead
1.10.1.1.2 | Perform Checks to Verify Migration | Pilot Site Lead,Pilot Site Deployment Manager[30%]
1.10.1.1.3 | Check Contingency Plan for Alternative(s) | Pilot Site Lead,Pilot Site Deployment Manager
1.10.1.1.4 | Modify System Environment or Components | Pilot Site Lead
1.10.1.1.5 | Execute Back out Plan | Pilot Site Deployment Manager
1.10.1.1.6 | Communicate To Stakeholders | Pilot Site Deployment Manager,Senior Manager,Pilot Site Manager
1.10.1.1.7 | Communicate Deployment Status | System Deployment Manager
1.10.1.2 | Migrated to New System at Pilot Site
1.10.1.3 | Update Generic Site Deployment Materials & System Documentation
1.10.1.4 | Transition to Operations at Pilot Site
1.10.1.4.1 | Support New System | Pilot Site Deployment Team Member,Pilot Site Deployment Manager
1.10.1.4.2 | Transfer Ownership to System Owner | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team
1.10.1.4.3 | Archive System Documentation, Training Material & Application/System Components | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team
1.10.1.4.4 | Train Operations Team | Pilot Site Operations & Support Team,System Owner,Pilot Site Deployment Manager
1.10.1.5 | De-Install Legacy System at Pilot Site | Pilot Site Deployment Manager
1.10.1.6 | Legacy System De-Installed at Pilot Site
1.10.2 | Deploy at Site <1>
1.10.2.1 | Migrate to New System at at Site <1>
1.10.2.1.1 | Execute Migration | Site1 Lead
1.10.2.1.2 | Perform Checks to Verify Migration | Site1 Deployment Manager[30%],Site1 Lead
1.10.2.1.3 | Check Contingency Plan for Alternative(s) | Site1 Deployment Manager,Site1 Lead
1.10.2.1.4 | Modify System Environment or Components | Site1 Lead
1.10.2.1.5 | Execute Back out Plan | Site1 Deployment Manager
1.10.2.1.6 | Communicate To Stakeholders | Site1 Manager,Senior Manager,Site1 Deployment Manager
1.10.2.1.7 | Communicate Deployment Status | System Deployment Manager
1.10.2.2 | Migrated to New System at at Site <1>
1.10.2.3 | Update Generic Site Deployment Materials & System Documentation
1.10.2.4 | Transition to Operations at at Site <1>
1.10.2.4.1 | Support New System | Site1 Deployment Manager,Site1 Deployment Team Member
1.10.2.4.2 | Transfer Ownership to System Owner | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.10.2.4.3 | Archive System Documentation, Training Material & Application/System Components | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.10.2.4.4 | Train Operations Team | Site1 Deployment Manager,System Owner,Site1 Operations & Support Team
1.10.2.5 | De-Install Legacy System at at Site <1> | Site1 Deployment Manager
1.10.2.6 | Legacy System De-Installed at Site <1>
1.10.3 | Close Project
1.10.3.1 | Conduct Post-Project Review
1.10.3.1.1 | Develop Post Project Review Breakout Session Topics & Agenda | Project Team,Project Manager,QA Analyst,CM Lead
1.10.3.1.2 | Conduct Post Project Review Meeting | Project Manager,Project Team,QA Analyst,CM Lead
1.10.3.1.3 | Complete Post Project Review Report | Project Manager,Project Team,QA Analyst,CM Lead
1.10.3.1.4 | Create Project Role Feedback Forms | Project Manager,Project Team,QA Analyst,CM Lead
1.10.3.2 | Archive Documents | Project Manager,Project Team,QA Analyst,CM Lead
1.10.3.3 | Close Project formally and Communicate | Project Manager
1.11 | Project <PTS -ID> Closed
1.12 | Project Support Activities
1.12.1 | Manage Requirements
1.12.1.1 | Understand Change in Requirements | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.2 | Perform Detailed Impact Analysis | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.3 | Raise Requirements Change Request (RCR) Form | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.4 | Review through Requirements Change Control Board (RCCB) | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.5 | Re-Estimate & Re-Plan the Project | Project Manager,Requirements Provider,Requirements Analyst,Process Engineer,Project Team Member[40%]
1.12.1.6 | Obtain Approval from Senior Manager for Change in Cost & Schedule | Senior Manager,Project Manager[30%]
1.12.1.7 | Update & Baseline Project Plan | Project Manager
1.12.1.8 | Communicate Changes in Project Plan | Project Manager
1.12.2 | Change Control
1.12.2.1 | Review Impact on CM Repository | CM Lead
1.12.2.2 | Review Impact on Work Products | Project Manager
1.12.2.3 | Update Change Register | CM Lead
1.12.2.4 | Review through Change Control Board (CCB) | Project Manager
1.12.2.5 | Update Change Register | CM Lead
1.12.2.6 | Update Change Register with Closure Details | Project Manager,CM Lead,Project Team Member[40%]
1.12.3 | Project Monitoring and Control
1.12.3.1 | Monitor Supplier Status
1.12.3.1.1 | Monitor Supplier Status 1 | Project Manager
1.12.3.1.2 | Monitor Supplier Status 2 | Project Manager
1.12.3.1.3 | Monitor Supplier Status 3 | Project Manager
1.12.3.1.4 | Monitor Supplier Status 4 | Project Manager
1.12.3.1.5 | Monitor Supplier Status 5 | Project Manager
1.12.3.2 | Update Project Log , Project Plan and Project Schedule
1.12.3.2.1 | Update Project Log , Project Plan and Project Schedule 1 | Project Manager
1.12.3.2.2 | Update Project Log , Project Plan and Project Schedule 2 | Project Manager
1.12.3.2.3 | Update Project Log , Project Plan and Project Schedule 3 | Project Manager
1.12.3.2.4 | Update Project Log , Project Plan and Project Schedule 4 | Project Manager
1.12.3.2.5 | Update Project Log , Project Plan and Project Schedule 5 | Project Manager
1.12.3.2.6 | Update Project Log , Project Plan and Project Schedule 6 | Project Manager
1.12.3.2.7 | Update Project Log , Project Plan and Project Schedule 7 | Project Manager
1.12.3.2.8 | Update Project Log , Project Plan and Project Schedule 8 | Project Manager
1.12.3.2.9 | Update Project Log , Project Plan and Project Schedule 9 | Project Manager
1.12.3.2.10 | Update Project Log , Project Plan and Project Schedule 10 | Project Manager
1.12.3.2.11 | Update Project Log , Project Plan and Project Schedule 11 | Project Manager
1.12.3.2.12 | Update Project Log , Project Plan and Project Schedule 12 | Project Manager
1.12.3.3 | Provide Measurement Results Based on SDP-21 Metrics | Project Manager
1.12.3.3.1 | Submit SDP-21 Standard Metrics
1.12.3.3.1.1 | Submit SDP-21 Standard Metrics 1 | Project Manager
1.12.3.3.1.2 | Submit SDP-21 Standard Metrics 2 | Project Manager
1.12.3.3.1.3 | Submit SDP-21 Standard Metrics 3 | Project Manager
1.12.3.3.1.4 | Submit SDP-21 Standard Metrics 4 | Project Manager
1.12.3.3.1.5 | Submit SDP-21 Standard Metrics 5 | Project Manager
1.12.3.4 | Update Project Tracking System (PTS)
1.12.3.4.1 | Update Project Tracking System (PTS) 1 | Project Manager
1.12.3.4.2 | Update Project Tracking System (PTS) 2 | Project Manager
1.12.3.4.3 | Update Project Tracking System (PTS) 3 | Project Manager
1.12.3.4.4 | Update Project Tracking System (PTS) 4 | Project Manager
1.12.3.4.5 | Update Project Tracking System (PTS) 5 | Project Manager
1.12.3.5 | Conduct Milestone Reviews
1.12.3.5.1 | Conduct Milestone Reviews 1 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.2 | Conduct Milestone Reviews 2 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.3 | Conduct Milestone Reviews 3 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.4 | Conduct Milestone Reviews 4 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.5.5 | Conduct Milestone Reviews 5 | Project Team,CM Lead,QA Analyst,Project Manager
1.12.3.6 | Conduct Senior Management Review (SMR) | Project Manager
1.12.3.6.1 | Conduct SMR meeting for the Project
1.12.3.6.1.1 | Conduct SMR meeting for the Project 1 | Project Manager,Senior Manager
1.12.3.6.1.2 | Conduct SMR meeting for the Project 2 | Project Manager,Senior Manager
1.12.3.6.1.3 | Conduct SMR meeting for the Project 3 | Project Manager,Senior Manager
1.12.3.6.1.4 | Conduct SMR meeting for the Project 4 | Project Manager,Senior Manager
1.12.3.6.1.5 | Conduct SMR meeting for the Project 5 | Project Manager,Senior Manager
1.12.3.7 | Conduct Progress Review Meetings | Project Manager
1.12.3.7.1 | Conduct Progress Review Meetings 1 | Project Manager
1.12.3.7.2 | Conduct Progress Review Meetings 2 | Project Manager
1.12.3.7.3 | Conduct Progress Review Meetings 3 | Project Manager
1.12.3.7.4 | Conduct Progress Review Meetings 4 | Project Manager
1.12.3.7.5 | Conduct Progress Review Meetings 5 | Project Manager
1.12.3.7.6 | Conduct Review with Stakeholders | Project Manager
1.12.3.8 | Monitor Project Plan and Schedule
1.12.3.8.1 | Monitor Project Plan and Schedule 1 | Project Manager
1.12.3.8.2 | Monitor Project Plan and Schedule 2 | Project Manager
1.12.3.8.3 | Monitor Project Plan and Schedule 3 | Project Manager
1.12.3.8.4 | Monitor Project Plan and Schedule 4 | Project Manager
1.12.3.8.5 | Monitor Project Plan and Schedule 5 | Project Manager
1.12.3.8.6 | Monitor Project Plan and Schedule 6 | Project Manager
1.12.3.8.7 | Monitor Project Plan and Schedule 7 | Project Manager
1.12.3.8.8 | Monitor Project Plan and Schedule 8 | Project Manager
1.12.3.8.9 | Monitor Project Plan and Schedule 9 | Project Manager
1.12.3.8.10 | Monitor Project Plan and Schedule 10 | Project Manager
1.12.3.9 | Monitor Project Risks
1.12.3.9.1 | Monitor Project Risks 1 | Project Manager
1.12.3.9.2 | Monitor Project Risks 2 | Project Manager
1.12.3.9.3 | Monitor Project Risks 3 | Project Manager
1.12.3.9.4 | Monitor Project Risks 4 | Project Manager
1.12.3.9.5 | Monitor Project Risks 5 | Project Manager
1.12.3.10 | Monitor Stakeholder Involvement Plan
1.12.3.10.1 | Monitor Stakeholder Involvement Plan 1 | Project Manager
1.12.3.10.2 | Monitor Stakeholder Involvement Plan 2 | Project Manager
1.12.3.10.3 | Monitor Stakeholder Involvement Plan 3 | Project Manager
1.12.3.10.4 | Monitor Stakeholder Involvement Plan 4 | Project Manager
1.12.3.10.5 | Monitor Stakeholder Involvement Plan 5 | Project Manager
1.12.3.11 | Monitor Data Management Plan
1.12.3.11.1 | Monitor Data Management Plan 1 | Project Manager
1.12.3.11.2 | Monitor Data Management Plan 2 | Project Manager
1.12.3.11.3 | Monitor Data Management Plan 3 | Project Manager
1.12.3.11.4 | Monitor Data Management Plan 4 | Project Manager
1.12.3.11.5 | Monitor Data Management Plan 5 | Project Manager
1.12.4 | Project Quality Assurance
1.12.4.1 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) | QA Analyst
1.12.4.1.1 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 1 | QA Analyst
1.12.4.1.2 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 2 | QA Analyst
1.12.4.1.3 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 3 | QA Analyst
1.12.4.1.4 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 4 | QA Analyst
1.12.4.1.5 | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 5 | QA Analyst
1.12.4.2 | Track and Verify NC Closure
1.12.4.2.1 | Track and Verify NC Closure 1 | Project Manager
1.12.4.2.2 | Track and Verify NC Closure 22 | Project Manager
1.12.4.2.3 | Track and Verify NC Closure 23 | Project Manager
1.12.4.3 | Verify Closure of Review Defect found in Work Product Review(s)
1.12.4.3.1 | Verify Closure of Review Defect found in Work Product Review(s) 1 | QA Analyst
1.12.4.3.2 | Verify Closure of Review Defect found in Work Product Review(s) 21 | QA Analyst
1.12.4.3.3 | Verify Closure of Review Defect found in Work Product Review(s) 22 | QA Analyst
1.12.4.3.4 | Verify Closure of Review Defect found in Work Product Review(s) 23 | QA Analyst
1.12.4.4 | Review Supplier's Process
1.12.4.4.1 | Review Supplier's Process 1 | QA Analyst,Project Manager
1.12.4.4.2 | Review Supplier's Process 2 | QA Analyst,Project Manager
1.12.4.4.3 | Review Supplier's Process 3 | QA Analyst,Project Manager
1.12.4.4.4 | Review Supplier's Process 4 | QA Analyst,Project Manager
1.12.4.4.5 | Review Supplier's Process 5 | QA Analyst,Project Manager
1.12.5 | Configuration Management
1.12.5.1 | Update Change Register with Status of CR's | CM Lead
1.12.5.1.1 | Update Change Register with Status of CR's 1 | CM Lead
1.12.5.1.2 | Update Change Register with Status of CR's 2 | CM Lead
1.12.5.1.3 | Update Change Register with Status of CR's 3 | CM Lead
1.12.5.1.4 | Update Change Register with Status of CR's 4 | CM Lead
1.12.5.1.5 | Update Change Register with Status of CR's 5 | CM Lead
1.12.5.2 | Create Baselines of the CIs
1.12.5.2.1 | Create Baselines of the CIs 1 | CM Lead
1.12.5.2.2 | Create Baselines of the CIs 2 | CM Lead
1.12.5.2.3 | Create Baselines of the CIs 3 | CM Lead
1.12.5.2.4 | Create Baselines of the CIs 4 | CM Lead
1.12.5.3 | Generate Configuration Status Accounting Report
1.12.5.3.1 | Generate Configuration Status Accounting Report 1 | CM Lead
1.12.5.3.2 | Generate Configuration Status Accounting Report 2 | CM Lead
1.12.5.3.3 | Generate Configuration Status Accounting Report 12 | CM Lead
1.12.5.4 | Verify Backup and Disaster Recovery
1.12.5.4.1 | Verify Backup and Disaster Recovery 1 | CM Lead
1.12.5.4.2 | Verify Backup and Disaster Recovery 2 | CM Lead

## SW Development
WBS | Task Name
1 | Plan Phase
1.1 | Initiate Plan Phase
1.1.1 | Determine the appropriate scenario for this project
1.1.2 | Perform phase start-up preparations
1.1.3 | Assign key personnel to the project teams
1.1.4 | Identify QA Analyst(s) and QA participation
1.1.5 | Orient teams to project
1.2 | Develop Process Design
1.2.1 | Clarify Goals
1.2.2 | Define Business Context Model
1.2.3 | Perform As-Is Assessment
1.2.4 | Develop To-Be Design
1.2.5 | Perform Change/Impact/Risk Analysis
1.2.6 | Perform Business Value Analysis
1.2.7 | Perform Implementation and Process Management Planning
1.3 | Develop Business Requirements
1.3.1 | Develop Business Requirements
1.3.2 | Review and Understand Business Requirements
1.3.3 | Identify and Resolve Inconsistencies Between Requirements and Scope
1.3.4 | Commit and Baseline Business Requirements
1.4 | Conduct Project Readiness Review
1.4.1 | Prepare Process Design Summary
1.4.2 | Determine Project Readiness
1.4.3 | Conduct Stakeholder Review
1.5 | Develop Project Charter
1.5.1 | Document project scope
1.5.2 | Develop and Document Project Management Strategy
1.5.3 | Document Recommended Project Strategy
1.5.4 | Review and Approve Project Charter
1.6 | Develop Initial Project Plan
1.6.1 | Mentor in the preparation of the Project Plan
1.6.2 | Document the Project Plan Maintenance Procedure
1.6.3 | Identify and document the project's organizational structure
1.6.4 | Identify and document project and process metrics
1.6.5 | Develop high level plan for the project
1.6.6 | Develop the work plan for the Define Phase
1.6.7 | Identify and document facilities and support tools
1.6.8 | Create Quality Assurance Plan for the project
1.6.9 | Develop the Configuration Management Plan for the project
1.6.10 | Develop the Communications Plan for the project
1.6.11 | Develop and document the Risk Processing Procedure for the project
1.6.12 | Conduct and document an Initial Project Risk Evaluation
1.6.13 | Develop and document the Issues Procedure for the Project
1.6.14 | Develop and document the Corrective Action Procedure for the project
1.6.15 | Conduct and document an Initial Project Issue Evaluation
1.6.16 | Review the Project Plan
1.6.16.1 | Develop the Integrated Project Plan Work Breakdown Structure
1.7 | Perform Project Monitoring and Control
1.7.1 | Perform project monitoring and control
1.7.2 | Collect and monitor standard and project specific measures
1.7.3 | Conduct QA Reviews
1.7.4 | Review QA Results
1.7.5 | Communicate QA Results
1.7.6 | Review QA Measurements
1.7.7 | Monitor Non-Compliances
1.7.8 | Resolve Non-Compliances
1.7.9 | Document, Escalate and Track Unresolved Non-Compliances
1.7.10 | Perform configuration management reviews according to the Project Plan and documented procedures
1.7.11 | Perform configuration library functions according to the Project Plan and documented procedures
1.7.12 | Consolidate, review and submit all measures for project status
1.7.13 | Perform project monitoring and control review
1.8 | Develop Initial Deployment and Support Plans
1.8.1 | Develop initial System Deployment Plan
1.8.2 | Develop initial Operations and Support Plan
1.8.3 | Review and Approve System Deployment Plan and Operations and Support Plan
1.9 | Develop Supplier Management Plan
1.9.1 | Define supplier acquisition objectives
1.9.1.1 | SAM Define Sourcing Requirements Phase
1.9.1.1.1 | Develop/Release RFI
1.9.1.1.2 | Determine Acquision Approach
1.9.1.1.3 | Establish Cross Functional Team
1.9.1.1.4 | Define SAM Requirements
1.9.1.1.5 | Create and Approve Acquisition Document
1.1 | Develop Business Case
1.10.1 | Develop Business Case
1.10.2 | Review and Approve Business Case
1.11 | Conduct Plan Phase Tollgate Review
1.11.1 | Prepare for Tollgate Review
1.11.2 | Confirm Tollgate Readiness
1.11.3 | Conduct Tollgate Review meeting
1.11.4 | Perform Tollgate Review follow-up
1.11.5 | Communicate Tollgate Review Meeting Results
2 | Define Phase
2.1 | Initiate Define Phase
2.1.1 | Perform phase start-up preparations
2.1.2 | Assign key personnel to the project teams
2.1.3 | Identify QA Analyst(s) and QA participation
2.1.4 | Orient teams to project
2.1.5 | Orient Deployment Team
2.1.6 | Orient Operations and Support Team
2.2 | Perform Project Monitoring and Control
2.2.1 | Perform project monitoring and control
2.2.2 | Collect and monitor standard and project specific measures
2.2.3 | Conduct QA Reviews
2.2.4 | Review QA Results
2.2.5 | Communicate QA Results
2.2.6 | Review QA Measurements
2.2.7 | Monitor Defects
2.2.8 | Resolve Defects
2.2.9 | Document, Escalate and Track Unresolved Defects
2.2.10 | Perform configuration management reviews according to the Project Plan and documented procedures
2.2.11 | Perform configuration library functions according to the Project Plan and documented procedures
2.2.12 | Consolidate, review and submit all measures for project status
2.2.13 | Perform project monitoring and control review
2.3 | Develop and Analyze User and System Requirements
2.3.1 | Develop User Requirements
2.3.2 | Develop Use Cases
2.3.3 | Develop System Requirements
2.3.3.1 | Derive Functional Requirements
2.3.3.2 | Derive Non-Functional Requirements for Disaster Recovery Planning
2.3.3.3 | Derive all other Non-Functional Requirements
2.3.3.4 | Validate and clarify requirements
2.3.3.5 | Identify and Document Operational Requirements
2.3.3.6 | Prioritize System Requirements
2.3.3.7 | Update Business and User Requirements as necessary
2.3.3.8 | Compile the System Requirements Specification document
2.3.4 | Develop Privacy Compliance Plan
2.3.5 | Create IT Standards Bill of Materials (BoM)
2.3.6 | Review and Understand System Requirements
2.3.7 | Identify and Resolve Inconsistencies Between Requirements
2.3.8 | Commit and baseline System Requirements Specification
2.4 | Manage Requirements
2.4.1 | Maintain bi-directional traceability
2.4.2 | Manage requirements changes
2.5 | Create Software Architecture
2.5.1 | Develop Software Architecture Document
2.5.2 | Review and Approve Software Architecture Document
2.5.3 | Develop build/buy/reuse recommendation
2.6 | Create Test Plans
2.6.1 | Develop Test Strategy
2.6.2 | For each test type, develop a test plan
2.6.3 | Develop initial test cases
2.6.4 | Review and Approve Test plans
2.7 | Define Training Requirements
2.7.1 | Define training requirements
2.7.2 | Review and Approve Training Requirements
2.8 | Revise Deployment and Support Plans
2.8.1 | Revise System Deployment Plan
2.8.2 | Develop initial Generic Site Implementation Materials
2.8.3 | Create initial Site Business Change Plan
2.8.4 | Obtain feedback and revised estimates
2.8.5 | Define the strategy for transition to operations and support
2.8.6 | Revise Operations and Support Plan
2.8.7 | Review and Approve System Deployment and Operations and Support Plans
2.9 | Procure Supplier Services
2.9.1 | Update the Supplier Management Plan
2.9.1.1 | SAM Define Sourcing Requirements Phase (cont)
2.9.1.1.1 | Define SAM Requirements
2.9.1.1.2 | Create and Approve Acquisition Document
2.9.2 | Define detailed IT needs
2.9.3 | Obtain A/R approval
2.9.4 | Select Suppliers
2.9.4.1 | SAM Select Suppliers Phase
2.9.4.1.1 | Develop RFP
2.9.4.1.2 | Develop Supplier Evaluation Criteria
2.9.4.1.3 | Identify Potential Suppliers
2.9.4.1.4 | Distribute RFP
2.9.4.1.5 | Evauate Proposals
2.9.4.1.6 | Approve Supplier(s) Down Select
2.1 | Establish Supplier Agreement
2.10.1 | Establish Supplier Agreement
2.10.1.1 | SAM Establish Agreement Phase
2.10.1.1.1 | Develop Negotiation Strategy
2.10.1.1.2 | Negotiate Agreement
2.10.1.1.3 | Evaluate and Select Final Supplier
2.10.1.1.4 | Create and Approve Agreement
2.10.1.1.5 | Communicate Agreement
2.10.2 | Select Suppliers
2.10.3 | Establish Supplier Agreement
2.10.4 | Tailor development process
2.11 | Revise Project Plan
2.11.1 | Update Project Management Procedures
2.11.2 | Update QA Plan
2.11.3 | Update Management Plans
2.11.4 | Update Integrated Plan
2.11.5 | Review and Approve Project Plan
2.12 | Revise Business Case
2.12.1 | Revise Business Case documents
2.12.2 | Review and Approve Business Case
2.13 | Conduct Define Phase Tollgate Review
2.13.1 | Prepare for Tollgate Review
2.13.2 | Confirm Tollgate Readiness
2.13.3 | Conduct Tollgate Review meeting
2.13.4 | Perform Tollgate Review follow-up
2.13.5 | Communicate Tollgate Review Meeting Results
3 | Design Phase
3.1 | Initiate Design Phase
3.1.1 | Perform phase start-up preparations
3.1.2 | Assign key personnel to the project teams
3.1.3 | Identify QA Analyst(s) and QA participation
3.1.4 | Orient teams to project
3.1.5 | Orient Deployment Team
3.1.6 | Orient Operations and Support Team
3.2 | Perform Project Monitoring and Control
3.2.1 | Perform project monitoring and control
3.2.2 | Collect and monitor standard and project specific measures
3.2.3 | Conduct QA Reviews
3.2.4 | Review QA Results
3.2.5 | Communicate QA Results
3.2.6 | Review QA Metrics
3.2.7 | Monitor Defects
3.2.8 | Resolve Defects
3.2.9 | Document, Escalate and Track Unresolved Defects
3.2.10 | Perform configuration management reviews according to the Project Plan and documented procedures
3.2.11 | Perform configuration library functions according to the Project Plan and documented procedures
3.2.12 | Consolidate, review and submit all measures for project status
3.2.13 | Perform project monitoring and control review
3.2.13.1 | SAM Execute Agreement Phase
3.2.13.1.1 | Execute Governance Model
3.2.13.1.2 | Monitor Supplier Progress and Performance
3.2.13.1.3 | Conduct Supplier Reviews
3.2.13.1.4 | Use Results of Reviews to Improve Performance
3.2.13.1.5 | Revise Supplier Agreement and Plans as Necessary
3.3 | Create System Design
3.3.1 | Develop feasibility prototype
3.3.2 | Refine Disaster Recovery Strategy
3.3.3 | Create design
3.3.4 | Support, critique and review
3.3.5 | Review and Approve System Design Document
3.4 | Allocate System Requirements
3.4.1 | Allocate requirements to IT solution
3.4.2 | Update bi-directional traceability
3.4.3 | Identify and resolve inconsistencies between requirements and IT solution
3.5 | Develop Training Curriculum
3.5.1 | Develop training curriculum
3.5.2 | Review and Approve Training Curriculum
3.6 | Create System Documentation Specification
3.6.1 | Specify the content of System Documentation
3.7 | Develop Test Cases
3.7.1 | For each internal test type, identify test cases
3.7.2 | Complete or develop detailed test cases
3.7.3 | Review and Approve Test Cases
3.8 | Revise Software Architecture Document
3.8.1 | Revise Software Architecture Document
3.8.2 | Review and Approve Software Architecture Document
3.9 | Revise Deployment and Support Plans
3.9.1 | Revise System Deployment Plan
3.9.2 | Revise Generic Site Implementation Materials
3.9.3 | Revise Site Business Change Plan
3.9.4 | Obtain feedback and revised estimates
3.9.5 | Revise Operations and Support Plan
3.9.6 | Review and Approve System Deployment and Operations and Support Plans
3.1 | Revise Project Plan
3.10.1 | Update QA Plan
3.10.2 | Revise Project Management Procedures and Management Plans
3.10.3 | Update Integrated Plan
3.10.4 | Review and Approve Project Plan
3.11 | Revise Business Case
3.11.1 | Revise Business Case
3.11.2 | Review and Approve Business Case
3.12 | Conduct Design Phase Tollgate Review
3.12.1 | Prepare for Tollgate Review
3.12.2 | Confirm Tollgate Readiness
3.12.3 | Conduct Tollgate Review meeting
3.12.4 | Perform Tollgate Review follow-up
3.12.5 | Communicate Tollgate Review Meeting Results
4 | Build Phase
4.1 | Initiate Build Phase
4.1.1 | Perform phase start-up preparations
4.1.2 | Assign key personnel to the project teams
4.1.3 | Identify QA Analyst(s) and QA participation
4.1.4 | Orient teams to project
4.1.5 | Orient Deployment Team
4.1.6 | Orient Operations and Support Team
4.2 | Perform Project Monitoring and Control
4.2.1 | Perform project monitoring and control
4.2.2 | Collect and monitor standard and project specific measures
4.2.3 | Conduct QA Reviews
4.2.4 | Review QA Results
4.2.5 | Communicate QA Results
4.2.6 | Review QA Measurements
4.2.7 | Monitor Non-Compliances
4.2.8 | Resolve Non-Compliances
4.2.9 | Document, Escalate and Track Unresolved Non-Compliances
4.2.10 | Perform configuration management reviews according to the Project Plan and documented procedures
4.2.11 | Perform configuration library functions according to the Project Plan and documented procedures
4.2.12 | Consolidate, review and submit all measures for project status
4.2.13 | Perform project monitoring and control review
4.2.14 | Perform SAM Management Activities
4.2.12.1.1 | Execute Governance Model
4.2.12.1.2 | Monitor Supplier Progress and Performance
4.2.12.1.3 | Conduct Supplier Reviews
4.2.12.1.4 | Use Results of Reviews to Improve Performance
4.2.12.1.5 | Revise Supplier Agreement and Plans as Necessary
4.3 | Code/Configure System
4.3.1 | Create, integrate and test system
4.3.1.1 | Develop Disaster Recovery Implementation Plans
4.3.2 | Support, critique and review
4.4 | Develop System and User Documentation
4.4.1 | Create System Documentation
4.4.1.1 | Create or revise User Guide
4.4.1.2 | Create or revise System Installation Guide
4.4.1.3 | Create or revise Operations Guide
4.4.1.4 | Create or revise System Maintenance Reference Guide
4.4.1.5 | Create Disaster Recovery Planning documentation
4.4.2 | Review and approve System and User Documentation
4.5 | Develop Training Materials
4.5.1 | Create training and training support materials
4.5.2 | Support, critique and review
4.6 | Conduct Testing
4.6.1 | Monitor supplier test results
4.6.2 | Train personnel
4.6.3 | Install system and verify basic operation in test environment
4.6.4 | Conduct testing
4.6.5 | Address issues and conflicts
4.6.6 | Review and Approve Test Results
4.7 | Revise Deployment and Support Plans
4.7.1 | Revise System Deployment Plan
4.7.2 | Revise Generic Site Implementation Materials
4.7.3 | Revise Site Business Change Plan
4.7.4 | Obtain feedback and revised estimates
4.7.5 | Revise the transition to operations and support plan
4.7.6 | Revise Operations and Support Plan
4.7.7 | Review and Approve System Deployment and Operations and Support Plans
4.8 | Revise Project Plan
4.8.1 | Revise Project Management Procedures and Management Plans
4.8.2 | Update QA Plan
4.8.3 | Revise Integrated Plan
4.8.4 | Review and Approve Project Plan
4.9 | Revise Business Case
4.9.1 | Revise Business Case
4.9.2 | Review and Approve Business Case
4.1 | Conduct Build Phase Tollgate Review
4.10.1 | Prepare for Tollgate Review
4.10.2 | Confirm Tollgate Readiness
4.10.3 | Conduct Tollgate Review meeting
4.10.4 | Perform Tollgate Review follow-up
4.10.5 | Communicate Tollgate Review Meeting Results
5 | Deploy Phase
5.1 | Initiate Deploy Phase
5.1.1 | Perform phase start-up preparations
5.1.2 | Assign key personnel to the project teams
5.1.3 | Identify QA Analyst(s) and QA participation
5.1.4 | Orient teams to project
5.2 | Perform Project Monitoring and Control
5.2.1 | Perform project monitoring and control
5.2.2 | Collect and monitor standard and project specific measures
5.2.3 | Conduct QA Reviews
5.2.4 | Review QA Results
5.2.5 | Communicate QA Results
5.2.6 | Review QA Measurements
5.2.7 | Monitor Non-Compliances
5.2.8 | Resolve Non-Compliances
5.2.9 | Document, Escalate and Track Unresolved Non-Compliances
5.2.10 | Perform configuration management reviews according to the Project Plan and documented procedures
5.2.11 | Perform configuration library functions according to the Project Plan and documented procedures
5.2.12 | Consolidate, review and submit all measures for project status
5.2.13 | Perform project monitoring and control review
5.2.14 | SAM Accept Product Phase
5.2.14.1 | Accept the Aqcuired Product or Service
5.2.14.2 | Transition Product to Operations
5.2.14.3 | Review Supplier Performance
5.2.14.4 | Execute Supplier Payment Process
5.3 | Prepare for Pilot(s)
5.3.1 | Create pilot implementation procedures
5.3.2 | Finalize support readiness
5.3.3 | Review and Approve Procedures and Generic Site Implementation Materials
5.3.4 | Refine and Test Disaster Recovery Test Plan
5.4 | Conduct Pilot(s)
5.4.1 | Orient pilot site
5.4.2 | Monitor pilot implementation progress
5.4.3 | Execute defect and issue procedures
5.4.4 | Evaluate pilot implementation
5.4.5 | Revise System Deployment Plan and Site Implementation Materials
5.4.6 | Review and Approve Site Implementation Materials
5.4.7 | Transfer Transition Documents to Deployment Project, if Appropriate
5.5 | Coordinate Site Implementations
5.5.1 | Determine if this activity needs to be conducted
5.5.2 | Transition to ongoing operations and support
5.5.3 | Orient each site
5.5.4 | Monitor site implementation progress
5.5.5 | Execute defect and issue procedures
5.5.6 | Maintain System Deployment Plan and Generic Site Implementation Materials
5.6 | Revise Deployment and Support Plans
5.6.1 | Revise System Deployment Plan
5.6.2 | Revise Operations and Support Plan
5.6.3 | Review and Approve System Deployment and Operations and Support Plans
5.7 | Revise Project Plan
5.7.1 | Revise Project Plan
5.7.2 | Review and Approve Project Plan
5.8 | Revise Business Case
5.8.1 | Revise Business Case
5.8.2 | Review and Approve Business Case
5.9 | Conduct Deploy Phase Tollgate Review
5.9.1 | Initiate the Post Project Review
5.9.2 | Prepare for Tollgate Review
5.9.3 | Confirm Tollgate Readiness
5.9.4 | Conduct Tollgate Review meeting
5.9.5 | Perform Tollgate Review follow-up
5.9.6 | Communicate Tollgate Review Meeting Results
6 | Close Phase
6.1 | Transfer Responsibility to System Owner
6.1.1 | Final transfer of system to GM System Owner
6.1.1.1 | Ensure that system owner is provided a copy of all system documentation
6.1.1.2 | Ensure that system owner is provided a copy of the IT Supplier Service Agreements
6.1.1.3 | Ensure that system owner is provided a copy of the SRS,SAD<SDD,Test Scripts, and
6.2 | Perform Post Project Review (PPR)
6.2.1 | Develop Post Project Review (PPR) Breakout Session Topics and Agenda
6.2.2 | Conduct Post Project Review Meeting
6.2.3 | Complete Post Project Review Report
6.2.4 | Create Project Role Feedback Forms
6.3 | Archive Project Documents
6.3.1 | Develop an archival scheme for project documents that is compliant with ILM policies
6.3.2 | Archive all deliverables per the Deliverable Retention and Archiving Requirements spreadsheet
6.4 | Close Project
6.4.1 | Communicate project closure
7 | INSERT SUPPLIER PLAN(S) HERE
8 | INSERT SITE IMPLEMENTATION PLAN(S) HERE
9 | INSERT OTHER PROCESS PLANS AS REQUIRED HERE

## Site Implementation
WBS | Task Name
1 | SIP Plan Phase for Site <name>
1.1 | Initiate Plan Phase
1.1.1 | Perform Phase Start-up Preparations
1.1.2 | Assign key personnel to the project teams
1.1.3 | Identify QA Analyst(s) and QA participation
1.1.4 | Orient site implementation teams
1.2 | Develop Site Implementation Charter
1.2.1 | Review, understand and commit to business requirements
1.2.2 | Perform As-Is Assessment for site
1.2.3 | Perform To-Be Assessment for site
1.2.4 | Perform Site Change/Impact/Risk Analysis
1.2.5 | Document project mission and business objectives in the Site Implementation Charter
1.2.6 | Document the future environment in the Site Implementation Charter
1.2.7 | Define the current environment
1.2.8 | Document major impacts
1.2.9 | Define and document the implementation organization
1.2.10 | Review and approve the Site Implementation Charter
1.3 | Develop Site Implementation Plan
1.3.1 | Mentor in the preparation of the Site Implementation Plan
1.3.2 | Develop and document project schedule
1.3.3 | Define and document project implementation factors
1.3.4 | Define and document initial business case as needed
1.3.5 | Complete the procurement plan
1.3.6 | Develop and document executive summary
1.3.7 | Develop the Communications Plan
1.3.8 | Define and document the Questions / Issues Resolution process
1.3.9 | Update the Quality Assurance Plan for the project (if none exists, Develop the Quality Assurance Plan)
1.3.10 | Update the Configuration Management Plan for the project (if none exists, Develop the Configuration Management Plan)
1.3.11 | Review and Approve the Site Implementation Plan
1.4 | Perform Project Monitoring and Control
1.4.1 | Perform project monitoring and control
1.4.2 | Collect and monitor standard and project specific measures
1.4.3 | Conduct QA Reviews
1.4.4 | Review QA Results
1.4.5 | Communicate QA Results
1.4.6 | Review QA Metrics
1.4.7 | Monitor Defects
1.4.8 | Resolve Defects
1.4.9 | Document, Escalate and Track Unresolved Defects
1.4.10 | Perform configuration management reviews according to the Site Implementation Plan and documented procedures
1.4.11 | Perform configuration library functions according to the Site Implementation Plan, Configuration Management Plan and documented procedures
1.4.12 | Consolidate, review and submit all measures for project status
1.4.13 | Perform project monitoring and control review
1.5 | Develop Acquisition Plan
1.5.1 | Identify and document the Acquisition Strategy
1.6 | Develop Business Case
1.6.1 | Update Business Case section of Site Implementation Plan
1.6.2 | Revise or complete Executive Summary in the Site Implementation Plan
1.6.3 | Review and Approve Site Implementation Plan
1.7 | Conduct Plan Phase Tollgate Review
1.7.1 | Prepare for tollgate review
1.7.2 | Confirm Tollgate Readiness
1.7.3 | Conduct tollgate review
1.7.4 | Prepare tollgate review follow-up
2 | SIP Define Phase
2.1 | Initiate Define Phase
2.1.1 | Perform Phase Start-up Preparations
2.1.2 | Assign key personnel to the project teams
2.1.3 | Identify QA Analyst(s) and QA participation
2.1.4 | Orient teams to Project Plan
2.2 | Perform Project Monitoring and Control
2.2.1 | Perform project monitoring and control
2.2.2 | Collect and monitor standard and project specific measures
2.2.3 | Conduct QA Reviews
2.2.4 | Review QA Results
2.2.5 | Communicate QA Results
2.2.6 | Review QA Metrics
2.2.7 | Monitor Defects
2.2.8 | Resolve Defects
2.2.9 | Document, Escalate and Track Unresolved Defects
2.2.10 | Perform configuration management reviews according to the Site Implementation Plan and documented procedures
2.2.11 | Perform configuration library functions according to the Site Implementation Plan, Configuration Management Plan and documented procedures.
2.2.12 | Consolidate, review and submit all measures for project status
2.2.13 | Perform project monitoring and control review
2.3 | Identify and Analyze Gaps
2.3.1 | Review As-Is and To-Be Processes
2.3.2 | Document the current system environment
2.3.3 | Build functional knowledge of new environment within the Site Implementation Team
2.3.4 | Manage gaps in the business process and system
2.4 | Allocate and Manage Gap Solutions
2.4.1 | Prioritize business process changes
2.4.2 | Identify gaps to be addressed
2.4.3 | Develop relevant models for each gap identified to communicate solutions
2.4.4 | Create/Update IT Standards Bill of Materials (BoM)
2.4.5 | Review and Understand System Requirements
2.4.6 | Identify and Resolve Inconsistencies Between Requirements
2.4.7 | Review and approve new environment and models
2.5 | Develop Test Plan and Initial Test Cases
2.5.1 | Develop/Update site test strategy
2.5.2 | Develop/Update initial site test plan
2.5.3 | Develop/Update site test cases
2.5.4 | Identify resources required to execute site test cases
2.5.5 | Develop site test plan and schedule
2.5.6 | Review and approve Site Test Plan
2.6 | Develop Site Training Plan
2.6.1 | Define training scope and gaps
2.6.2 | Develop training schedule
2.6.3 | Review and approve Site Training Plan
2.7 | Revise Site Implementation Plan
2.7.1 | Revise the content of the Site Implementation Plan
2.7.2 | Review Site Implementation Plan
2.7.3 | Update QA Plan
2.8 | Procure Supplier Services
2.8.1 | Define detailed IT needs
2.8.2 | Obtain A/R approval
2.8.3 | Establish Supplier Agreement
2.8.4 | Tailor implementation process
2.9 | Revise Business Case
2.9.1 | Update Business Case section of Site Implementation Plan
2.9.2 | Revise the Project Schedule as needed
2.9.3 | Assess impact to project
2.9.4 | Review and approve Site Implementation Plan
2.1 | Conduct Define Phase Tollgate Review
2.10.1 | Prepare for tollgate review
2.10.2 | Confirm Tollgate Readiness
2.10.3 | Conduct tollgate review
2.10.4 | Prepare tollgate review follow-up
3 | SIP Prepare Phase
3.1 | Initiate Prepare Phase
3.1.1 | Perform phase start-up preparations
3.1.2 | Assign key personnel to the project teams
3.1.3 | Identify QA Analyst(s) and QA participation
3.1.4 | Orient teams to project
3.2 | Perform Project Monitoring and Control
3.2.1 | Perform project monitoring and control
3.2.2 | Collect and monitor standard and project specific measures
3.2.3 | Conduct QA Reviews
3.2.4 | Review QA Results
3.2.5 | Communicate QA Results
3.2.6 | Review QA Metrics
3.2.7 | Monitor Defects
3.2.8 | Resolve Defects
3.2.9 | Document, Escalate and Track Unresolved Defects
3.2.10 | Perform configuration management reviews according to the Site Implementation Plan and documented procedures
3.2.11 | Perform configuration library functions according to the Site Implementation Plan, Configuration Management Plan and documented procedures.
3.2.12 | Consolidate, review and submit all measures for project status
3.2.13 | Perform project monitoring and control review
3.3 | Monitor Supplier Progress
3.3.1 | Monitor and communicate status
3.3.2 | Resolve issues and conflicts
3.4 | Prepare Business Process Changes
3.4.1 | Develop new business process materials
3.4.2 | Review and approve business process materials
3.5 | Prepare System Changes
3.5.1 | Prepare software code and configuration changes
3.5.2 | Allocate site system requirements found during the Gap Analysis Results
3.5.3 | Prepare infrastructure changes
3.5.4 | Prepare security changes
3.5.5 | Prepare data conversion and load
3.6 | Conduct Training
3.6.1 | Review training materials
3.6.2 | Review training plan and implement schedule
3.7 | Conduct Testing
3.7.1 | Finalize test cases
3.7.2 | Train testers
3.7.3 | Install test environment
3.7.4 | Conduct actual testing
3.7.5 | Review site test results
3.8 | Conduct Site Preparation
3.8.1 | Implement infrastructure changes
3.8.2 | Implement security
3.8.3 | Implement data conversion and load
3.9 | Revise Site Implementation Plan
3.9.1 | Finalize the migration plan
3.9.2 | Revise the Implementation Schedule
3.9.3 | Revise the Business Case
3.9.4 | Review and approve Site Implementation Plan
3.9.5 | Update QA Plan
3.1 | Conduct Prepare Phase Tollgate Review
3.10.1 | Prepare for tollgate review
3.10.2 | Confirm Tollgate Readiness
3.10.3 | Conduct tollgate review
3.10.4 | Prepare tollgate review follow-up
4 | SIP Implement Phase
4.1 | Initiate Implement Phase
4.1.1 | Perform Phase Start-up Preparations
4.1.2 | Assign key personnel to the project teams
4.1.3 | Identify QA Analyst(s) and QA participation
4.1.4 | Orient teams to project
4.2 | Perform Project Monitoring and Control
4.2.1 | Perform project monitoring and control
4.2.2 | Collect and monitor standard and project specific measures
4.2.3 | Conduct QA Reviews
4.2.4 | Review QA Results
4.2.5 | Communicate QA Results
4.2.6 | Review QA Metrics
4.2.7 | Monitor Defects
4.2.8 | Resolve Defects
4.2.9 | Document, Escalate and Track Unresolved Defects
4.2.10 | Perform configuration management reviews according to the Site Implementation Plan and documented procedures
4.2.11 | Perform configuration library functions according to the Site Implementation Plan, Configuration Management Plan and documented procedures.
4.2.12 | Consolidate, review and submit all measures for project status
4.2.13 | Perform project monitoring and control review
4.3 | Monitor Supplier Progress
4.3.1 | Monitor and communicate status
4.3.2 | Resolve issues and conflicts
4.4 | Migrate to New System
4.4.1 | Install and verify system components
4.4.2 | If necessary, execute the Backout Plan
4.4.3 | Support the new system start up
4.4.4 | Transition system responsibility to support groups
4.5 | De-install Legacy Components
4.5.1 | De-install obsolete components
4.5.2 | Update Site Implementation Plan
4.6 | Conduct Implement Phase Tollgate Review
4.6.1 | Prepare for tollgate review
4.6.2 | Confirm Tollgate Readiness
4.6.3 | Conduct tollgate review
4.6.4 | Prepare tollgate review follow-up
4.7 | Close Implementation Project
4.7.1 | Close down the project

## System Deployment
WBS | [5 empty] | Task Name | Resource Names
1 | [5 empty] | System Deployment Schedule for < Project Name>
1.2 | 1.1 |  |  |  |  | Define
1.2.1 |  | 1.1.1 |  |  |  | Develop Plan for System Deployment
1.2.1.1 |  |  | 1.1.1.1 |  |  | Understand Deployment Scope of the System | System Deployment Manager
1.2.1.2 |  |  | 1.1.1.2 |  |  | Plan for Supplier Sourcing
1.2.1.2.1 |  |  |  | 1.1.1.2.1 |  | Develop & Release RFI | SAM Analyst,WWP/Contract Manager,System Deployment Manager
1.2.1.2.2 |  |  |  | 1.1.1.2.2 |  | Get Single Sourcing Justification Letter and Obtain Approval | Senior Manager[30%],System Deployment Manager[30%]
1.2.1.2.3 |  |  |  | 1.1.1.2.3 |  | Procure Resources
1.2.1.2.3.1 |  |  |  |  | 1.1.1.2.3.1 | Engage Time & Material Resources | SAM Analyst,WWP/Contract Manager,Senior Manager,System Deployment Manager
1.2.1.2.4 |  |  |  | 1.1.1.2.4 |  | Procure Supplier
1.2.1.2.4.1 |  |  |  |  | 1.1.1.2.4.1 | Develop RFP & Evaluation Criteria | SAM Analyst,System Deployment Manager
1.2.1.2.4.2 |  |  |  |  | 1.1.1.2.4.2 | Distribute RFP to Suppliers | WWP/Contract Manager,SAM Analyst
1.2.1.2.4.3 |  |  |  |  | 1.1.1.2.4.3 | Evaluate Proposals | SAM Analyst[0%],System Deployment Manager[0%]
1.2.1.2.4.4 |  |  |  |  | 1.1.1.2.4.4 | Approve Supplier(s) Down-Select | Senior Manager,SAM Analyst,System Deployment Manager
1.2.1.2.4.5 |  |  |  |  | 1.1.1.2.4.5 | Negotiate Agreement & Select Final Supplier | Senior Manager,SAM Analyst,System Deployment Manager
1.2.1.2.5 |  |  |  | 1.1.1.2.5 |  | Finalize Supplier Management Plan | System Deployment Manager
1.2.1.3 |  |  | 1.1.1.3 |  |  | Identify Customer Deliverables | System Deployment Manager
1.2.1.4 |  |  | 1.1.1.4 |  |  | Orient QA with Project Background | QA Analyst,System Deployment Manager
1.2.1.5 |  |  | 1.1.1.5 |  |  | Tailor SDP-21 for Project Characteristics | System Deployment Manager,QA Analyst
1.2.1.6 |  |  | 1.1.1.6 |  |  | Develop Test Strategy | System Deployment Manager
1.2.1.7 |  |  | 1.1.1.7 |  |  | Develop Peer Review Plan | System Deployment Manager
1.2.1.8 |  |  | 1.1.1.8 |  |  | Identify Resources, Tools and Training Needs | System Deployment Manager,System Deployment Team
1.2.1.9 |  |  | 1.1.1.9 |  |  | Document CM Plan | System Deployment Manager,CM Lead
1.2.1.10 |  |  | 1.1.1.10 |  |  | Document Project Data Management Plan | System Deployment Manager,CM Lead
1.2.1.11 |  |  | 1.1.1.11 |  |  | Document QA Plan | System Deployment Manager,QA Analyst
1.2.1.12 |  |  | 1.1.1.12 |  |  | Document Stakeholder(s) Involvement Plan | System Deployment Manager,System Deployment Team,Senior Manager
1.2.1.13 |  |  | 1.1.1.13 |  |  | Identify Critical Dependencies and Issues | System Deployment Manager
1.2.1.14 |  |  | 1.1.1.14 |  |  | Asess and Create Procurement Plan for acquiring Supplier/Products for System Deployment | System Deployment Manager,System Deployment Team
1.2.1.15 |  |  | 1.1.1.15 |  |  | Refine and Optimize Project Schedule | System Deployment Manager
1.2.1.16 |  |  | 1.1.1.16 |  |  | Document Project Plan for System Deployment | System Deployment Manager
1.2.1.17 |  |  | 1.1.1.17 |  |  | Check for Consistency | System Deployment Manager
1.2.1.18 |  |  | 1.1.1.18 |  |  | Ensure Review of Project Plan | QA Analyst,System Deployment Manager[30%],Operations & Support Manager,PMO Prg. Mgr.
1.2.1.19 |  |  | 1.1.1.19 |  |  | Update Project Plan | System Deployment Manager
1.2.1.20 |  |  | 1.1.1.20 |  |  | Review Project Commitments | System Deployment Manager,Senior Manager
1.2.1.21 |  |  | 1.1.1.21 |  |  | Communicate Project Plan | System Deployment Manager
1.2.2 |  | 1.1.2 |  |  |  | Identify Site-Specific Gaps
1.2.2.1 |  |  | 1.1.2.1 |  |  | Review Application & System Documentation | Site1 Deployment Manager,Pilot Site Deployment Manager,Site2 Deployment Manager
1.2.2.2 |  |  | 1.1.2.2 |  |  | Identify Infrastructure Changes | Site1 Deployment Manager,Pilot Site Deployment Manager,Site2 Deployment Manager
1.2.2.3 |  |  | 1.1.2.3 |  |  | Identify Security Gaps | Site1 Deployment Manager,Pilot Site Deployment Manager,Site2 Deployment Manager
1.2.2.4 |  |  | 1.1.2.4 |  |  | Identify Migration Gaps | Site1 Deployment Manager,Pilot Site Deployment Manager,Site2 Deployment Manager
1.2.2.5 |  |  | 1.1.2.5 |  |  | Document Site Specific Gap Analysis | Pilot Site Deployment Manager,Site1 Deployment Manager,Site2 Deployment Manager
1.2.3 |  | 1.1.3 |  |  |  | Analyze System Deployment Gaps
1.2.3.1 |  |  | 1.1.3.1 |  |  | Review Site Specific Gap Analysis Document(s) | System Owner,System Deployment Manager
1.2.3.2 |  |  | 1.1.3.2 |  |  | Prioritize Gaps to be Addressed | Pilot Site Deployment Manager[20%],Site1 Deployment Manager[20%]
1.2.3.3 |  |  | 1.1.3.3 |  |  | Update Site Specific Gap Analysis Document | Pilot Site Deployment Manager[20%],Site1 Deployment Manager[20%]
1.2.3.4 |  |  | 1.1.3.4 |  |  | Approve Site Specific Gap Analysis Document | System Deployment Manager,Pilot Site Deployment Manager[20%],Site1 Deployment Manager[20%]
1.2.3.5 |  |  | 1.1.3.5 |  |  | Prepare System Deployment Gap Analysis Document | System Deployment Manager
1.2.3.6 |  |  | 1.1.3.6 |  |  | Check for Consistency in Gap Analysis Documents (Sites and Total System) | System Deployment Manager
1.2.3.7 |  |  | 1.1.3.7 |  |  | Review System Deployment Gap Analysis Document | QA Analyst[20%],Development System Deployment Manager,Business Project Champion[10%],Business Team Member(s),Pilot Site Deployment Manager[20%],Site1 Deployment Manager[20%]
1.2.3.8 |  |  | 1.1.3.8 |  |  | Obtain Approval and Baseline System Deployment Gap Analysis Docume | CM Lead[30%],Senior Manager,Business Project Champion,System Deployment Manager[30%]
1.2.4 |  | 1.1.4 |  |  |  | Document Deployment Strategy | System Deployment Manager
1.2.5 |  | 1.1.5 |  |  |  | Conduct Define Tollgate
1.2.5.1 |  |  | 1.1.5.1 |  |  | Update Plan(s) for Prepare Phase | System Deployment Manager[50%]
1.2.5.2 |  |  | 1.1.5.2 |  |  | Request for Tollgate Review | System Deployment Manager[30%]
1.2.5.3 |  |  | 1.1.5.3 |  |  | Review Configuration Status Account (CSA) Report | QA Analyst,CM Lead[20%]
1.2.5.4 |  |  | 1.1.5.4 |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst,CM Lead[20%]
1.2.5.5 |  |  | 1.1.5.5 |  |  | Provide Support to Update Business Case | System Deployment Manager[20%]
1.2.5.6 |  |  | 1.1.5.6 |  |  | Prepare for the Project Tollgate | Stakeholder[30%]
1.2.5.6.1 |  |  |  | 1.1.5.6.1 |  | Conduct Supplier Reviews | System Deployment Manager[50%]
1.2.5.6.2 |  |  |  | 1.1.5.6.2 |  | Use results of reviews to improve Performance | System Deployment Manager[50%]
1.2.5.6.3 |  |  |  | 1.1.5.6.3 |  | Revise Supplier agreement and plans as necessary | System Deployment Manager[50%]
1.2.5.7 |  |  | 1.1.5.7 |  |  | Review Plan for Next Phase | PMO Prg. Mgr.[50%]
1.2.5.8 |  |  | 1.1.5.8 |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%]
1.2.5.9 |  |  | 1.1.5.9 |  |  | Update Tollgate Review Report | System Deployment Manager[30%]
1.2.5.10 |  |  | 1.1.5.10 |  |  | Communicate Define Tollgate Review Report | Senior Manager[20%],Supplier[20%],Pilot Site Deployment Manager,PMO Prg. Mgr.[20%],Site1 Deployment Manager,System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%],CM Lead
1.3 | 1.2 |  |  |  |  | Define Phase Tollgate Conducted
1.4 | 1.3 |  |  |  |  | Construct
1.4.1 |  | 1.3.1 |  |  |  | Procure Supplier/Products for System Deployment
1.4.1.1 |  |  | 1.3.1.1 |  |  | Engage Time and Material Resources | System Deployment Manager,Senior Manager,WWP/Contract Manager
1.4.1.2 |  |  | 1.3.1.2 |  |  | Get Single Sourcing Justification Letter and Obtain Approval | System Deployment Manager[30%],Senior Manager[30%]
1.4.1.3 |  |  | 1.3.1.3 |  |  | Procure Products | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.4 |  |  | 1.3.1.4 |  |  | Define Sourcing Requirements
1.4.1.4.1 |  |  |  | 1.3.1.4.1 |  | Determine Acquisition Type | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.4.2 |  |  |  | 1.3.1.4.2 |  | Establish Cross-Functional Team | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.4.3 |  |  |  | 1.3.1.4.3 |  | Define Requirements | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.4.4 |  |  |  | 1.3.1.4.4 |  | Create and Approve Acquisition Document | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.5 |  |  | 1.3.1.5 |  |  | Select Suppliers
1.4.1.5.1 |  |  |  | 1.3.1.5.1 |  | Develop RFP | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.5.2 |  |  |  | 1.3.1.5.2 |  | Develop Supplier evaluation criteria | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.5.3 |  |  |  | 1.3.1.5.3 |  | Identify potential suppliers | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.5.4 |  |  |  | 1.3.1.5.4 |  | Distribute proposals | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.5.5 |  |  |  | 1.3.1.5.5 |  | Evaluate proposals | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.5.6 |  |  |  | 1.3.1.5.6 |  | Approve Supplier Downselect | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.6 |  |  | 1.3.1.6 |  |  | Establish Agreement
1.4.1.6.1 |  |  |  | 1.3.1.6.1 |  | Develop Negotiation Strategy | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.6.2 |  |  |  | 1.3.1.6.2 |  | Negotiate Agreement | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.6.3 |  |  |  | 1.3.1.6.3 |  | Evaluate and select final supplier | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.6.4 |  |  |  | 1.3.1.6.4 |  | Create and approve agreement | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.1.6.5 |  |  |  | 1.3.1.6.5 |  | Communicate agreement | System Deployment Manager,WWP/Contract Manager,SAM Analyst
1.4.2 |  | 1.3.2 |  |  |  | Develop System Deployment Plan (DP)
1.4.2.1 |  |  | 1.3.2.1 |  |  | Develop Pilot Deployment Plan (PDP) for the Pilot Site
1.4.2.1.1 |  |  |  | 1.3.2.1.1 |  | Develop Operations, Maintenance and Support Plan for Pilot Site | Site Operations and Support Manager,Pilot Site Deployment Manager,System Deployment Manager
1.4.2.1.2 |  |  |  | 1.3.2.1.2 |  | Procure Supplier/Products for the Pilot Site | System Deployment Manager,Pilot Site Deployment Manager
1.4.2.1.3 |  |  |  | 1.3.2.1.3 |  | Develop Security Plan | Site Lead,Pilot Site Deployment Manager
1.4.2.1.4 |  |  |  | 1.3.2.1.4 |  | Develop Data Conversion an Load Plan | Site Lead,Pilot Site Deployment Manager
1.4.2.1.5 |  |  |  | 1.3.2.1.5 |  | Develop Test Plansfor the site | Site Lead,Pilot Site Deployment Manager
1.4.2.1.6 |  |  |  | 1.3.2.1.6 |  | Develop Application Disaster Recovery Plan for the Site | Site Operations and Support Manager
1.4.2.1.7 |  |  |  | 1.3.2.1.7 |  | Develop Pilot Deployment Schedule | Site Lead,Pilot Site Deployment Manager
1.4.2.1.8 |  |  |  | 1.3.2.1.8 |  | Document Pilot Deployment Document (PDP) | Site Lead,Pilot Site Deployment Manager
1.4.2.2 |  |  | 1.3.2.2 |  |  | Review Pilot Deployment Plan | Site Lead,Pilot Site Deployment Manager,System Deployment Team,Site Test Manager,Site Operations and Support Manager,QA Analyst,Site Deployment Team Member(s)
1.4.2.2.1 |  |  |  | 1.3.2.2.1 |  | Peer Review | Pilot Site Deployment Manager
1.4.2.2.1.1 |  |  |  |  | 1.3.2.2.1.1 | Initiate Request for Review Setup
1.4.2.2.1.2 |  |  |  |  | 1.3.2.2.1.2 | Setup Review Meeting
1.4.2.2.1.3 |  |  |  |  | 1.3.2.2.1.3 | Prepare for Peer Review Meeting
1.4.2.2.1.4 |  |  |  |  | 1.3.2.2.1.4 | Conduct Peer Review Meeting
1.4.2.2.1.5 |  |  |  |  | 1.3.2.2.1.5 | Incorporate Peer Review Feedback
1.4.2.2.1.6 |  |  |  |  | 1.3.2.2.1.6 | Verify Closure of Action Items
1.4.2.3 |  |  | 1.3.2.3 |  |  | Obtain Approval and Baseline PDP | CM Lead[30%],Pilot Site Deployment Manager,System Deployment Manager,Site Operations and Support Manager
1.4.2.4 |  |  | 1.3.2.4 |  |  | Develop Site Deployment Plan (SDP) for the Site <1>
1.4.2.4.1 |  |  |  | 1.3.2.4.1 |  | Develop Operations, Maintenance and Support Plan for Site < 1> | Site1 Operations and Support Manager,Site1 Deployment Manager,System Deployment Manager
1.4.2.4.2 |  |  |  | 1.3.2.4.2 |  | Procure Supplier/Products for the Site <1> | System Deployment Manager,Pilot Site Deployment Manager
1.4.2.4.3 |  |  |  | 1.3.2.4.3 |  | Develop Security Plan | Site1 Lead,Site1 Deployment Manager
1.4.2.4.4 |  |  |  | 1.3.2.4.4 |  | Develop Data Conversion an Load Plan | Site1 Lead,Site1 Deployment Manager
1.4.2.4.5 |  |  |  | 1.3.2.4.5 |  | Develop Test Plans for the site <1> | Site1 Lead,Site1 Deployment Manager
1.4.2.4.6 |  |  |  | 1.3.2.4.6 |  | Develop Application Disaster Recovery Plan for the Site <1> | Site1 Operations and Support Manager
1.4.2.4.7 |  |  |  | 1.3.2.4.7 |  | Develop Site Deployment Schedule | Pilot Site1 Deployment Manager,Site1 Lead
1.4.2.4.8 |  |  |  | 1.3.2.4.8 |  | Document Site Deployment Document (SDP) | Site1 Deployment Manager,Site1 Lead
1.4.2.5 |  |  | 1.3.2.5 |  |  | Review Site Deployment Plan for the Site <1> | Site1 Deployment Team Member(s),Site1 Operations and Support Manager,Site1 Test Manager,Site1 Deployment Manager,QA Analyst,Site1 Lead
1.4.2.5.1 |  |  |  | 1.3.2.5 |  | Peer Review | Site1 Deployment Manager
1.4.2.5.1.1 |  |  |  |  | 1.3.2.5.1 | Initiate Request for Review Setup
1.4.2.5.1.2 |  |  |  |  | 1.3.2.5.2 | Setup Review Meeting
1.4.2.5.1.3 |  |  |  |  | 1.3.2.5.3 | Prepare for Peer Review Meeting
1.4.2.5.1.4 |  |  |  |  | 1.3.2.5.4 | Conduct Peer Review Meeting
1.4.2.5.1.5 |  |  |  |  | 1.3.2.5.5 | Incorporate Peer Review Feedback
1.4.2.5.1.6 |  |  |  |  | 1.3.2.5.6 | Verify Closure of Action Items
1.4.2.6 |  |  |  | 1.3.2.6 |  | Obtain Approval and Baseline SDP for Site<1> | CM Lead[30%],Site1 Deployment Manager,System Deployment Manager,Site Operations and Support Manager
1.4.2.7 |  |  |  | 1.3.2.7 |  | Develop Training Plan for System Deployment | System Deployment Manager,System Deployment Team
1.4.2.8 |  |  |  | 1.3.2.8 |  | Develop System Deployment Schedule | System Deployment Manager,System Deployment Team
1.4.2.9 |  |  |  | 1.3.2.9 |  | Document System Deployment Plan (DP) | System Deployment Manager,System Deployment Team
1.4.2.10 |  |  |  | 1.3.2.10 |  | Check for Consistency with SDP(s) | System Deployment Manager,System Deployment Team
1.4.2.11 |  |  |  | 1.3.2.11 |  | Review System Deployment Plan | System Deployment Manager,Site2 Deployment Manager,Pilot Site Deployment Manager,QA Analyst,Site1 Deployment Manager
1.4.2.12 |  |  |  | 1.3.2.12 |  | Obtain Approval and Baseline DP | System Deployment Manager,Site2 Deployment Manager,Pilot Site Deployment Manager,Senior Manager,Site1 Deployment Manager
1.4.3 |  | 1.3.3 |  |  |  | System Deployment Plan Completed
1.4.4 |  | 1.3.4 |  |  |  | Prepare Pilot Site
1.4.4.1 |  |  | 1.3.4.1. |  |  | Prepare Site for System Changes
1.4.4.1.1 |  |  |  | 1.3.4.1.1 |  | Prepare Site for Infrastructure Changes | Pilot Site Lead,Pilot Site Test Manager,System Owner,Pilot Site Deployment Manager
1.4.4.1.2 |  |  |  | 1.3.4.1.2 |  | Prepare Site for Security Changes | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.1.3 |  |  |  | 1.3.4.1.3 |  | Prepare for Application Data Migration | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.2 |  |  | 1.3.4.2 |  |  | Create System Migration Plan for Pilot Site | System Owner,Pilot Site Deployment Manager,Pilot Site Test Manager,Pilot Site Lead
1.4.4.3 |  |  | 1.3.4.3 |  |  | Prepare Test Cases for the Pilot Site | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.4 |  |  | 1.3.4.4 |  |  | Apply Infrastructure Changes | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.5 |  |  | 1.3.4.5 |  |  | Apply Security Changes | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.6 |  |  | 1.3.4.6 |  |  | Convert and Migrate Data | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.7 |  |  | 1.3.4.7 |  |  | Update System Documentation and Test Plans for the Pilot Site | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.8 |  |  | 1.3.4.8 |  |  | Update Pilot Deployment Plan | Pilot Site Deployment Manager,Pilot Site Lead,Pilot Site Test Manager,System Owner
1.4.4.9 |  |  | 1.3.4.9 |  |  | Conduct Test and Pilot Site Readiness Review | QA Analyst,Pilot Site Test Manager,Pilot Site Lead,Senior Manager,System Owner,Pilot Site Deployment Manager
1.4.5 |  | 1.3.5 |  |  |  | Testing and Site Readiness Review Conducted for Pilot Site
1.4.6 |  | 1.3.6 |  |  |  | Prepare Site <1>
1.4.6.1 |  |  | 1.3.6.1 |  |  | Prepare Site for System Changes
1.4.6.1.1 |  |  |  | 1.3.6.1.1 |  | Prepare Site for Infrastructure Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.1.2 |  |  |  | 1.3.6.1.2 |  | Prepare Site for Security Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.1.3 |  |  |  | 1.3.6.1.3 |  | Prepare for Application Data Migration | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.2 |  |  | 1.3.6.2 |  |  | Create System Migration Plan for Site 1 | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.3 |  |  | 1.3.6.3 |  |  | Prepare Test Cases for the Site 1 | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.4 |  |  | 1.3.6.4 |  |  | Apply Infrastructure Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.5 |  |  | 1.3.6.5 |  |  | Apply Security Changes | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.6 |  |  | 1.3.6.6 |  |  | Convert and Migrate Data | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.7 |  |  | 1.3.6.7 |  |  | Update System Documentation and Test Plans for Site1 | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.8 |  |  | 1.3.6.8 |  |  | Update Site Deployment Plan | Site1 Deployment Manager,Site1 Test Manager,System Owner,Site1 Lead
1.4.6.9 |  |  | 1.3.6.9 |  |  | Conduct Test and Site Readiness Review | QA Analyst,Site1 Deployment Manager,Site1Test Manager,Senior Manager,System Owner,Site1 Lead
1.4.7 |  | 1.3.7 |  |  |  | Testing and Site Readiness Review Conducted for Site 1
1.4.8 |  | 1.3.8 |  |  |  | Update System Deployment Plan | System Deployment Manager
1.4.9 |  | 1.3.9 |  |  |  | Conduct Construct Tollgate
1.4.9.1 |  |  | 1.3.9.1 |  |  | Update Plan(s) for Prepare Phase | System Deployment Manager[50%]
1.4.9.2 |  |  | 1.3.9.2 |  |  | Request for Tollgate Review | System Deployment Manager[30%]
1.4.9.3 |  |  | 1.3.9.3 |  |  | Review Configuration Status Account (CSA) Report | QA Analyst,CM Lead[20%]
1.4.9.4 |  |  | 1.3.9.4 |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst,CM Lead[20%]
1.4.9.5 |  |  | 1.3.9.5 |  |  | Provide Support to Update Business Case | System Deployment Manager[20%]
1.4.9.6 |  |  | 1.3.9.6 |  |  | Prepare for the Project Tollgate | Stakeholder[30%]
1.4.9.6.1 |  |  |  | 1.3.9.6.1 |  | Conduct Supplier Reviews | System Deployment Manager[50%]
1.4.9.6.2 |  |  |  | 1.3.9.6.2 |  | Use results of reviews to improve Performance | System Deployment Manager[50%]
1.4.9.6.3 |  |  |  | 1.3.9.6.3 |  | Revise Supplier agreement and plans as necessary | System Deployment Manager[50%]
1.4.9.7 |  |  | 1.3.9.7 |  |  | Review Plan for Next Phase | PMO Prg. Mgr.[50%]
1.4.9.8 |  |  | 1.3.9.8 |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%]
1.4.9.9 |  |  | 1.3.9.9 |  |  | Update Tollgate Review Report | System Deployment Manager[30%]
1.4.9.10 |  |  | 1.3.9.10 |  |  | Communicate Construct Tollgate Review Report | Senior Manager[20%],Supplier[20%],Site1 Deployment Manager,PMO Prg. Mgr.[20%],Pilot Site Deployment Manager,System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%],CM Lead
1.5 | 1.4 |  |  |  |  | Construct Phase Tollgate Conducted
1.6 | 1.5 |  |  |  |  | Test
1.6.1 |  | 1.5.1 |  |  |  | Testing of Pilot Site
1.6.1.1 |  |  | 1.5.1.1 |  |  | Conduct System Testing at Pilot Site
1.6.1.1.1 |  |  |  | 1.5.1.1.1 |  | Execute System Tests | Pilot Site Lead,Pilot Site Deployment Manager[20%],Pilot Site Deployment Team Member[20%]
1.6.1.1.2 |  |  |  | 1.5.1.1.2 |  | Log Defects and Issues | Pilot Site Test Manager
1.6.1.1.3 |  |  |  | 1.5.1.1.3 |  | Prepare System Test Summary Report (STSR) at End of Cycle | Pilot Site Test Manager
1.6.1.1.4 |  |  |  | 1.5.1.1.4 |  | Review System Test Summary Report | Pilot Site Test Manager
1.6.1.1.5 |  |  |  | 1.5.1.1.5 |  | Generate Final STSR | Pilot Site Test Manager,Pilot Site Deployment Manager[20%]
1.6.1.1.6 |  |  |  | 1.5.1.1.6 |  | Plan Next Test Cycle | Pilot Site Test Manager
1.6.1.1.7 |  |  |  | 1.5.1.1.7 |  | Fix Defects and Issues | Pilot Site Deployment Manager
1.6.1.1.8 |  |  |  | 1.5.1.1.8 |  | Install and Configure System | Pilot Site Deployment Manager
1.6.1.1.9 |  |  |  | 1.5.1.1.9 |  | Verify System Installation and Configuration | Pilot Site Test Manager[30%],Pilot Site Deployment Manager,Pilot Site Lead[30%]
1.6.1.1.10 |  |  |  | 1.5.1.1.10 |  | Execute System Tests | Pilot Site Lead,Pilot Site Deployment Manager[20%],Pilot Site Deployment Team Member[20%]
1.6.1.1.11 |  |  |  | 1.5.1.1.11 |  | Verify Test Results | Pilot Site Deployment Team Member,Pilot Site Lead
1.6.1.2 |  |  | 1.5.1.2 |  |  | Conduct Acceptance Testing Readiness Review - Pilot Site
1.6.1.2.1 |  |  |  | 1.5.1.2.1 |  | Setup Test Environment at Pilot Site
1.6.1.2.1.1 |  |  |  |  | 1.5.1.2.1.1 | Install Test Environment | Pilot Site Test Manager
1.6.1.2.1.2 |  |  |  |  | 1.5.1.2.1.2 | Apply Infrastructure Changes | Pilot Site Lead,Pilot Site Test Manager
1.6.1.2.1.3 |  |  |  |  | 1.5.1.2.1.3 | Apply Security Changes | Pilot Site Test Manager,Pilot Site Lead
1.6.1.2.1.4 |  |  |  |  | 1.5.1.2.1.4 | Convert & Migrate Data | Pilot Site Test Manager,Pilot Site Lead
1.6.1.2.1.5 |  |  |  |  | 1.5.1.2.1.5 | Perform Checks to Verify Test Environment | Pilot Site Test Manager
1.6.1.2.1.6 |  |  |  |  | 1.5.1.2.1.6 | Fix Gaps Related to Test Environment | Pilot Site Test Manager
1.6.1.2.1.7 |  |  |  |  | 1.5.1.2.1.7 | Verify / Audit Test Environment | Pilot Site Lead[30%],Pilot Site Deployment Manager,Pilot Site Test Manager[30%]
1.6.1.2.2 |  |  |  | 1.5.1.2.2 |  | Test Build & Installation of System at Piot Site
1.6.1.2.2.1 |  |  |  |  | 1.5.1.2.2.1 | Fix Defects & Issues | Pilot Site Deployment Manager[20%],Pilot Site Lead,Pilot Site Deployment Team Member[20%]
1.6.1.2.2.2 |  |  |  |  | 1.5.1.2.2.2 | Update Installation & System Documentation | Pilot Site Lead,Pilot Site Deployment Manager[20%],Pilot Site Deployment Team Member[20%]
1.6.1.2.2.3 |  |  |  |  | 1.5.1.2.2.3 | Verify Installation & System Documentation | Pilot Site Test Manager
1.6.1.2.2.4 |  |  |  |  | 1.5.1.2.2.4 | Obtain Approval & Check In System Documentation, Installation Guide & Source | CM Lead,Pilot Site Test Manager[30%],Pilot Site Deployment Manager
1.6.1.2.2.5 |  |  |  |  | 1.5.1.2.2.5 | Install & Configure Application | Pilot SiteTest Manager,Pilot Site Lead[30%]
1.6.1.2.3 |  |  |  | 1.5.1.2.3 |  | Conduct Acceptance Testing Readiness Review Meeting | Senior Manager,System Owner,End User,Piot Site Deployment Manager,Pilot Site Lead,QA Analyst,Pilot Site Test Manager
1.6.1.3 |  |  | 1.5.1.3 |  |  | Conduct Acceptance Testing at Pilot Site
1.6.1.3.1 |  |  |  | 1.5.1.3.1 |  | Execute User Acceptance Tests | Pilot Site Deployment Manager[30%],Pilot Site Deployment Team Member[30%],End User
1.6.1.3.2 |  |  |  | 1.5.1.3.2 |  | Verify Test Results | Pilot Site Deployment Manager
1.6.1.3.3 |  |  |  | 1.5.1.3.3 |  | Log Defects & Issues | End User[30%],Pilot Site Deployment Manage
1.6.1.3.4 |  |  |  | 1.5.1.3.4 |  | Prepare Test Summary Report at End of Cycle | Pilot Site Deployment Manager
1.6.1.3.5 |  |  |  | 1.5.1.3.5 |  | Review Test Summary Report | Pilot Site Deployment Manage,End User[30%]
1.6.1.3.6 |  |  |  | 1.5.1.3.6 |  | Generate Final Test Summary Report | Pilot Site Deployment Manager
1.6.1.3.7 |  |  |  | 1.5.1.3.7 |  | Sign-off on User Acceptance Tests | Pilot Site Deployment Manage,End User[30%]
1.6.1.4 |  |  | 1.5.1.4 |  |  | Acceptance Testing Conducted for Pilot Site
1.6.1.5 |  |  | 1.5.1.5 |  |  | Plan Next Cycle | Pilot Site Deployment Manager[20%],Pilot Site Lead,Pilot Site Deployment Team Member[20%]
1.6.1.6 |  |  | 1.5.1.6 |  |  | Analyze Defects & Change Requests at Pilot Site | End User[30%],Pilot Site Deployment Manager,Pilot Site Test Manager[30%],Pilot Site Lead[30%]
1.6.1.7 |  |  | 1.5.1.7 |  |  | Verify Production Readiness at Pilot Site | Pilot Site Lead,Pilot Site Test Manager
1.6.2 |  | 1.5.2 |  |  |  | Testing of Site <1>
1.6.2.1 |  |  | 1.5.2.1 |  |  | Conduct System Testing at Site <1>
1.6.2.1.1 |  |  |  | 1.5.2.1.1 |  | Execute System Tests | Site1 Lead,Site1 Deployment Manager[20%],Site1 Deployment Team Member[20%]
1.6.2.1.2 |  |  |  | 1.5.2.1.2 |  | Log Defects and Issues | Site1 Test Manager
1.6.2.1.3 |  |  |  | 1.5.2.1.3 |  | Prepare System Test Summary Report (STSR) at End of Cycle | Site1 Test Manager
1.6.2.1.4 |  |  |  | 1.5.2.1.4 |  | Review System Test Summary Report | Site1 Test Manager
1.6.2.1.5 |  |  |  | 1.5.2.1.5 |  | Generate Final STSR | Site1 Test Manager,Site1 Deployment Manager[20%]
1.6.2.1.6 |  |  |  | 1.5.2.1.6 |  | Plan Next Test Cycle | Site1 Test Manager
1.6.2.1.7 |  |  |  | 1.5.2.1.7 |  | Fix Defects and Issues | Site1 Deployment Manager
1.6.2.1.8 |  |  |  | 1.5.2.1.8 |  | Install and Configure System | Site1 Deployment Manager
1.6.2.1.9 |  |  |  | 1.5.2.1.9 |  | Verify System Installation and Configuration | Site1 Test Manager[30%],Site1 Deployment Manager,Site1 Lead[30%]
1.6.2.1.10 |  |  |  | 1.5.2.1.10 |  | Execute System Tests | Site1 Lead,Site1 Deployment Manager[20%],Site1 Deployment Team Member[20%]
1.6.2.1.11 |  |  |  | 1.5.2.1.11 |  | Verify Test Results | Site1 Deployment Team Member,Site1 Lead
1.6.2.2 |  |  | 1.5.2.2 |  |  | Conduct Acceptance Testing Readiness Review - Site <1>
1.6.2.2.1 |  |  |  | 1.5.2.2.1 |  | Setup Test Environment at Site<1>
1.6.2.2.1.1 |  |  |  |  | 1.5.2.2.1 | Install Test Environment | Site1 Test Manager
1.6.2.2.1.2 |  |  |  |  | 1.5.2.2.2 | Apply Infrastructure Changes | Site1 Lead,Site1 Test Manager
1.6.2.2.1.3 |  |  |  |  | 1.5.2.2.3 | Apply Security Changes | Site1 Test Manager,Site1 Lead
1.6.2.2.1.4 |  |  |  |  | 1.5.2.2.4 | Convert & Migrate Data | Site1 Test Manager,Site1 Lead
1.6.2.2.1.5 |  |  |  |  | 1.5.2.2.5 | Perform Checks to Verify Test Environment | Site1 Test Manager
1.6.2.2.1.6 |  |  |  |  | 1.5.2.2.6 | Fix Gaps Related to Test Environment | Site1 Test Manager
1.6.2.2.1.7 |  |  |  |  | 1.5.2.2.7 | Verify / Audit Test Environment | Site1 Lead[30%],Site1 Deployment Manager,Site1 Test Manager[30%]
1.6.2.2.2 |  |  |  | 1.5.2.2.2 |  | Test Build & Installation of System at Site <>
1.6.2.2.2.1 |  |  |  |  | 1.5.2.2.2.1 | Fix Defects & Issues | Site1 Deployment Team Member[20%],Site1 Deployment Manager[20%],Site1 Lead
1.6.2.2.2.2 |  |  |  |  | 1.5.2.2.2.2 | Update Installation & System Documentation | Site1 Deployment Team Member[20%],Site1 Lead,Site1 Deployment Manager[20%]
1.6.2.2.2.3 |  |  |  |  | 1.5.2.2.2.3 | Verify Installation & System Documentation | Site1 Test Manager
1.6.2.2.2.4 |  |  |  |  | 1.5.2.2.2.4 | Obtain Approval & Check In System Documentation, Installation Guide & Source | CM Lead,Site1 Test Manager[30%],Site1 Deployment Manager
1.6.2.2.2.5 |  |  |  |  | 1.5.2.2.2.5 | Install & Configure Application | Site1Test Manager,Site1 Lead[30%]
1.6.2.2.3 |  |  |  | 1.5.2.2.3 |  | Conduct Acceptance Testing Readiness Review Meeting of System at Site <> | Senior Manager,System Owner,End User,Site1 Lead,Site1 Test Manager,QA Analyst,Piot Site Deployment Manager
1.6.2.3 |  |  | 1.5.2.3 |  |  | Conduct Acceptance Testing at Site <1>
1.6.2.3.1 |  |  |  | 1.5.2.3.1 |  | Execute User Acceptance Tests | Site1 Deployment Manager[30%],Site1 Deployment Team Member[30%],End User
1.6.2.3.2 |  |  |  | 1.5.2.3.2 |  | Verify Test Results | Site1 Deployment Manager
1.6.2.3.3 |  |  |  | 1.5.2.3.3 |  | Log Defects & Issues | End User[30%],Site1 Deployment Manage
1.6.2.3.4 |  |  |  | 1.5.2.3.4 |  | Prepare Test Summary Report at End of Cycle | Site1 Deployment Manager
1.6.2.3.5 |  |  |  | 1.5.2.3.5 |  | Review Test Summary Report | Site1 Deployment Manage,End User[30%]
1.6.2.3.6 |  |  |  | 1.5.2.3.6 |  | Generate Final Test Summary Report | Site1 Deployment Manager
1.6.2.3.7 |  |  |  | 1.5.2.3.7 |  | Sign-off on User Acceptance Tests | Site1 Deployment Manage,End User[30%]
1.6.2.4 |  |  | 1.5.2.4 |  |  | Acceptance Testing Conducted for Site <1>
1.6.2.5 |  |  | 1.5.2.5 |  |  | Plan Next Cycle | Site1 Deployment Team Member[20%],Site1 Lead,Site1 Deployment Manager[20%]
1.6.2.6 |  |  | 1.5.2.6 |  |  | Analyze Defects & Change Requests at Site <1> | End User[30%],Site1 Deployment Manager,Site1 Test Manager[30%],Site1 Lead[30%]
1.6.2.7 |  |  | 1.5.2.7 |  |  | Verify Production Readiness at Site <1> | Site1 Lead,Site1 Test Manager
1.6.3 |  | 1.5.3 |  |  |  | Conduct Test Phase Tollgate
1.6.3.1 |  |  | 1.5.3.1 |  |  | Update Plan(s) for Prepare Phase | System Deployment Manager[50%]
1.6.3.2 |  |  | 1.5.3.2 |  |  | Request for Tollgate Review | System Deployment Manager[30%]
1.6.3.3 |  |  | 1.5.3.3 |  |  | Review Configuration Status Account (CSA) Report | QA Analyst,CM Lead[20%]
1.6.3.4 |  |  | 1.5.3.4 |  |  | Review Work Product Baseline and Conduct CM Audit | QA Analyst,CM Lead[20%]
1.6.3.5 |  |  | 1.5.3.5 |  |  | Provide Support to Update Business Case | System Deployment Manager[20%]
1.6.3.6 |  |  | 1.5.3.6 |  |  | Prepare for the Project Tollgate | Stakeholder[30%]
1.6.3.6.1 |  |  |  | 1.5.3.6.1 |  | Conduct Supplier Reviews | System Deployment Manager[50%]
1.6.3.6.2 |  |  |  | 1.5.3.6.2 |  | Use results of reviews to improve Performance | System Deployment Manager[50%]
1.6.3.6.3 |  |  |  | 1.5.3.6.3 |  | Revise Supplier agreement and plans as necessary | System Deployment Manager[50%]
1.6.3.7 |  |  | 1.5.3.7 |  |  | Review Plan for Next Phase | PMO Prg. Mgr.[50%]
1.6.3.8 |  |  | 1.5.3.8 |  |  | Close Tollgate Observations | PMO Prg. Mgr.[30%],QA Analyst[30%],Supplier[30%]
1.6.3.9 |  |  | 1.5.3.9 |  |  | Update Tollgate Review Report | System Deployment Manager[30%]
1.6.3.10 |  |  | 1.5.3.10 |  |  | Communicate Test Tollgate Review Report | Senior Manager[20%],Supplier[20%],Site1 Deployment Manager,PMO Prg. Mgr.[20%],Pilot Site Deployment Manager,System Deployment Manager[20%],Process Engineer[20%],QA Analyst[20%],CM Lead
1.6.3.11 |  |  | 1.5.3.11 |  |  | Accept Product | System Deployment Manager[50%]
1.6.3.11.1 |  |  |  | 1.5.3.11.1 |  | Accept the acquired product
1.6.3.11.2 |  |  |  | 1.5.3.11.2 |  | Transition product to Operations
1.6.3.11.3 |  |  |  | 1.5.3.11.3 |  | Review Supplier Performance
1.6.3.11.4 |  |  |  | 1.5.3.11.4 |  | Execute Supplier payment process
1.7 | 1.6 |  |  |  |  | Test Phase Tollgate Conducted
1.8 | 1.7 |  |  |  |  | Deploy
1.8.1 |  | 1.7.1 |  |  |  | Deploy at Pilot Site
1.8.1.1 |  |  | 1.7.1.1 |  |  | Migrate to New System at Pilot Site
1.8.1.1.1 |  |  |  | 1.7.1.1.1 | Execute Migration |  | Pilot Site Lead
1.8.1.1.2 |  |  |  | 1.7.1.1.2 | Perform Checks to Verify Migration |  | Pilot Site Lead,Pilot Site Deployment Manager[30%]
1.8.1.1.3 |  |  |  | 1.7.1.1.3 |  | Check Contingency Plan for Alternative(s) | Pilot Site Lead,Pilot Site Deployment Manager
1.8.1.1.4 |  |  |  | 1.7.1.1.4 |  | Modify System Environment or Components | Pilot Site Lead
1.8.1.1.5 |  |  |  | 1.7.1.1.5 |  | Execute Back out Plan | Pilot Site Deployment Manager
1.8.1.1.6 |  |  |  | 1.7.1.1.6 |  | Communicate To Stakeholders | Pilot Site Deployment Manager,Senior Manager,Pilot Site Manager
1.8.1.1.7 |  |  |  | 1.7.1.1.7 |  | Communicate Deployment Status | System Deployment Manager
1.8.1.2 |  |  | 1.7.1.2 |  |  | Migrated to New System at Pilot Site
1.8.1.3 |  |  | 1.7.1.3 |  |  | Update Generic Site Deployment Materials & System Documentation | Pilot Site Deployment Manage,System Deployment Manager
1.8.1.4 |  |  | 1.7.1.4 |  |  | Transition to Operations at Pilot Site
1.8.1.4.1 |  |  |  | 1.7.1.4.1 |  | Support New System | Pilot Site Deployment Team Member,Pilot Site Deployment Manager
1.8.1.4.2 |  |  |  | 1.7.1.4.2 |  | Transfer Ownership to System Owner | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team
1.8.1.4.3 |  |  |  | 1.7.1.4.3 |  | Archive System Documentation, Training Material & Application/System Components | Pilot Site Deployment Manager,System Owner,Pilot Site Operations & Support Team
1.8.1.4.4 |  |  |  | 1.7.1.4.4 |  | Train Operations Team | Pilot Site Operations & Support Team,System Owner,Pilot Site Deployment Manager
1.8.1.5 |  |  | 1.7.1.5 |  |  | De-Install Legacy System at Pilot Site | Pilot Site Deployment Manager
1.8.1.6 |  |  | 1.7.1.6 |  |  | Legacy System De-Installed at Pilot Site
1.8.2 |  | 1.7.1 |  |  |  | Deploy at Site <1>
1.8.2.1 |  |  | 1.7.2.1 |  |  | Migrate to New System at at Site <1>
1.8.2.1.1 |  |  |  | 1.7.2.1.1 |  | Execute Migration | Site1 Lead
1.8.2.1.2 |  |  |  | 1.7.2.1.2 |  | Perform Checks to Verify Migration | Site1 Deployment Manager[30%],Site1 Lead
1.8.2.1.3 |  |  |  | 1.7.2.1.3 |  | Check Contingency Plan for Alternative(s) | Site1 Deployment Manager,Site1 Lead
1.8.2.1.4 |  |  |  | 1.7.2.1.4 |  | Modify System Environment or Components | Site1 Lead
1.8.2.1.5 |  |  |  | 1.7.2.1.5 |  | Execute Back out Plan | Site1 Deployment Manager
1.8.2.1.6 |  |  |  | 1.7.2.1.6 |  | Communicate To Stakeholders | Site1 Manager,Senior Manager,Site1 Deployment Manager
1.8.2.1.7 |  |  |  | 1.7.2.1.7 |  | Communicate Deployment Status | System Deployment Manager
1.8.2.2 |  |  | 1.7.2.2 |  |  | Migrated to New System at at Site <1>
1.8.2.3 |  |  | 1.7.2.3 |  |  | Update Generic Site Deployment Materials & System Documentation | Site1 Deployment Manage,System Deployment Manager
1.8.2.4 |  |  | 1.7.2.4 |  |  | Transition to Operations at at Site <1>
1.8.2.4.1 |  |  |  | 1.7.2.4.1 |  | Support New System | Site1 Deployment Manager,Site1 Deployment Team Member
1.8.2.4.2 |  |  |  | 1.7.2.4.2 |  | Transfer Ownership to System Owner | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.8.2.4.3 |  |  |  | 1.7.2.4.3 |  | Archive System Documentation, Training Material & Application/System Components | Site1 Operations & Support Team,System Owner,Site1 Deployment Manager
1.8.2.4.4 |  |  |  | 1.7.2.4.4 |  | Train Operations Team | Site1 Deployment Manager,System Owner,Site1 Operations & Support Team
1.8.2.5 |  |  | 1.7.2.5 |  |  | De-Install Legacy System at at Site <1> | Site1 Deployment Manager
1.8.2.6 |  |  | 1.7.2.6 |  |  | Legacy System De-Installed at Site <1>
1.8.3 |  | 1.7.3 |  |  |  | Project Close
1.8.3.1 |  |  | 1.7.3.1 |  |  | Conduct Post-Project Review
1.8.3.1.1 |  |  |  | 1.7.3.1.1 |  | Develop Post Project Review Breakout Session Topics & Agenda | Pilot Site Deployment Manager,Site1 Deployment Manager,System Deployment Manager,CM Lead,QA Analyst
1.8.3.1.2 |  |  |  | 1.7.3.1.2 |  | Conduct Post Project Review Meeting | Pilot Site Deployment Manager,Site1 Deployment Manager,System Deployment Manager,CM Lead,QA Analyst
1.8.3.1.3 |  |  |  | 1.7.3.1.3 |  | Complete Post Project Review Report | Pilot Site Deployment Manager,Site1 Deployment Manager,System Deployment Manager,CM Lead,QA Analyst
1.8.3.1.4 |  |  |  | 1.7.3.1.4 |  | Create Project Role Feedback Forms | Pilot Site Deployment Manager,Site1 Deployment Manager,System Deployment Manager,CM Lead,QA Analyst
1.8.3.2 |  |  | 1.7.3.2 |  |  | Archive Documents | System Deployment Manager,CM Lead,QA Analyst
1.8.3.3 |  |  | 1.7.3.3 |  |  | Close Project formally and Communicate | System Deployment Manager
1.9 | 1.8 |  |  |  |  | Deployment Project <PTS -ID> Closed
1.1 | [5 empty] | Project Support Activities
1.10.1 | [5 empty] | Manage Requirements
1.10.1.1 | [5 empty] | Understand Change in Requirements
1.10.1.2 | [5 empty] | Perform Detailed Impact Analysis
1.10.1.3 | [5 empty] | Raise Requirements Change Request (RCR) Form
1.10.1.4 | [5 empty] | Review through Requirements Change Control Board (RCCB)
1.10.1.5 | [5 empty] | Re-Estimate & Re-Plan the Project
1.10.1.6 | [5 empty] | Obtain Approval from Senior Manager for Change in Cost & Schedule | Senior Manager,System Deployment Manager[30%]
1.10.1.7 | [5 empty] | Update & Baseline Project Plan
1.10.1.8 | [5 empty] | Communicate Changes in Project Plan
1.10.2 | [5 empty] | Change Control
1.10.2.1 | [5 empty] | Review Impact on CM Repository | CM Lead
1.10.2.2 | [5 empty] | Review Impact on Work Products | System Deployment Manager
1.10.2.3 | [5 empty] | Update Change Register | CM Lead
1.10.2.4 | [5 empty] | Review through Change Control Board (CCB) | System Deployment Manager
1.10.2.5 | [5 empty] | Update Change Register
1.10.2.6 | [5 empty] | Update Change Register with Closure Details
1.10.3 | [5 empty] | Project Monitoring and Control
1.10.3.1 | [5 empty] | Monitor Supplier Status
1.10.3.1.1 | [5 empty] | Monitor Supplier Status 1 | System Deployment Manager
1.10.3.1.2 | [5 empty] | Monitor Supplier Status 2 | System Deployment Manager
1.10.3.1.3 | [5 empty] | Monitor Supplier Status 3 | System Deployment Manager
1.10.3.1.4 | [5 empty] | Monitor Supplier Status 4 | System Deployment Manager
1.10.3.1.5 | [5 empty] | Monitor Supplier Status 5 | System Deployment Manager
1.10.3.2 | [5 empty] | Update Project Log , Project Plan and Project Schedule | System Deployment Manager
1.10.3.2.1 | [5 empty] | Update Project Log , Project Plan and Project Schedule 1 | System Deployment Manager
1.10.3.2.2 | [5 empty] | Update Project Log , Project Plan and Project Schedule 2 | System Deployment Manager
1.10.3.2.3 | [5 empty] | Update Project Log , Project Plan and Project Schedule 3 | System Deployment Manager
1.10.3.2.4 | [5 empty] | Update Project Log , Project Plan and Project Schedule 4 | System Deployment Manager
1.10.3.2.5 | [5 empty] | Update Project Log , Project Plan and Project Schedule 5
1.10.3.2.6 | [5 empty] | Update Project Log , Project Plan and Project Schedule 6
1.10.3.2.7 | [5 empty] | Update Project Log , Project Plan and Project Schedule 7
1.10.3.2.8 | [5 empty] | Update Project Log , Project Plan and Project Schedule 8
1.10.3.2.9 | [5 empty] | Update Project Log , Project Plan and Project Schedule 9
1.10.3.2.10 | [5 empty] | Update Project Log , Project Plan and Project Schedule 10
1.10.3.2.11 | [5 empty] | Update Project Log , Project Plan and Project Schedule 11
1.10.3.2.12 | [5 empty] | Update Project Log , Project Plan and Project Schedule 12
1.10.3.3 | [5 empty] | Provide Measurement Results Based on SDP-21 Metrics | System Deployment Manager
1.10.3.3.1 | [5 empty] | Submit SDP-21 Standard Metrics
1.10.3.3.1.1 | [5 empty] | Submit SDP-21 Standard Metrics 1
1.10.3.3.1.2 | [5 empty] | Submit SDP-21 Standard Metrics 2
1.10.3.3.1.3 | [5 empty] | Submit SDP-21 Standard Metrics 3
1.10.3.3.1.4 | [5 empty] | Submit SDP-21 Standard Metrics 4
1.10.3.3.1.5 | [5 empty] | Submit SDP-21 Standard Metrics 5
1.10.3.4 | [5 empty] | Update Project Tracking System (PTS)
1.10.3.4.1 | [5 empty] | Update Project Tracking System (PTS) 1
1.10.3.4.2 | [5 empty] | Update Project Tracking System (PTS) 2
1.10.3.4.3 | [5 empty] | Update Project Tracking System (PTS) 3
1.10.3.4.4 | [5 empty] | Update Project Tracking System (PTS) 4
1.10.3.4.5 | [5 empty] | Update Project Tracking System (PTS) 5
1.10.3.5 | [5 empty] | Conduct Milestone Reviews
1.10.3.5.1 | [5 empty] | Conduct Milestone Reviews 1
1.10.3.5.2 | [5 empty] | Conduct Milestone Reviews 2
1.10.3.5.3 | [5 empty] | Conduct Milestone Reviews 3
1.10.3.5.4 | [5 empty] | Conduct Milestone Reviews 4
1.10.3.5.5 | [5 empty] | Conduct Milestone Reviews 5
1.10.3.6 | [5 empty] | Conduct Senior Management Review (SMR) | System Deployment Manager
1.10.3.6.1 | [5 empty] | Conduct SMR meeting for the Project
1.10.3.6.1.1 | [5 empty] | Conduct SMR meeting for the Project 1
1.10.3.6.1.2 | [5 empty] | Conduct SMR meeting for the Project 2
1.10.3.6.1.3 | [5 empty] | Conduct SMR meeting for the Project 3
1.10.3.6.1.4 | [5 empty] | Conduct SMR meeting for the Project 4
1.10.3.6.1.5 | [5 empty] | Conduct SMR meeting for the Project 5
1.10.3.7 | [5 empty] | Conduct Progress Review Meetings | System Deployment Manager
1.10.3.7.1 | [5 empty] | Conduct Progress Review Meetings 1 | System Deployment Manager
1.10.3.7.2 | [5 empty] | Conduct Progress Review Meetings 2 | System Deployment Manager
1.10.3.7.3 | [5 empty] | Conduct Progress Review Meetings 3 | System Deployment Manager
1.10.3.7.4 | [5 empty] | Conduct Progress Review Meetings 4 | System Deployment Manager
1.10.3.7.5 | [5 empty] | Conduct Progress Review Meetings 5 | System Deployment Manager
1.10.3.7.6 | [5 empty] | Conduct Review with Stakeholders | System Deployment Manager
1.10.3.8 | [5 empty] | Monitor Project Plan and Schedule
1.10.3.8.1 | [5 empty] | Monitor Project Plan and Schedule 1
1.10.3.8.2 | [5 empty] | Monitor Project Plan and Schedule 2
1.10.3.8.3 | [5 empty] | Monitor Project Plan and Schedule 3
1.10.3.8.4 | [5 empty] | Monitor Project Plan and Schedule 4
1.10.3.8.5 | [5 empty] | Monitor Project Plan and Schedule 5
1.10.3.8.6 | [5 empty] | Monitor Project Plan and Schedule 6
1.10.3.8.7 | [5 empty] | Monitor Project Plan and Schedule 7
1.10.3.8.8 | [5 empty] | Monitor Project Plan and Schedule 8
1.10.3.8.9 | [5 empty] | Monitor Project Plan and Schedule 9
1.10.3.8.10 | [5 empty] | Monitor Project Plan and Schedule 10
1.10.3.9 | [5 empty] | Monitor Project Risks
1.10.3.9.1 | [5 empty] | Monitor Project Risks 1
1.10.3.9.2 | [5 empty] | Monitor Project Risks 2
1.10.3.9.3 | [5 empty] | Monitor Project Risks 3
1.10.3.9.4 | [5 empty] | Monitor Project Risks 4
1.10.3.9.5 | [5 empty] | Monitor Project Risks 5
1.10.3.10 | [5 empty] | Monitor Stakeholder Involvement Plan
1.10.3.10.1 | [5 empty] | Monitor Stakeholder Involvement Plan 1
1.10.3.10.2 | [5 empty] | Monitor Stakeholder Involvement Plan 2
1.10.3.10.3 | [5 empty] | Monitor Stakeholder Involvement Plan 3
1.10.3.10.4 | [5 empty] | Monitor Stakeholder Involvement Plan 4
1.10.3.10.5 | [5 empty] | Monitor Stakeholder Involvement Plan 5
1.10.3.11 | [5 empty] | Monitor Data Management Plan
1.10.3.11.1 | [5 empty] | Monitor Data Management Plan 1
1.10.3.11.2 | [5 empty] | Monitor Data Management Plan 2
1.10.3.11.3 | [5 empty] | Monitor Data Management Plan 3
1.10.3.11.4 | [5 empty] | Monitor Data Management Plan 4
1.10.3.11.5 | [5 empty] | Monitor Data Management Plan 5
1.10.4 | [5 empty] | Project Quality Assurance
1.10.4.1 | [5 empty] | Conduct Process Reviews ( Including Process Compliance Checks and Verification) | QA Analyst
1.10.4.1.1 | [5 empty] | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 1
1.10.4.1.2 | [5 empty] | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 2
1.10.4.1.3 | [5 empty] | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 3
1.10.4.1.4 | [5 empty] | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 4
1.10.4.1.5 | [5 empty] | Conduct Process Reviews ( Including Process Compliance Checks and Verification) 5
1.10.4.2 | [5 empty] | Track and Verify NC Closure
1.10.4.2.1 | [5 empty] | Track and Verify NC Closure 1
1.10.4.2.2 | [5 empty] | Track and Verify NC Closure 22
1.10.4.2.3 | [5 empty] | Track and Verify NC Closure 23
1.10.4.3 | [5 empty] | Verify Closure of Review Defect found in Work Product Review(s)
1.10.4.3.1 | [5 empty] | Verify Closure of Review Defect found in Work Product Review(s) 1
1.10.4.3.2 | [5 empty] | Verify Closure of Review Defect found in Work Product Review(s) 21
1.10.4.3.3 | [5 empty] | Verify Closure of Review Defect found in Work Product Review(s) 22
1.10.4.3.4 | [5 empty] | Verify Closure of Review Defect found in Work Product Review(s) 23
1.10.4.4 | [5 empty] | Review Supplier's Process | QA Analyst
1.10.4.4.1 | [5 empty] | Review Supplier's Process 1
1.10.4.4.2 | [5 empty] | Review Supplier's Process 2
1.10.4.4.3 | [5 empty] | Review Supplier's Process 3
1.10.4.4.4 | [5 empty] | Review Supplier's Process 4
1.10.4.4.5 | [5 empty] | Review Supplier's Process 5
1.10.5 | [5 empty] | Configuration Management
1.10.5.1 | [5 empty] | Update Change Register with Status of CR's | CM Lead
1.10.5.1.1 | [5 empty] | Update Change Register with Status of CR's 1 | CM Lead
1.10.5.1.2 | [5 empty] | Update Change Register with Status of CR's 2 | CM Lead
1.10.5.1.3 | [5 empty] | Update Change Register with Status of CR's 3 | CM Lead
1.10.5.1.4 | [5 empty] | Update Change Register with Status of CR's 4 | CM Lead
1.10.5.1.5 | [5 empty] | Update Change Register with Status of CR's 5 | CM Lead
1.10.5.2 | [5 empty] | Create Baselines of the CIs | CM Lead
1.10.5.2.1 | [5 empty] | Create Baselines of the CIs 1
1.10.5.2.2 | [5 empty] | Create Baselines of the CIs 2
1.10.5.2.3 | [5 empty] | Create Baselines of the CIs 3
1.10.5.2.4 | [5 empty] | Create Baselines of the CIs 4
1.10.5.3 | [5 empty] | Generate Configuration Status Accounting Report | CM Lead
1.10.5.3.1 | [5 empty] | Generate Configuration Status Accounting Report 1
1.10.5.3.2 | [5 empty] | Generate Configuration Status Accounting Report 2
1.10.5.3.3 | [5 empty] | Generate Configuration Status Accounting Report 12
1.10.5.4 | [5 empty] | Verify Backup and Disaster Recovery | CM Lead
1.10.5.4.1 | [5 empty] | Verify Backup and Disaster Recovery 1
1.10.5.4.2 | [5 empty] | Verify Backup and Disaster Recovery 2

## Small Project
3
WBS |  | Task Name | Duration |  |  | Resource Names
115.5
1 | Plan Phase (Small) |  |  | 25.5
| 1.1 | Develop Process Design |  |  | 4.5
| 1.2 | Develop Business Requirements |  |  | 3
| 1.3 | Conduct Project Readiness Review |  |  | 3
| 1.4 | Develop Initial Project Plan |  |  | 3
| 1.5 | Perform Project Monitoring and Control |  |  | 3
| 1.6 | Develop Initial Deployment and Support Plans |  |  | 3
| 1.7 | Develop Supplier Management Plan |  |  | 3
| 1.8 | Conduct Plan Phase Tollgate Review |  |  | 3
2 | Define Phase (Small) |  |  | 27
| 2.1 | Initiate Define Phase |  |  | 3
| 2.2 | Perform Project Monitoring and Control |  |  | 3
| 2.3 | Develop and Analyze User and System Requirements |  |  | 3
| 2.4 | Manage Requirements |  |  | 3
| 2.5 | Create Software Architecture |  |  | 3
| 2.6 | Create Test Plans |  |  | 3
| 2.7 | Define Training Requirements |  |  | 3
| 2.8 | Revise Plans (project, operations, support, deployment) |  |  | 3
| 2.9 | Conduct Define Phase Tollgate Review |  |  | 3
3 | Design Phase (Small) |  |  | 24
| 3.1 | Perform Project Monitoring and Control |  |  | 3
| 3.2 | Create System Design |  |  | 3
| 3.3 | Allocate System Requirements |  |  | 3
| 3.4 | Develop Training Curriculum |  |  | 3
| 3.5 | Develop Test Cases |  |  | 3
| 3.6 | Revise Software Architecture Document |  |  | 3
| 3.7 | Revise Plans (project, operations, support, deployment) |  |  | 3
| 3.8 | Conduct Design Phase Tollgate Review |  |  | 3
4 | Build Phase (Small) |  |  | 24
| 4.1 | Perform Project Monitoring and Control |  |  | 3
| 4.2 | Code/Configure System |  |  | 3
| 4.3 | Develop System and User Documentation |  |  | 3
| 4.4 | Develop Training Materials |  |  | 3
| 4.5 | Conduct Testing |  |  | 3
| 4.6 | Revise Plans (project, operations, support, deployment) |  |  | 3
| 4.7 | Conduct Build Phase Tollgate Review |  |  | 3
5 | Deploy Phase (small) |  |  | 15
| 5.1 | Perform Project Monitoring and Control |  |  | 3
| 5.2 | Coordinate Site Implementation |  |  | 3
| 5.3 | Archive Project Documents |  |  | 3
| 5.4 | Revise Plans (project, operations, support, deployment) |  |  | 3
| 5.5 | Conduct Deploy Phase Tollgate Review |  |  | 3
6 |  | INSERT SUPPLIER PLAN(S) HERE
7 |  | INSERT OTHER PROCESS PLANS AS REQUIRED HERE