## Dashboard
Project | Test Project |  | Dashboard Accuracy |  | Product Owner | Jane Doe |  | Thresholds
Date | 2013-06-18 |  | Enough Data |  | Scrum Master | John Doe |  | Not Enough Data | 2 | sprints
[8 empty] | Almost Enough Data | 3 | sprints
Sprint Planning | Committed / Completed Ratio |  |  |  |  | Planning Health
| Last 4 Sprints |  |  |  | Trend
| 100% | 100% | 0% | 100% |  | Good | 1 | Planning (low/high) | 75% | 125%
| 2013-05-07 | 2013-05-21 | 2013-06-04 | 2013-06-18
Sprint Velocity | Planned / Actual Deviation |  |  |  |  | Velocity Health
| Last 4 Sprints |  |  |  | Trend
| -9.091% | 18.18% | -6.25% | -50% |  | Average | 2 | Velocity (low/high) | -10% | 10%
| 2013-05-07 | 2013-05-21 | 2013-06-04 | 2013-06-18
Framework | Info Radiation | Progress Indicator | Backlog Sized | Backlog Prioritized | Retros (last 4 sprints) | Framework Health |  | Backlog (sized/prioritized) | 75% | 25%
| Y | Y | 100% | 30.95% | 4 | Good | 1 | Retros | 4
| 0 | 0 | 0 | 1 | 0 | 2 | 4
Team | Composition |  | Size Health | Dedication Health | Team Building Activity
| Total | Split |  |  | Last | Days |  | Size (low/high) | 4 | 9
| 7 | 3 | Ideal | 42.86% | 2013-06-12 | 3061 |  | Dedication | 90%
[8 empty] | Team Build (days) | 30
Recent Change
Hardening Starts On:
Rough Burn Down Projection | Based on Planned Velocity, you will need |  |  | 3 | more sprints + hardening. | 2013-07-30 |  | Planned Velocity Last Sprint | 16 | points
| Based on Actual Velocity, you will need |  |  | 5 | more sprints + hardening. | 2013-08-27 |  | Actual Velocity Last Sprint | 8 | points
| Based on Avg. Act. Velocity, you will need |  |  | 4 | more sprints + hardening. | 2013-08-13 |  | Average Velocity (last 4) | 11.5 | points
Formulas:
Jane Doe = TODAY()-[Product Owner]
Jane Doe = IF([Backlog Prioritized]<>"---", E7+([Backlog Prioritized]*14), "Backlog not fully sized.")

## Data
Release | Sprint |  |  | Stories |  |  | Velocity |  |  | Framework |  |  | Team |  |  | Backlog |  |  | Release Rem. Pts. | Agile Coach
| # | Start | End | Commited | Completed | Ratio | Planned | Actual | Deviation | Radiate | Progress | Retro | Size | Split | Change | Story Count | Sized | Prioritized
Release 1 | 4 | 2013-06-04 | 2013-06-18 | 2 | 2 | 100% | 16 | 8 | -50% | Y | Y | Y | 7 | 3 | Y | 42 | 42 | 13 | 32 | N
Release 1 | 3 | 2013-05-21 | 2013-06-04 | 2 | 0 | 0% | 16 | 15 | -6.25% | Y | Y | Y | 7 | 3 | Y | 42 | 31 | 13 | 68 | N
Release 1 | 2 | 2013-05-07 | 2013-05-21 | 2 | 2 | 100% | 11 | 13 | 18.18% | Y | N | Y | 6 | 3 | N | 36 | 30 | 12 | 42 | N
Release 1 | 1 | 2013-04-22 | 2013-05-07 | 2 | 2 | 100% | 11 | 10 | -9.091% | Y | N | Y | 6 | 3 | N | 36 | 30 | 12 | 48 | N
Note:
To ensure an accurate dashboard, sprints should be inserted at row 3 and be in descending order (most recent sprint in row 3).
Note on E2: Len Lagestee: The number of stories committed during sprint planning to be completed during this sprint.
Note on F2: Len Lagestee: The number of actual stories accepted by the product owner during the sprint.
Note on G2: Len Lagestee: Calculated as the number of completed stories divided by the number of committed stories.
Note on H2: Len Lagestee: The planning velocity used to determine how many story points the team can complete during this sprint.
Note on I2: Len Lagestee: The actual number of story points accepted by the product owner durint this sprint.
Note on J2: Len Lagestee: Calculated as the percentage deviation between the planned velocity and the actual velocity.
Note on K2: Len Lagestee: Is the information radiator (task wall) created and in use by the team?
Note on L2: Len Lagestee: Did the team use a burndown or burnup chart this sprint?
Note on M2: Len Lagestee: Did the team hold a retrospective at the end of this sprint?
Note on N2: Len Lagestee: How many team members were on the team this sprint?
Note on O2: Len Lagestee: Of all the team members, how many of them were split across more than 1 project?
Note on P2: Len Lagestee: Did the team composition change? Were team members added or removed?
Note on Q2: Len Lagestee: How many stories are in your current product/project backlog?
Note on R2: Len Lagestee: How many backlog stories have been sized by the team?
Note on S2: Len Lagestee: How many backlog stories have been prioritized by the product owner?
Note on P3: Len Lagestee: Off-shore tester swapped out with an on-shore tester
Note on P4: Len Lagestee: New developer joined the team